## TELKOMSEL
Project Name : TELKOMSEL
1348 | 1399 | 1378 | 907 | 897 | 723 | 1399 | 1399 | 0 | 529 | 935 | 406 | 585 | 665 | 0 | 0 | 0 | 55 | 75 | 14 | 98 | 33 | 126 | 93 | 94 | 63 | 0 | 30 | 0 | 0 | 0
[10 empty] | Job Description | [6 empty] | Document |  |  |  |  | ESAR | [5 empty] | PR to Subcon
[10 empty] | Installation |  | Site Integration |  | ATP
No | Site ID NE | Site Name | Site ID FE | Site Name | NE-FE | SOW | PO Detail SOW | Project | PO Number Released | MOS Status (each SOW Date) | Installation Status | SI Date | SI Status | ATP Date | Punch list close date | ATP Status | SIR ID List that already approve by DC Region | email/transmittal submit SIR documents to QC | TSSR Documemt Submit Date | ATP Documemt Submit Date | BAST Approved Date | ESAR 1 SUBMITTED | ESAR 1 APPROVED | ESAR 2 SUBMITTED | ESAR 2 APPROVED | Document Complete Submit to Jakarta | Remark | 1st Milestone | 2nd Milestone | 3rd Milestone
1 | TSK152_W_N | CIKUTOMAS | NA | NA | TSK152 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-1 | 2012-08-15 | DONE | [7 empty] | 2012-08-28 |  |  | 2013-01-28 | 2013-02-13 | 2013-01-31
2 | TSK478_W_N | SUKASUKUR | NA | NA | TSK478 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-1 | 2012-08-24 | DONE | [7 empty] | 2012-08-28 |  |  | 2013-01-28 | 2013-02-13 | 2013-01-31
3 | TSK440_W_N | GALUNGGUNG | NA | NA | TSK440 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-1 | 2012-08-25 | DONE | [7 empty] | 2012-08-28 |  |  | 2013-01-28 | 2013-02-13 | 2013-01-31
4 | TSK474_W_N | PANCARGATUN | NA | NA | TSK474 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-1 | 2012-08-25 | DONE | [7 empty] | 2012-08-28 |  |  | 2013-01-28 | 2013-02-13 | 2013-01-31
5 | TSK129_W_N | DSKARYABAKTI | NA | NA | TSK129 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-13 | DONE | [7 empty] | 2012-09-17 |  |  | 2013-01-28 |  | 2013-01-31
6 | TSK135_W_N | COGREG | NA | NA | TSK135 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-14 | [8 empty] | 2012-09-17 |  |  | 2013-01-28 |  | 2013-01-31
7 | TSK465_W_N | KPMADUR | NA | NA | TSK465 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-18 | DONE | [7 empty] | 2012-09-21 |  |  | 2013-01-28 |  | 2013-01-31
8 | TSK466_W_N | BJNGRENCONG | NA | NA | TSK466 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-18 | DONE | [7 empty] | 2012-09-21 |  |  | 2013-01-28 |  | 2013-01-31
9 | TSK130_W_N | KPSDANGJAYA | NA | NA | TSK130 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-20 | DONE | [7 empty] | 2012-09-21 |  |  | 2013-01-28 |  | 2013-01-31
10 | TSK458_W_N | WANGUNWATI | NA | NA | TSK458 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-21 | DONE | [7 empty] | 2012-09-25 |  |  | 2013-01-28 |  | 2013-01-31
11 | TSK459_W_N | ANGGALASAN | NA | NA | TSK459 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-22 | DONE | [7 empty] | 2012-09-25 |  |  | 2013-01-28 |  | 2013-01-31
12 | TSK147_W_N | PETIRNUNGAL | NA | NA | TSK147 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-22 | DONE | [7 empty] | 2012-09-25 |  |  | 2013-01-28 |  | 2013-01-31
13 | TSK457 | BARENGKOK-GNGOONG | NA | NA | N/A | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-25 | [8 empty] | 2012-10-03 |  |  | 2013-01-28 |  | 2013-01-31
14 | GRT219_W_N | PAGERBUMI-CIGUGUR | NA | NA | GRT219 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-2 | 2012-09-27 | DONE | [7 empty] | 2012-10-03 |  |  | 2013-01-28 |  | 2013-01-31
15 | BDG256_W_N | TMLCICAHEUM-PASIRLEUTIK | NA | NA | BDG256 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091117097-49 | 2012-10-11 | DONE
16 | BDG551_W_N | BDGN-144-TBG (palasari raya) | NA | NA | BDG551 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091117097-50 | 2012-10-11 | DONE
17 | IND174_G_N | TBG-Bojongsari | NA | NA | IND174 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-4 | 2012-11-05 | DONE | [10 empty] | 2013-01-28 |  | 2013-01-31
18 | IND169_G_N | TBG-Tempel | NA | NA | IND169 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-4 | 2012-11-06 | DONE | [10 empty] | 2013-01-28 |  | 2013-01-31
19 | IND170_G_N | TBG-Lelea | NA | NA | IND170 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-4 | 2012-11-06 | DONE | [10 empty] | 2013-01-28 |  | 2013-01-31
20 | IND173_G_N | TBG-IndramayuSLT | NA | NA | IND173 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-4 | 2012-11-07 | DONE | [10 empty] | 2013-01-28 |  | 2013-01-31
21 | MJL123_W_N | Abdhalim-Sidamukti | NA | NA | MJL123 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091117097-49 | 2012-11-06
22 | BDG526_W_N | PLAZAIBCC | NA | NA | BDG526 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  |  | 2012-11-21 | DONE
23 | BDG769 | HTLHORIZON | NA | NA | BDG769 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  |  | 2012-12-08 | DONE
24 | BDG756 | APT.Majestic | NA | NA | BDG756 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  |  | 2012-12-07 | DONE
25 | TSK129_W_N | DSKARYABAKTI | NA | NA | TSK129 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-10-01 |  | 2012-10-01 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
26 | TSK458_W_N | WANGUNWATI | NA | NA | TSK458 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-10-09 |  | 2012-10-09 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
27 | TSK440_W_N | GALUNGGUNG | NA | NA | TSK440 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-4 | 2012-09-27 |  | 2012-09-27 | DONE | [8 empty] | 2013-03-08
28 | TSK474_W_N | PANCARGATUN | NA | NA | TSK474 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-4 | 2012-09-26 |  | 2012-09-26 | DONE | [8 empty] | 2013-03-08
29 | TSK478_W_N | SUKASUKUR | NA | NA | TSK478 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-4 | 2012-09-26 |  | 2012-09-26 | DONE | [8 empty] | 2013-03-08
30 | TSK152_W_N | CIKUTOMAS | NA | NA | TSK152 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-4 | 2012-08-31 |  | 2012-08-31 | DONE | [8 empty] | 2013-03-08
31 | TSK135_W_N | COGREG | NA | NA | TSK135 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-10-09 |  | 2012-10-09 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
32 | TSK457_W_N | BARENGKOK-GNGOONG | NA | NA | N/A | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-10-10 |  | 2012-10-10 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
33 | TSK465_W_N | KPMADUR | NA | NA | TSK465 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-09-26 |  | 2012-09-26 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
34 | TSK466_W_N | BJNGRENCONG | NA | NA | TSK466 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-09-27 |  | 2012-09-27 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
35 | TSK130_W_N | KPSDANGJAYA | NA | NA | TSK130 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-11-11 |  | 2012-11-11 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
36 | TSK459_W_N | ANGGALASAN | NA | NA | TSK459 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-09-28 |  | 2012-09-28 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
37 | TSK147_W_N | PETIRNUNGAL | NA | NA | TSK147 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-10-12 |  | 2012-10-12 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
38 | GRT219_W_N | PAGERBUMI-CIGUGUR | NA | NA | GRT219 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-7 | 2012-10-31 |  | 2012-10-31 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
39 | BDG256_W_N | TMLCICAHEUM-PASIRLEUTIK | NA | NA | BDG256 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  |  | 2012-11-06 |  | 2012-11-06 | DONE
40 | BDG551_W_N | BDGN-144-TBG (palasari raya) | NA | NA | BDG551 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  |  | 2012-11-07 |  | 2012-11-07 | DONE
41 | GRT270_G_N | TBG-MargahayuGRT | NA | NA | GRT270 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-12-08 |  | 2012-12-08 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
42 | GRT261_G_N | TBG-Wanaraja | NA | NA | GRT261 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-11-26 |  | 2012-11-26 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
43 | BDG351_G_N | Tbg-Manggahang | NA | NA | BDG351 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-12-07 |  | 2012-12-07 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
44 | KNG119_W_N | Maleber-Garawangi | NA | NA | KNG119 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-11-26 |  | 2012-11-26 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
45 | KNG119_G_N | Maleber-Garawangi | NA | NA | KNG119 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | 2012-11-21 |  | 2012-11-21 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
46 | MJL139_G_N | TBG-SINDANGWANGI | NA | NA | MJL139 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-12-06 |  | 2012-12-06 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
47 | CMS226_W_N | Pasirjaya-Jatinegara | NA | NA | CMS226 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-11-27 |  | 2012-11-27 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
48 | CMS226_G_N | Pasirjaya-Jatinegara | NA | NA | CMS226 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | 2012-11-21 |  | 2012-11-21 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
49 | GRT265_G_N | TBG-Ciarok | NA | NA | GRT265 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-11-27 |  | 2012-11-27 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
50 | KNG136_G_N | Nodal Tangkolo | NA | NA | KNG136 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-11-27 |  | 2012-11-27 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
51 | BDG926_W_N | CISARANTEN-CINGESED | NA | NA | BDG926 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-11-26 |  | 2012-11-26 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
52 | BDG343_W_N | Isat-Sekebungur | NA | NA | BDG343 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-12-01 |  | 2012-12-01 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
53 | BDG343_G_N | Isat-Sekebungur | NA | NA | BDG343 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | 2012-12-01 |  | 2012-12-01 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
54 | CJR417_G_N | TBG-CUGENANG | NA | NA | CJR417 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | 2012-12-28 |  | 2012-12-28 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
55 | CJR417_W_N | TBG-CUGENANG | NA | NA | CJR417 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-12-22 |  | 2012-12-22 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
56 | BDG648_G_N | ISAT-SUKAPURA | NA | NA | BDG648 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | 2012-11-29 |  | 2012-11-29 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
57 | GRT222_G_N | JATITUJUH-SUKANIMJLK | NA | NA | GRT222 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | 2013-01-18 |  | 2013-01-18 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
58 | IND169_G_N | TBG-Lelea | NA | NA | IND169 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-12-13 |  | 2012-12-13 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
59 | IND170_G_N | TBG-Tempel | NA | NA | IND170 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-11-26 |  | 2012-11-26 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
60 | BDG984_W_N | CIGANITRI-MARGACINTA | NA | NA | BDG984 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-10-02 |  | 2012-10-02 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
61 | IBCC_W_N | IBCC | NA | NA | BDG526 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091115745-3 | 2012-12-30 |  | 2012-12-30 | DONE | [8 empty] | 2013-03-08
62 | CRB561_G_N | TBG-BEBER | NA | NA | CRB561 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-12-06 |  | 2012-12-06 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
63 | BDG465_W_N | Isat-NANJUNGCPATIK | NA | NA | BDG465 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-12-01 |  | 2012-12-01 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
64 | BDG465_G_N | Isat-NANJUNGCPATIK | NA | NA | BDG465 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | 2012-12-01 |  | 2012-12-01 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
65 | CMI083_W_N | TBG.BAROS | NA | NA | CMI083 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-12-13 |  | 2012-12-13 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
66 | MJL123_W_N | ABDULHALIM-SIDAMUKTI | NA | NA | MJL123 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091115745-4 | 2012-12-13 |  | 2012-12-13 | DONE | [8 empty] | 2013-03-08
67 | IND174_G_N | TBG.BOJONGSARI | NA | NA | IND174 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-12-12 |  | 2012-12-12 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
68 | IND173_G_N | TBG.INDRAMAYUSLT | NA | NA | IND173 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-12-12 |  | 2012-12-12 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
69 | KNG132_G_N | SINDANGSARI | NA | NA | KNG132 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2012-12-14 |  | 2012-12-14 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
70 | CRB561 ex CRB531_W_N_583-585 | TBG BEBER | NA | NA | CRB561 | CROSSCONNECT | E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-11 | 2012-12-18 |  | 2012-12-18 | DONE
71 | GRT217_G_N | BOJONG-NAGREK | NA | NA | GRT217 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | 2012-12-20 |  | 2012-12-20 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
72 | KNG131_G_N | TBG-Kelapagunung | NA | NA | KNG131 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2013-03-19 |  | 2013-03-19 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
73 | BDG769_W_N | Hotel Horison | NA | NA | BDG769 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091115745-3 | 2012-12-24 |  | 2012-12-24 | DONE | [8 empty] | 2013-03-08
74 | Aptmajestic_W_N | Aptmajestic | NA | NA | BDG756 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091115745-3 | 2012-12-13 |  | 2012-12-13 | DONE | [8 empty] | 2013-03-08
75 | CJR411_W_N | XL-Kotabunga | NA | NA | CJR411 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-12-28 |  | 2012-12-28 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
76 | BDG616_W_N | BDGN-181-PABxl | NA | NA | BDG616 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-12-27 |  | 2012-12-27 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
77 | TSK129_W_N | DSKARYABAKTI | NA | NA | TSK129 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-01-06 | 2012-09-29 | 2012-10-01 | DONE |  |  |  | 2012-12-19 | 2012-12-27 |  | 2012-11-27 |  | 2012-12-26 | 2013-02-18 | 2013-02-25
78 | TSK458_W_N | WANGUNWATI | NA | NA | TSK458 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-01-30 | 2012-10-01 | 2012-10-09 | DONE |  |  |  | 2012-12-19 | 2012-12-27 |  | 2012-11-28 |  | 2012-12-20 | 2013-02-18 | 2013-02-25
79 | TSK440_W_N | GALUNGGUNG | NA | NA | TSK440 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-16 | 2013-10-30 | 2012-09-24 | 2012-09-27 | DONE |  |  |  | 2013-02-14 | 2013-03-25 |  | 2013-02-05 | 2013-03-22
80 | TSK474_W_N | PANCARGATUN | NA | NA | TSK474 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-16 | 2013-01-18 | 2012-09-24 | 2012-09-26 | DONE |  |  |  | 2012-12-19 | 2012-12-27 |  | 2012-11-28 | 2013-03-22
81 | TSK478_W_N | SUKASUKUR | NA | NA | TSK478 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-16 | 2013-01-18 | 2012-09-24 | 2012-09-26 | DONE
82 | TSK152_W_N | CIKUTOMAS | NA | NA | TSK152 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-16 | 2013-01-18 | 2012-08-28 | 2012-08-31 | DONE |  |  |  | 2013-02-13 |  |  | 2013-02-11
83 | TSK135_W_N | COGREG | NA | NA | TSK135 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-01-22 | 2012-09-29 | 2012-10-09 | DONE |  |  |  | 2012-12-19 | 2012-12-27 |  |  |  | 2012-12-26 | 2013-02-18 | 2013-02-25
84 | TSK457_W_N | BARENGKOK-GNGOONG | NA | NA | N/A | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-01-19 | 2012-09-29 | 2012-10-10 | DONE |  |  |  | 2013-02-14 |  |  | 2013-02-11 | 2013-03-22
85 | TSK465_W_N | KPMADUR | NA | NA | TSK465 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-01-29 | 2012-10-01 | 2012-09-26 | DONE |  |  |  | 2012-12-19 | 2012-12-27 |  |  |  | 2012-12-26 | 2013-02-18 | 2013-02-25
86 | TSK466_W_N | BJNGRENCONG | NA | NA | TSK466 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-02-20 | 2012-10-01 | 2012-09-27 | DONE |  |  |  | 2012-12-19 | 2012-12-27 |  | 2012-11-22 | 2013-03-22 | 2012-12-20 | 2013-02-18 | 2013-02-25
87 | TSK130_W_N | KPSDANGJAYA | NA | NA | TSK130 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-01-26 | 2012-10-09 | 2012-11-11 | DONE |  |  |  | 2013-02-12 |  |  | 2013-02-11 | 2013-03-22
88 | TSK459_W_N | ANGGALASAN | NA | NA | TSK459 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-01-29 | 2012-10-01 | 2012-09-28 | DONE |  |  |  | 2012-12-27 |  |  | 2012-12-20
89 | TSK147_W_N | PETIRNUNGAL | NA | NA | TSK147 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-01-28 | 2012-09-30 | 2012-10-12 | DONE |  |  |  | 2012-12-19 | 2012-12-27 |  | 2012-11-22 | 2013-03-22 | 2012-12-20 | 2013-02-18 | 2013-02-25 | 2013-03-20
90 | GRT219_W_N | PAGERBUMI-CIGUGUR | NA | NA | GRT219 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-24 | 2013-01-28 | 2012-10-19 | 2012-10-31 | DONE |  |  |  | 2013-03-04 |  |  | 2013-02-12
91 | BDG256_W_N | TMLCICAHEUM-PASIRLEUTIK | NA | NA | BDG256 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  |  | 2012-12-12 | 2012-10-25 | 2012-11-06 | DONE |  |  |  | 2013-03-04 |  |  | 2013-02-13 | 2013-03-22
92 | BDG551_W_N | BDGN-144-TBG (palasari raya | NA | NA | BDG551 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  |  | 2013-02-13 | 2012-10-31 | 2012-11-07 | DONE
93 | GRT270_G_N | TBG-MargahayuGRT | NA | NA | GRT270 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2013-02-13 | 2012-12-06 | 2012-12-08 | DONE
94 | GRT261_G_N | TBG-Wanaraja | NA | NA | GRT261 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2013-02-13 | 2012-11-13 | 2012-11-26 | DONE
95 | BDG351_G_N | Tbg-Manggahang | NA | NA | BDG351 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2012-11-07 | 2012-11-10 | 2012-12-07 | DONE
96 | KNG119_W_N | Maleber-Garawangi | NA | NA | KNG119 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2012-11-09 | 2012-11-12 | 2012-11-26 | DONE
97 | KNG119_G_N | Maleber-Garawangi | NA | NA | KNG119 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2012-11-09 | 2012-11-12 | 2012-11-21 | DONE
98 | MJL139_G_N | TBG-SINDANGWANGI | NA | NA | MJL139 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2012-12-06 | 2012-11-12 | 2012-12-06 | DONE
99 | CMS226_W_N | Pasirjaya-Jatinegara | NA | NA | CMS226 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-01-31 | 2012-11-13 | 2012-11-27 | DONE |  |  |  | 2013-03-04 | 2013-03-19 |  | 2013-01-19 | 2013-03-22 | 2013-03-20 |  | 2013-03-20
100 | CMS226_G_N | Pasirjaya-Jatinegara | NA | NA | CMS226 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2013-02-16 | 2012-11-13 | 2012-11-21 | DONE |  |  |  | 2013-03-06
101 | GRT265_G_N | TBG-Ciarok | NA | NA | GRT265 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2012-12-28 | 2012-11-13 | 2012-11-27 | DONE
102 | KNG136_G_N | Nodal Tangkolo | NA | NA | KNG136 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2013-02-18 | 2012-11-15 | 2012-11-27 | DONE
103 | BDG926_W_N | CISARANTEN-CINGESED | NA | NA | BDG926 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-02-16 | 2012-11-24 | 2012-11-26 | DONE |  |  |  | 2012-12-26 | 2012-12-27 |  | 2012-12-05 |  | 2013-02-18 | 2013-02-25
104 | BDG343_W_N | Isat-Sekebungur | NA | NA | BDG343 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-02-16 | 2012-11-21 | 2012-12-01 | DONE | [6 empty] | 2013-01-14
105 | BDG343_G_N | Isat-Sekebungur | NA | NA | BDG343 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2013-02-16 | 2012-11-21 | 2012-12-01 | DONE | [6 empty] | 2013-03-08
106 | CJR417_W_N | TBG-CUGENANG | NA | NA | CJR417 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2012-11-17 | 2012-11-21 | 2012-12-28 | DONE |  |  |  | 2012-12-27 | 2012-12-28 |  | 2013-03-03 | 2013-03-22 | 2013-02-18 | 2013-02-25 | 2013-03-20
107 | CJR417_G_N | TBG-CUGENANG | NA | NA | CJR417 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2012-11-17 | 2012-11-21 | 2012-12-22 | DONE | [6 empty] | 2013-02-08
108 | BDG648_G_N | ISAT-SUKAPURA | NA | NA | BDG648 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2013-02-26 | 2012-11-21 | 2012-11-29 | DONE
109 | GRT222_G_N | JATITUJUH-SUKANIMJLK | NA | NA | GRT222 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2012-11-17 | 2012-11-24 | 2013-01-27 | DONE
110 | IND169_G_N | TBG-Lelea | NA | NA | IND169 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2013-02-19 | 2012-11-25 | 2012-12-13 | DONE | [6 empty] | 2013-02-08
111 | IND170_G_N | TBG-Tempel | NA | NA | IND170 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2013-03-20 | 2012-11-25 | 2012-11-26 | DONE
112 | BDG984_W_N | CIGANITRI-MARGACINTA | NA | NA | BDG984 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-02-27 | 2012-11-30 | 2012-10-02 | DONE |  |  |  | 2012-12-26 | 2012-12-27 |  | 2012-12-05 | 2013-03-22 | 2013-02-18 | 2013-02-25
113 | BDG526_W_N | IBCC | NA | NA | BDG526 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091115556-2 | 2013-02-25 | 2012-11-29 | 2012-12-30 | DONE |  |  |  | 2012-12-27 | 2012-12-28 |  | 2012-12-10 |  | 2013-01-31 | 2013-02-25
114 | CRB561_G_N | TBG.BEBER | NA | NA | CRB561 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2012-11-28 | 2012-11-30 | 2012-12-06 | DONE |  |  |  | 2012-01-07 | 2013-01-17 |  | 2012-02-21 |  | 2013-01-07 | 2013-02-18 | 2013-02-25
115 | BDG465_W_N | Isat-NANJUNGCPATIK | NA | NA | BDG465 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-02-27 | 2012-11-27 | 2012-12-01 | DONE | [6 empty] | 2013-01-15
116 | BDG465_G_N | Isat-NANJUNGCPATIK | NA | NA | BDG465 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2013-02-26 | 2012-12-01 | 2012-12-01 | DONE | [6 empty] | 2013-02-08
117 | CMI083_W_N | TBG.BAROS | NA | NA | CMI083 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2012-12-04 | 2012-12-05 | 2012-12-13 | DONE | [6 empty] | 2013-01-16
118 | MJL123_W_N | ABDULHALIM-SIDAMUKTI | NA | NA | MJL123 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091115556-1 | 2012-12-08 | 2012-12-10 | 2012-12-13 | DONE |  |  |  | 2013-03-20 |  |  | 2013-02-15
119 | IND174_G_N | TBG.BOJONGSARI | NA | NA | IND174 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2013-02-27 | 2012-11-07 | 2012-12-12 | DONE
120 | IND173_G_N | TBG.INDRAMAYUSLT | NA | NA | IND173 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2013-02-27 | 2012-12-10 | 2012-12-12 | DONE |  |  |  | 2012-01-07 | 2013-01-17 |  | 2013-02-21 |  | 2013-01-07 | 2013-02-18 | 2013-02-25
121 | KNG132_G_N | SINDANGSARI | NA | NA | KNG132 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2012-12-08 | 2012-12-10 | 2012-12-14 | DONE
122 | CRB561_W_N | TBG BEBER | NA | NA | CRB561 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  |  | 2012-12-12 | 2013-12-14 | 2012-12-18 | DONE |  |  |  | 2012-01-07 | 2013-01-17
123 | GRT217_G_N | BOJONG-NAGREK | NA | NA | GRT217 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2012-12-14 | 2012-12-16 | 2012-12-20 | DONE |  |  |  | 2013-03-06 |  |  | 2013-02-08
124 | KNG131_G_N | TBG-Kelapagunung | NA | NA | KNG131 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2013-03-15 | 2013-03-17 | 2013-03-18 | DONE | [13 empty] | KNG131 comm case; materials return back to WH
125 | BDG769_W_N | Hotel Horison | NA | NA | BDG769 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091115556-2 | 2012-12-20 | 2012-12-24 | 2012-12-24 | DONE |  |  |  | 2013-01-08 | 2013-01-17 |  | 2013-01-09 |  | 2013-01-31 | 2013-02-25
126 | BDG756_W_N | Aptmajestic | NA | NA | BDG756 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091115556-2 | 2012-12-12 | 2012-12-13 | 2012-12-13 | DONE |  |  |  | 2013-01-07 | 2013-01-17 |  | 2013-01-04
127 | CJR411_W_N | XL-Kotabunga | NA | NA | CJR411 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2012-12-17 | 2012-12-19 | 2012-12-28 | DONE |  |  |  | 2013-01-22 | 2013-03-20 |  | 2013-01-04 |  | 2013-03-20
128 | CJR412_W_N | XL-Lembah Hijau | NA | NA | CJR412 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2012-12-17 | 2012-12-19 | 2012-12-28 | DONE |  |  |  | 2013-01-07 | 2013-01-23 |  | 2013-01-14
129 | BDG616_W_N | BDGN-181-PABxl | NA | NA | BDG616 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2012-12-17 | 2012-12-23 | 2012-12-27 | DONE |  |  |  | 2012-12-27 | 2013-01-04 |  | 2013-01-04 |  | 2013-02-18 | 2013-02-25
130 | BDG600_W_N | XL-Bumi Panyawangan | NA | NA | BDG600 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2012-12-20 | 2012-12-24 | 2012-12-26 | DONE | [6 empty] | 2013-01-18
131 | TSK152 | CIKUTOMAS | TSK017 | KARANGNUNGGAL | TSK152-TSK017 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-14 | 2012-08-28 | 2012-08-30 | 2012-08-30 | DONE | [6 empty] | 2012-11-27 | 2012-11-21
132 | TSK005 | INDIHIYANG | TSK013 | KARANGRESIK | TSK005-TSK013 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-15 | 2012-08-28 | 2012-08-29 | 2012-08-30 | DONE |  |  |  |  | 2013-01-25 |  | 2013-01-22
133 | TSK079 | SALAWU | TSK072 | CISARUNI | TSK079-TSK072 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-15 | 2012-08-28 | 2012-08-29 | 2012-09-11 | DONE |  |  |  |  | 2013-01-25 |  | 2013-01-22
134 | TSK133 | REJATANJUNG-SALAWU | TSK079 | SALAWU | TSK133-TSK079 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-15 | 2012-08-14 | 2012-08-17 | 2012-08-29 | DONE |  |  |  |  | 2013-02-15
135 | TSK135 | COGREG | CMS079 | CIRANCA | TSK135-CMS079 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-17 | 2012-09-14 | 2012-09-14 | 2012-09-14 | DONE |  |  |  | 2013-02-22 | 2013-02-14 |  | 2012-11-20 | 2012-12-27 | 2013-02-25 | 2013-02-26
136 | TSK465 | KPMADUR | TSK403 | HONJE | TSK465-TSK403 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-17 | 2012-09-20 | 2012-09-21 | 2012-09-21 | DONE | [6 empty] | 2012-11-22 | 2013-03-21
137 | TSK403 | HONJE | TSK017 | KARANGNUNGGAL | TSK403-TSK017 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-17 | 2012-09-28 | 2012-09-20 | 2012-09-21 | DONE | [6 empty] | 2012-11-27 | 2013-03-21
138 | TSK396 | PAMIJAHAN | TSK017 | KARANGNUNGGAL | TSK396-TSK017 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-17 | 2012-09-19 | 2012-09-20 | 2012-09-21 | DONE | [6 empty] | 2012-11-23
139 | TSK130 | KPSDANGJAYA | TSK059 | CILUMBA | TSK130-TSK059 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-17 | 2013-09-19 | 2012-09-20 | 2012-09-22 | DONE | [6 empty] | 2012-11-23 | 2013-03-21
140 | TSK458 | WANGUNWATI | TSK059 | CILUMBA | TSK458-TSK059 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-17 | 2012-09-19 | 2012-09-20 | 2012-09-22 | DONE |  |  |  |  | 2013-02-19 |  | 2012-11-21 | 2013-03-21
141 | TSK142 | BARENGKOK | TSK032 | CIKALONG | TSK142-TSK032 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-17 | 2012-09-19 | 2012-09-20 | 2012-09-22 | DONE | [6 empty] | 2012-11-20
142 | TSK457 | BARENGKOK GNGOONG | TSK142 | BARENGKOK | BARENGKOK GNGOONG-TSK142 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-17 | 2012-09-19 | 2012-09-20 | 2012-09-22 | DONE | [6 empty] | 2013-02-26
143 | GRT219 | PAGERBUMI CIGUGUR | CMS022 | CIGUGUR | GRT219-CMS022 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-18 | 2012-08-15 | 2012-10-16 | 2012-10-17 | DONE
144 | CMS079 | CIRANCA | TSK059 | CILUMBA | CMS079-TSK059 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-18 |  | 2012-09-20 | 2012-10-02 | DONE |  |  |  | 2013-02-02 | 2013-01-29 |  |  | 2013-03-21 | 2013-02-07 | 2013-02-13
145 | TSK129 | DSKARYABAKTI | TSK011 | KAWALU | TSK129-TSK011 | MW NEW | MW PDH 1.8m 2: Installation and Commissioning |  | 1091098837-19 | 2012-10-05 | 2012-10-05 | 2012-10-06 | DONE | [6 empty] | 2012-11-22
146 | TSK059 | CILUMBA | TSK017 | KARANGNUNGGAL | TSK059-TSK017 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-18 | 2012-10-07 | 2012-10-08 | 2012-10-09 | DONE |  |  |  |  | 2013-02-14 |  | 2012-11-21 | 2013-01-31
147 | TSK032 | CIKALONG | TSK017 | KARANGNUNGGAL | TSK032-TSK017 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-18 | 2012-10-07 | 2012-10-08 | 2012-10-09 | DONE |  |  |  | 2013-02-22 | 2013-02-14 |  | 2012-11-21 |  | 2013-02-25 | 2013-02-26
148 | CMS022 | CIGUGUR | CMS020 | CIMERAK | CMS022-CMS020 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-18 | 2012-10-16 | 2012-10-17 | 2012-10-18 | DONE
149 | MJL010 | RJGALUHKOTA | MJL019 | WIKA | MJL010-MJL019 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-32 | 2012-10-30 | 2012-10-31 | 2012-10-31 | DONE |  |  |  |  | 2013-02-14 |  | 2013-01-26
150 | MJL019 | WIKA | SMD019 | UJUNGJAYA | MJL019-SMD019 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-32 | 2012-10-30 | 2012-10-31 | 2012-10-31 | DONE |  |  |  |  | 2013-01-08 |  | 2012-11-28
151 | SMD019 | UJUNGJAYA | MJL002 | KADIPATEN | SMD019-MJL002 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-32 | 2012-10-30 | 2012-10-31 | 2012-10-31 | DONE |  |  |  |  | 2013-01-29 |  | 2012-11-28 |  | 2013-04-05
152 | IND014 | PEKANDANGAN | IND006 | LOBENER | IND014-IND006 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091115556-5 | 2012-12-06 | 2012-12-07 | 2012-12-08 | DONE |  |  |  |  | 2013-01-25 |  | 2013-01-16
153 | IND006 | LOBENER | IND008 | JATIBARANG | IND020-IND008 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091115556-5 | 2012-10-25 | 2012-12-08 | 2012-12-08 | DONE |  |  |  |  | 2013-02-15 |  | 2013-01-21
154 | SUB020 | HAURGLSKOTA | SUB029 | JAYAMULYA | SUB020-SUB029 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091115556-5 | 2012-10-25 | 2012-10-30 | 2012-10-31 | DONE |  |  |  | 2013-02-25 | 2013-01-23 |  | 2013-01-14
155 | CMS006 | RANCAHCIAMIS | TSK042 | NANGGEWER | CMS006-TSK042 | MW NEW | MW PDH 1.8m 2: Installation and Commissioning |  | 1091098837-32 | 2012-10-25 | 2012-10-30 | 2012-10-31 | DONE |  |  |  |  | 2013-02-14
156 | KNG136 | TBG NODAL TANGKOLO | CMS006 | RANCAHCIAMIS | KNG136-CMS006 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-31 | 2012-10-29 | 2012-11-21 | 2012-11-21 | DONE | [6 empty] | 2013-02-27
157 | KNG132 | TBG SINDANGSARI | KNG006 | CIPORANG | KNG132-KNG006 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-30 | 2012-10-29 | 2012-11-09 | 2012-11-09 | DONE |  |  |  | 2013-02-02 | 2013-01-29 |  | 2013-01-16 | 2013-03-21 | 2013-02-07 | 2013-02-13 | 2013-03-20
158 | CRB561 | TBG BEBER | CRB021 | BEBER | CRB561-CRB021 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-30 | 2012-10-29 | 2012-11-09 | 2012-11-09 | DONE |  |  |  | 2013-02-25 | 2013-01-26 |  | 2013-01-16 |  | 2013-02-07 | 2013-02-13
159 | IND169 | TBG TEMPEL | IND010 | LOSARANG | IND169-IND010 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-30 | 2012-10-29 | 2012-11-19 | 2012-11-20 | DONE | [6 empty] | 2013-01-17
160 | IND170 | TBG LELEA | IND010 | LOSARANG | IND170-IND010 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-30 | 2012-10-29 | 2012-11-19 | 2012-11-20 | DONE | [6 empty] | 2013-01-23 | 2013-03-21
161 | SMD010 | DARMARAJAM | SMD023 | CISITUSMDM | SMD010-SMD023 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-11-09 | 2013-01-10 | 2013-01-10 | DONE | [6 empty] | 2013-01-17
162 | BDG320 | SANGKANHURIP | BDG021 | CISEAH | BDG320-BDG021 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-11-09 | 2012-11-13 | 2012-11-14 | DONE |  |  |  | 2013-01-07 | 2012-12-27 |  | 2012-12-21 |  | 2013-02-18 | 2013-02-25
163 | BDG465 | Isat-NANJUNGCPATIK | BDG021 | CISEAH | BDG465-BDG021 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-11-10 | 2012-11-13 | 2012-11-14 | DONE
164 | BDG343 | Isat-Sekebungur | BDG320 | SANGKANHURIP | BDG343-BDG320 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-11-10 | 2012-11-13 | 2012-11-15 | DONE |  |  |  |  | 2013-02-15 |  | 2013-03-15 | 2013-03-21 | 2013-03-13 | 2013-03-21 | 2013-03-20
165 | SMD023 | CISITUS | SMD004 | CIMALAKA | SMD023-SMD004 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-27 | 2012-11-10 | 2012-11-13 | 2012-11-15 | DONE | [6 empty] | 2013-01-14
166 | CJR417 | TBG-CUGENANG | BDG251 | CISALAK | CJR417-BDG251 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-11-19 | 2012-11-21 | 2012-11-22 | DONE |  |  |  |  | 2013-02-07 |  | 2013-01-22 | 2013-03-21
167 | BDG648 | ISAT-SUKAPURA | BDG112 | PSRCIPARAY | BDG648-BDG112 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-27 | 2012-11-19 | 2012-11-21 | 2012-11-29 | DONE
168 | GRT222 | JATITUJUH-SUKANIMJLK | MJL016 | LIGUNG | GRT222-MJL016 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-11-17 | 2012-11-24 | 2012-11-24 | DONE |  |  |  | 2012-12-27 | 2012-12-27 |  | 2012-12-21 | 2012-12-29 | 2013-02-18 | 2013-02-25
169 | CMI063 | Cibaligo-Kebonkopi | BDG147 | MARGAASIH | CMI063-BDG147 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-11-17 | 2013-01-19 | 2013-01-19 | DONE |  |  |  | 2013-02-14 | 2013-02-07 |  | 2013-02-22 | 2013-03-21 | 2013-02-25 | 2013-02-26 | 2013-03-20
170 | GRT217 | BOJONG-NAGREK | BDG087 | CICALENGKA | GRT217-BDG087 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091115556-4 | 2012-11-17 | 2012-12-07 | 2012-12-08 | DONE |  |  |  | 2012-12-27 | 2012-12-27 |  | 2012-12-21 | 2013-01-31
171 | KNG119 | Maleber-Garawangi | KNG005 | CIAWIGEBANG | KNG119-KNG005 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-11-17 | 2012-11-21 | 2012-11-21 | DONE |  |  |  | 2013-01-17 | 2013-01-10 |  | 2013-01-28 | 2013-01-30 | 2013-02-18 | 2013-02-25
172 | IND165 | TBG-KARANGDEMPEL | IND015 | KARANGAMPEL | IND165-IND015 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-11-17 | 2012-11-19 | 2012-11-21 | DONE |  |  |  |  | 2013-02-06 |  | 2013-02-13
173 | CRB021 | BEBER | CRB007 | SUMBER | CRB021-CRB007 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091115556-4 | 2012-11-26 | 2012-11-29 | 2012-11-30 | DONE | [6 empty] | 2013-01-21
174 | KNG131 | TBG.KLPGUNUNG | KNG011 | GN.KELING | KNG131-KNG011 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-30 | 2012-11-26 | 2012-11-29 | 2012-11-30 | DONE |  |  |  | 2013-01-25 | 2013-01-25 |  | 2013-01-21 | 2013-03-21 | 2013-02-07 | 2013-02-13
175 | IND171 | TBG.WANAKAYA | SUB020 | HAURGLSKOTA | IND171-SUB020 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-30 | 2012-11-26 | 2012-11-29 | 2012-11-30 | DONE |  |  |  | 2012-12-28 | 2012-12-27 |  | 2012-12-21 | 2013-03-21 | 2013-02-18 | 2013-02-25
176 | CMI008 | CIBEBERCMH | CMI009 | BAROS | CMI008-CMI009 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-12-05 | 2012-12-07 | 2012-12-07 | DONE
177 | BDG087 | CICALENGKA | BDG166 | CICALNGKBSC | BDG087-BDG166 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091115556-4 | 2012-12-14 | 2012-12-12 | 2012-12-18 | DONE |  |  |  | 2013-02-25 | 2013-01-24 |  | 2012-12-21
178 | BDG029 | CICADAS | BDG079 | BABAKANSARI | BDG029-BDG079 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2012-12-08 | 2012-12-12 | 2012-12-12 | DONE |  |  |  | 2013-01-17 | 2013-01-09 |  | 2013-01-07 |  | 2013-02-18 | 2013-02-25
179 | COD032 | CombatCipanas | BOO067 | CUGCIPANAS | COD032-BOO067 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091115556-4 | 2013-01-04 | 2013-01-05 | 2013-01-06 | DONE
180 | BOO067 | CUGCIPANAS | CJR001 | GUNUNGGEDE | BOO067-CJR001 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091115556-4 | 2013-01-04 | 2013-01-05 | 2013-01-06 | DONE
181 | CJR001 | GUNUNGGEDE | CJR011 | BSCCIANJUR | CJR001-CJR011 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091115556-4 | 2013-01-04 | 2013-01-05 | 2013-01-06 | DONE |  |  |  |  | 2013-02-04 |  | 2013-02-12
182 | TSK478_W_N | SUKASUKUR | NA | NA | TSK478 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2012-12-18 |  |  | DONE | [8 empty] | 2013-02-18 | 2013-03-11 | 2013-02-18 | 2013-03-11
183 | TSK474_W_N | PANCARGATUN | NA | NA | TSK474 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 |  |  |  | DONE | [8 empty] | 2013-02-18 | 2013-03-11 | 2013-02-18 | 2013-03-11
184 | TSK440_W_N | GALUNGGUNG | NA | NA | TSK440 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2012-12-18 |  |  | DONE | [8 empty] | 2013-02-18 | 2013-03-11 | 2013-02-18 | 2013-03-11
185 | TSK129_W_N | DSKARYABAKTI | NA | NA | TSK129 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE |  |  |  |  | 2013-02-20 |  |  |  | 2013-02-18 | 2013-03-11 | 2013-02-18 | 2013-03-11
186 | TSK135_W_N | COGREG | NA | NA | TSK135 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2012-12-28 |  |  | DONE | [8 empty] | 2013-02-18 | 2013-03-11 | 2013-02-18 | 2013-03-11
187 | TSK457_W_N | BARENGKOK-GNGOONG | NA | NA | TSK457 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE
188 | TSK130_W_N | KPSDANGJAYA | NA | NA | TSK130 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE |  |  |  |  | 2013-02-05
189 | TSK466_W_N | BJNGRENCONG | NA | NA | TSK466 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 |  |  |  | DONE |  |  |  |  | 2013-02-06
190 | TSK465_W_N | KPMADUR | NA | NA | TSK465 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 |  |  |  | DONE |  |  |  |  | 2013-02-05
191 | TSK459_W_N | ANGGALASAN | NA | NA | TSK459 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2012-12-18 |  |  | DONE
192 | TSK458_W_N | WANGUNWATI | NA | NA | TSK458 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE |  |  |  |  | 2013-02-21
193 | TSK147_W_N | PETIRNUNGAL | NA | NA | TSK147 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE | [8 empty] | 2013-02-18 | 2013-03-11 | 2013-02-18 | 2013-03-11
194 | GRT216_W_N | JAYAMUKTI-LEUWISARI (KPSUKAMAJU) | NA | NA | GRT216 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE | [8 empty] | 2013-02-18 | 2013-03-11 | 2013-02-18 | 2013-03-11
195 | TSK502_W_N | Salawu-Purwarahayu (ex.Kampungnaga-Keltjsari) | NA | NA | TSK502 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE |  |  |  |  | 2013-03-11 |  |  |  | 2013-02-18 | 2013-03-11 | 2013-02-18 | 2013-03-11
196 | IND159_W_N | KERTAMULYA-BUNGASINDMY | NA | NA | IND159 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE |  |  |  |  | 2013-03-24
197 | IND160_W_N | RAJAWALI-ANJATANINDMY | NA | NA | IND160 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-01-15 |  |  | DONE
198 | KNG115_W_N | Japara-Cipicung | NA | NA | KNG115 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE
199 | MJL124_W_N | KELAPADUA-CIKADUMJL | NA | NA | MJL124 | BOARD INS | BTS0701_Expansion: BTS/NodeB Base-Band Board |  | 1091115745-5 | 2013-02-08 |  |  | DONE
200 | COD032_W_N | CombatCipanas | NA | NA | CJRXXX | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091115745-6 | 2013-01-06 |  | 2013-01-06 | DONE | [8 empty] | 2013-03-08
201 | COD032 | CombatCipanas | BOO067 | CUGCIPANAS | COD032-BOO067 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  | 1091118158-2 | 2013-01-04
202 | BOO067 | CUGCIPANAS | CJR001 | GUNUNGGEDE | BOO067-CJR001 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  | 1091118158-2 | 2013-01-04 | [7 empty] | 2013-02-27
203 | CJR001 | GUNUNGGEDE | CJR011 | BSCCIANJUR | CJR001-CJR011 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  | 1091118158-2 | 2013-01-04
204 | COD032_W_N | CombatCipanas | NA | NA | COD032 | LAST MILE DELIVERY | DBS RRU On Tower + POWER SYS + ANT&FEEDER; CD4 |  |  | 2013-01-04
205 | SMD153_G_N | XL(CILENGKRANG) | NA | NA | SMD153 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2013-01-08 | 2013-01-10 | 2013-01-31 | DONE
206 | TSK537 | Isat-BANTARKALONG | NA | NA | TSK537 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna | [19 empty] | TSK537 Comm Case; materials relocated into another site
207 | GRT201 | Malangbong-Cipeundeuy | GRT012 | CIPEUNDEUY | GRT201-GRT012 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091115556-4 | 2013-01-16 | 2013-01-19 | 2013-01-20 | DONE
208 | TSK531 | ISAT(PASIRWARU)-Cibeber | TSK017 | KRNGNUNGGAL | TSK531-TSK017 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-06 | 2013-03-07 | 2013-03-08 | DONE | [13 empty] | hop cancelled
209 | GRT255 | XL(PASIRWANGI) | GRT148 | SARIMUKTI | GRT255-GRT148 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091115556-4 | 2013-01-12 | 2013-01-14 | 2013-01-15 | DONE
210 | SMD153_G_N | XL(CILENGKRANG) | NA | NA | SMD153 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | 2013-01-30 |  | 2013-01-30 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
211 | COD032_W_N | CombatCipanas | NA | NA | CJRXXX | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091115556-3 | 2013-01-04 | 2013-01-05 | 2013-01-06 | DONE
212 | SMD153 | XL(CILENGKRANG) | SMD010 | DARMARAJA | SMD153-SMD010 | MW NEW | MW PDH (0.9m/1.2m) 2: Installation and Commissioning |  | 1091098837-27 | 2013-01-07 | 2013-01-08 | 2013-01-09 | DONE |  |  |  |  | 2013-02-20 |  |  |  | 2013-04-05
213 | SUB398_W_N | RANCASARI-KRAJANPMNKAN | NA | NA | SUB398 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  |  | 2012-10-20 | 2012-10-22 | 2012-10-24 | DONE
214 | IND171_W_N | TBG-Wanakaya | NA | NA | IND171 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-01-07 | 2013-01-09 | 2013-01-18 | DONE | [6 empty] | 2013-02-13
215 | IND171_G_N | TBG-Wanakaya | NA | NA | IND171 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-25 | 2013-01-07 | 2013-01-09 | 2013-01-29 | DONE
216 | GRT201_W_N | Malangbong-Cipeundeuy | NA | NA | GRT201 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-01-15 | 2013-01-18 | 2013-01-18 | DONE
217 | CRB565_W_N | XLBakungLor | NA | NA | CRB565 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-01-16 | 2013-01-18 | 2013-01-22 | DONE | [6 empty] | 2013-02-13
218 | GRT221_G_N | Kertamukti-Cikelet | NA | NA | GRT221 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-01-17 | 2013-01-19 | 2013-01-19 | DONE
219 | GRT263_W_N | Protel-Wanakerta | NA | NA | GRT263 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-26 | 2013-02-28 | 2013-03-21 | DONE
220 | BJR030_W_N | Pataruman-Rancakole | NA | NA | BJR030 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-01-19 | 2013-01-23 | 2013-01-23 | DONE |  |  |  | 2013-03-21 |  |  | 2013-02-21 | 2013-03-22 | [5 empty] | GRT263 Comm Case; materials in GCI WH
221 | GRT283_W_N | Ciariliu-Simpanggrt | NA | NA | GRT283 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091115556-3 | 2013-01-19 | 2013-01-24 | 2013-01-29 | DONE | [13 empty] | BJR030 Comm Case; Materials in GCI WH
222 | CMS262_W_N | Jlnagrog-Pasirbatang | NA | NA | CMS262 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091115556-3 | 2013-03-23 | [16 empty] | CMS262 Comm Case; Materials in GCI WH; material already relocated from GCI WH to BDG201
223 | BDG952_W_N | TANIMULYA-SASAKBEUSI | NA | NA | BDG952 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-01-23 | 2013-01-25 | 2013-01-29 | DONE |  |  |  | 2013-03-25 |  |  | 2013-03-09
224 | CMI063_W_N | Cibaligo-Kebonkopi | NA | NA | CMI063 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-01-23 | 2013-01-25 | 2013-01-26 | DONE | [6 empty] | 2013-01-16 |  | 2013-04-08
225 | IND165_W_N | TBG-KARANGDEMPEL | NA | NA | IND165 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-01-25 | 2013-01-27 | 2013-01-29 | DONE | [6 empty] | 2013-03-19
226 | BDG975_W_N | Thepeak-Pasirwangi | NA | NA | BDG975 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-01-26 | 2013-01-28 | 2013-01-28 | DONE | [6 empty] | 2013-03-22 |  | 2013-04-08
227 | BDG290_W_N | Ktrbersama-Margacinta | NA | NA | BDG290 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-01-27 | 2013-01-29 | 2013-01-28 | DONE |  |  |  | 2013-03-25 |  |  | 2013-02-13
228 | GRT263 | Protel-Wanakerta | GRT008 | CIBATU | GRT263-GRT008 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-3 | 2013-03-18 | 2013-03-20 | 2013-03-20 | DONE | [13 empty] | GRT263 Comm Case; materials delivered to GCI WH
229 | GRT283 | Ciariliu-Simpanggrt | GRT063 | CIARILIU | GRT283-GRT063 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-01-18 | 2013-01-20 | 2013-01-21 | DONE
230 | BJR030 | Pataruman-Rancakole | BJR024 | RANCAKOLE | BJR030-BJR024 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-01-19 | 2013-01-20 | 2013-01-30 | DONE |  |  |  |  | 2013-02-05 |  | 2013-02-21 | 2013-03-21
231 | CMS021 | CIKEMBULAN | CMS099 | JLKAWASEN | CMS021-CMS099 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  | 1091117396-6 | 2013-01-18 | 2013-01-21 | 2013-01-21 | DONE |  |  |  |  | 2013-02-06 |  | 2013-02-22
232 | GRT031 | SAMARANG | GRT082 | DSMEKARJAYA | GRT031-GRT082 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-3 | 2013-01-25 | 2013-01-27 | 2013-01-28 | DONE |  |  |  |  | 2013-02-05
233 | GRT082 | DSMEKARJAYA | GRT001 | STOGARUT | GRT082-GRT001 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-3 | 2013-01-28 | 2013-01-29 | 2013-01-30 | DONE
234 | GRT253 | PROTEL-samarang | GRT031 | SAMARANG | GRT253-GRT031 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-3 | 2013-01-28 | 2013-01-29 | 2013-01-30 | DONE |  |  |  | 2013-03-13 | 2013-02-21 |  | 2013-03-11
235 | CMS262 | Jlnagrog-Pasirbatang | CMS011 | STDNGALUHCMS | CMS262-CMS011 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-23 | [16 empty] | CMS262 Comm Case; materials delivered to GCI WH; materials already relocated from GCI WH to BDG924
236 | BDG172 | CIMAREME | BDG426 | BONGKOKKULON | BDG172-BDG426 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  | 1091117396-6 | 2013-01-28 | [16 empty] | Hop Cancelled
237 | GRT221 | Kertamukti-Cikelet | GRT207 | BUNGBULANG | GRT221-GRT207 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-01-13 | 2013-01-16 | 2013-01-17 | DONE |  |  |  | 2013-03-21 | 2013-03-11
238 | SUB398_W_N | RANCASARI-KRAJANPMNKAN | NA | NA | SUB398 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-3 | 2013-10-30 |  | 2013-10-30 | DONE
239 | IND171 ex TSK473_W_N_583-585 | TBG-Wanakaya | NA | NA | IND171 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-11 | 2013-01-18 |  | 2013-01-18 | DONE
240 | IND171_G_N | TBG-Wanakaya | NA | NA | IND171 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-11 | 2013-01-18 |  | 2013-01-18 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
241 | GRT201_W_N | Malangbong-Cipeundeuy | NA | NA | GRT201 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-01-18 |  | 2013-01-18 | DONE
242 | CRB565_W_N | XLBakungLor | NA | NA | CRB565 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-01-22 |  | 2013-01-22 | DONE
243 | GRT221_G_N | Kertamukti-Cikelet | NA | NA | GRT221 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-01-19 |  | 2013-01-19 | DONE
244 | GRT283_W_N | Ciariliu-Simpanggrt | NA | NA | GRT283 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091115745-3 | 2013-01-29 |  | 2013-01-29 | DONE | [8 empty] | 2013-03-08
245 | BDG952_W_N | TANIMULYA-SASAKBEUSI | NA | NA | BDG952 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2013-02-20 |  | 2013-02-20 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
246 | CMI063_W_N | Cibaligo-Kebonkopi | NA | NA | CMI063 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2013-01-26 |  | 2013-01-26 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
247 | IND165_W_N | TBG-KARANGDEMPEL | NA | NA | IND165 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2013-01-29 |  | 2013-01-29 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
248 | BDG975_W_N | Thepeak-Pasirwangi | NA | NA | BDG975 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2013-01-28 |  | 2013-01-28 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
249 | BDG290_W_N | Ktrbersama-Margacinta | NA | NA | BDG290 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2013-01-28 |  | 2013-01-28 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
250 | BDG975 | Thepeak-Pasirwangi | BDG074 | THEPEAK | BDG975-BDG074 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-01-27 | 2013-01-28 | 2013-01-27 | DONE |  |  |  |  | 2013-03-24 |  | 2013-03-20
251 | BDG290 | Ktrbersama-Margacinta | BDG067 | KTRBERSAMA | BDG290-BDG067 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-4 | 2013-02-13 | 2013-01-26 | 2013-01-27 | DONE | [6 empty] | 2013-02-21
252 | SMD153_G_N | XL(CILENGKRANG) | NA | NA | SMD153 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-13
253 | IND171_W_N | TBG-Wanakaya | NA | NA | IND171 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-13
254 | GRT201_W_N | Malangbong-Cipeundeuy | NA | NA | GRT201 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-15
255 | CRB565_W_N | XLBakungLor | NA | NA | CRB565 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-16
256 | GRT221_G_N | Kertamukti-Cikelet | NA | NA | GRT221 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-17
257 | GRT263_W_N | Protel-Wanakerta | NA | NA | GRT263 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-20 | 2013-03-20 | 2013-03-20 | DONE | [13 empty] | 1st Time Delivery; Comm Case; Return Back to WH
258 | BJR030_W_N | Pataruman-Rancakole | NA | NA | BJR030 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-19
259 | GRT283_W_N | Ciariliu-Simpanggrt | NA | NA | GRT283 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-19
260 | CMS262_W_N | Jlnagrog-Pasirbatang | NA | NA | CMS262 | LAST MILE DELIVERY | Combined BTS/NodeB with antenna&feeder & MW 0.3/0.6m 2; CD6 |  |  | 2013-03-23
261 | BDG952_W_N | TANIMULYA-SASAKBEUSI | NA | NA | BDG952 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-23
262 | CMI063_W_N | Cibaligo-Kebonkopi | NA | NA | CMI063 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-23
263 | IND165_W_N | TBG-KARANGDEMPEL | NA | NA | IND165 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-25
264 | BDG975_W_N | Thepeak-Pasirwangi | NA | NA | BDG975 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-26
265 | BDG290_W_N | Ktrbersama-Margacinta | NA | NA | BDG290 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-27
266 | GRT201 | Malangbong-Cipeundeuy | GRT012 | CIPEUNDEUY | GRT201-GRT012 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  | 1091118159-3 | 2013-01-16
267 | TSK531 | ISAT(PASIRWARU)-Cibeber | TSK017 | KRNGNUNGGAL | TSK531-TSK017 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  | 1091118159-3 | 2013-03-07
268 | GRT255_G_N | XL(PASIRWANGI) | GRT148 | SARIMUKTI | GRT255-GRT148 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  | 1091118159-3 | 2013-01-12
269 | SMD153 | XL(CILENGKRANG) | SMD010 | DARMARAJA | SMD153-SMD010 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-01-07
270 | GRT263 | Protel-Wanakerta | GRT008 | CIBATU | GRT263-GRT008 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-20 | [16 empty] | 1st Time Delivery; Comm Case; Return Back to WH
271 | GRT283 | Ciariliu-Simpanggrt | GRT063 | CIARILIU | GRT283-GRT063 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-01-18
272 | BJR030 | Pataruman-Rancakole | BJR024 | RANCAKOLE | BJR030-BJR024 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-01-19
273 | CMS021 | CIKEMBULAN | CMS099 | JLKAWASEN | CMS021-CMS099 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-01-18
274 | GRT031 | SAMARANG | GRT082 | DSMEKARJAYA | GRT031-GRT082 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  | 1091118159-2 | 2013-01-25
275 | GRT082 | DSMEKARJAYA | GRT001 | STOGARUT | GRT082-GRT001 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  | 1091118159-2 | 2013-01-28
276 | GRT253 | PROTEL-samarang | GRT031 | SAMARANG | GRT253-GRT031 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  | 1091118159-2 | 2013-01-28
277 | BDG172 | CIMAREME | BDG426 | BONGKOKKULON | BDG172-BDG426 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-01-07
278 | GRT221 | Kertamukti-Cikelet | GRT207 | BUNGBULANG | GRT221-GRT207 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-01-13
279 | BDG975 | Thepeak-Pasirwangi | BDG074 | THEPEAK | BDG975-BDG074 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-01-27
280 | BDG290 | Ktrbersama-Margacinta | BDG067 | KTRBERSAMA | BDG290-BDG067 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-13
281 | GRT255_G_N | XL(PASIRWANGI) | NA | NA | GRT255 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-01-28 | 2013-05-31 | 2013-05-31 | DONE
282 | TSK531_G_N | ISAT(PASIRWARU)-Cibeber | NA | NA | TSK531 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-01-30 | 2013-03-07 | 2013-03-08 | DONE
283 | GRT253_G_N | PROTEL-samarang | NA | NA | GRT253 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-01-30 | 2013-01-31 | 2013-01-31 | DONE | [6 empty] | 2013-02-21 | 2013-03-22
284 | BDG201_W_N | PROTEL-Longonsari | NA | NA | BDG201 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-08 | 2013-02-08 | 2013-02-10 | DONE
285 | CMS243 | PROTEL-CIAMIS (lengkongsari Dskliwon) | CMS016 | CIHIDEUNGTSK | CMS243-CMS016 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-07 | 2013-02-14 | 2013-02-17 | [14 empty] | rerouted into CMS243-CMS053
286 | GRT284 | Dsmekarjaya-Sampireun | GRT082 | DSMEKARJAYA | GRT284-GRT082 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-08 | 2013-02-09 | 2013-02-10 | DONE
287 | BDG201 | PROTEL-Longonsari | BDG747 | MALAKASARI | BDG201-BDG747 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-08 | 2013-02-08 | 2013-02-08 | DONE
288 | BDG494 | Protel-Cibolerang | BDG117 | CIGONDEWAHMW | BDG494-BDG117 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-08 | 2013-02-09 | 2013-02-09 | DONE | [6 empty] | 2013-03-18
289 | BDG924 | Protel-Cihaliwung | BDG109 | TOLPDLARANG | BDG924-BDG109 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-08 | 2013-02-09 | 2013-02-09 | DONE | [6 empty] | 2013-03-11 | 2013-03-21
290 | SUB417 | PROTEL-Pabuaran | SUB016 | SARENGSENG | SUB417-SUB016 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-09 | 2013-02-10 | 2013-02-11 | DONE |  |  |  | 2013-03-13 | 2013-02-27
291 | BDG117 | CIGONDEWAH | BDG026 | MARGAJAYA | BDG117-BDG026 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-3 | 2013-02-11 | 2013-02-12 | 2013-02-15 | DONE
292 | BDG809 | SINDGKERTA | BDG109 | TOLPDLARANG | BDG809-BDG109 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  | 1091117396-5 | 2013-02-12 | 2013-02-13 | 2013-02-15 | DONE
293 | TSK531_G_N | ISAT(PASIRWARU)-Cibeber | NA | NA | TSK531 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-30 | [16 empty] | 1st LMD : return back, comm case
294 | GRT253_G_N | PROTEL-samarang | NA | NA | GRT253 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-01-28
295 | BDG201_W_N | PROTEL-Longonsari | NA | NA | BDG201 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-08
296 | BDG201_G_N | PROTEL-Longonsari | NA | NA | BDG201 | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-02-14
297 | CMS243 | PROTEL-CIAMIS (lengkongsari Dskliwon) | CMS016 | CIHIDEUNGTSK | CMS243-CMS016 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-07
298 | GRT284 | Dsmekarjaya-Sampireun | GRT082 | DSMEKARJAYA | GRT284-GRT082 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-08
299 | BDG201 | PROTEL-Longonsari | BDG747 | MALAKASARI | BDG201-BDG747 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-08
300 | BDG494 | Protel-Cibolerang | BDG117 | CIGONDEWAHMW | BDG494-BDG117 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-08
301 | BDG924 | Protel-Cihaliwung | BDG109 | TOLPDLARANG | BDG924-BDG109 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-08
302 | CJR410 | Protel-Sindanglaya | BOO046 | STOCIPANAS | CJR410-BOO046 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-07
303 | SUB417 | PROTEL-Pabuaran | SUB016 | SARENGSENG | SUB417-SUB016 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-09
304 | BDG117 | CIGONDEWAH | BDG026 | MARGAJAYA | BDG117-BDG026 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  | 1091118159-2 | 2013-02-11
305 | BDG809 | SINDGKERTA | BDG109 | TOLPDLARANG | BDG809-BDG109 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-02-09
306 | IND174_W_N | TBG.BOJONGSARI | NA | NA | IND174 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  |  | 2012-12-08 | 2012-12-10 | 2012-12-12 | DONE |  |  |  | 2012-01-07 | 2013-01-17 |  | 2013-02-21 | 2013-03-22 | 2013-04-08
307 | IND174_W_N | TBG.BOJONGSARI | NA | NA | IND174 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  |  | 2012-12-12 |  | 2012-12-12 | DONE
308 | BDG201_G_N | PROTEL-Longonsari | NA | NA | BDG201 | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-02-14 | 2013-02-14 | 2013-02-15 | DONE
309 | BDK138_W_N | CISEREUH-CANGKUANGWTN | NA | NA | BDK138 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-15 | 2013-02-16 | 2013-02-16 | DONE
310 | BDG201_W_N | PROTEL-Longonsari | NA | NA | BDG201 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-02-13 |  | 2013-02-13 | DONE
311 | BDG201_G_N | PROTEL-Longonsari | NA | NA | BDG201 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-02-13 |  | 2013-02-13 | DONE
312 | BDG600_W_N | XL-Bumi Panyawangan | NA | NA | BDG600 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2013-02-13 |  | 2013-02-13 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
313 | BJR030 ex IND156_W_N_583-585 | Pataruman-Rancakole | NA | NA | BJR030 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-11 | 2013-02-14 |  | 2013-02-14 | DONE
314 | CMS262_W_N | Jlnagrog-Pasirbatang | NA | NA | CMS262 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091115745-6 | [12 empty] | 2013-03-28
315 | GRT255_G_N | XL(PASIRWANGI) | NA | NA | GRT255 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-02-15 |  | 2013-05-31 | DONE
316 | GRT255_G_N | XL(PASIRWANGI) | NA | NA | GRT255 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-15
317 | TSK531_G_N | ISAT(PASIRWARU)-Cibeber | NA | NA | TSK531 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-2 | 2013-02-15 |  | 2013-02-15 | DONE
318 | GRT253_G_N | PROTEL-samarang | NA | NA | GRT253 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-02-17 |  | 2013-02-17 | DONE
319 | BDK138_W_N | CISEREUH-CANGKUANGWTN | NA | NA | BDK138 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1 | 2013-02-16 |  | 2013-02-16 | DONE
320 | BDK138_W_N | CISEREUH-CANGKUANGWTN | NA | NA | BDK138 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2012-12-28
321 | BDK138 | CISEREUH-CANGKUANGWTN | BDG061 | MEKARWANGI | BDK138-BDG061 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-18
322 | BDK138 | CISEREUH-CANGKUANGWTN | BDG061 | MEKARWANGI | BDK138-BDG061 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-11 | 2013-02-12 | 2013-02-14 | DONE |  |  |  |  | 2013-03-20 |  | 2013-03-18
323 | CJR412_W_N | XL-Lembah Hijau | NA | NA | CJR412 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | 2012-12-28 |  | 2012-12-28 | DONE | [8 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
324 | BDG494_W_N | Protel-Cibolerang | NA | NA | BDG494 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-15 | 2013-02-16 | 2013-02-16 | DONE
325 | BDG494_Dummy | Protel-Cibolerang | NA | NA | BDG494 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1 | 2013-02-18 |  | 2013-02-18 | DONE
326 | BDG494_W_N | Protel-Cibolerang | NA | NA | BDG494 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-15
327 | BDG924_W_N | Protel-Cihaliwung | NA | NA | BDG924 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-14 | 2013-02-15 | 2013-02-16 | DONE
328 | BDG924_Dummy | Protel-Cihaliwung | NA | NA | BDG924 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1 | 2013-02-16 |  | 2013-02-16 | DONE
329 | BDG924_W_N_024-026 | Protel-Cihaliwung | NA | NA | BDG924 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-13 | 2013-02-16 |  | 2013-02-16 | DONE
330 | BDG924_W_N | Protel-Cihaliwung | NA | NA | BDG924 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6; 2 system |  |  | 2013-02-15
331 | GRT284_W_N | Dsmekarjaya-Sampireun | NA | NA | GRT284 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-15 | 2013-02-16 | 2013-02-17 | DONE
332 | GRT284_W_N | Dsmekarjaya-Sampireun | NA | NA | GRT284 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-02-16 |  | 2013-02-16 | DONE
333 | GRT284_W_N | Dsmekarjaya-Sampireun | NA | NA | GRT284 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-17
334 | CMS243_W_N | PROTEL-CIAMIS (lengkongsari Dskliwon) | NA | NA | CMS243 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-9 | 2013-02-16 |  | 2013-02-16 | DONE
335 | CMS243_W_N | PROTEL-CIAMIS (lengkongsari Dskliwon) | NA | NA | CMS243 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-15
336 | CMS243_W_N | PROTEL-CIAMIS (lengkongsari Dskliwon) | NA | NA | CMS243 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-15 | 2013-02-16 | 2013-02-17 | DONE
337 | BDG777_W_N | DSLOA | NA | NA | BDG777 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-15 | 2013-02-18 | 2013-02-18 | DONE
338 | BDG777_Dummy | DSLOA | NA | NA | BDG777 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1 | 2013-02-15 |  | 2013-02-15 | DONE
339 | BDG777_W_N | DSLOA | NA | NA | BDG777 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-15
340 | BDG777 | DSLOA | BDG942 | DARAWATI | BDG777-BDG942 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-17
341 | BDG777 | DSLOA | BDG942 | DARAWATI | BDG777-BDG942 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-16 | 2013-02-16
342 | BDG789_Dummy | RNCSENGGANG | NA | NA | BDG789 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1 | 2013-02-26 |  | 2013-02-26 | DONE
343 | BDG789_W_N | RNCSENGGANG | NA | NA | BDG789 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-15
344 | BDG789_W_N | RNCSENGGANG | NA | NA | BDG789 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-15 | 2013-02-18 | 2013-02-19 | DONE
345 | BDG789 | RNCSENGGANG | BDG809 | SINDGKERTA | BDG789-BDG809 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-15 | 2013-02-23 | 2013-02-23 | DONE
346 | BDG789 | RNCSENGGANG | BDG809 | SINDGKERTA | BDG789-BDG809 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-17
347 | BDG694_W_N | RNCKASUMBA | NA | NA | BDG694 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-15 | 2013-02-18 | 2013-02-19 | DONE
348 | BDG694_W_N | RNCKASUMBA | NA | NA | BDG694 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-15
349 | BDG694_Dummy | RNCKASUMBA | NA | NA | BDG694 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1
350 | BDG553_W_N | SKMULYAPASEH | NA | NA | BDG553 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-15 | 2013-02-18 | 2013-02-19 | DONE
351 | BDG553_W_N | SKMULYAPASEH | NA | NA | BDG553 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-15
352 | BDG553_W_N | SKMULYAPASEH | NA | NA | BDG553 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-02-19 |  | 2013-02-19 | DONE
353 | CMS243 | PROTEL-CIAMIS (lengkongsari Dskliwon) | CMS016 | CIHIDEUNGTSK | CMS243-CMS016 | MW DISMANTLE | MW0601_Dismantlement&Packing: MW 0.3/0.6m 2 |  |  | 2013-03-20 | 2013-02-19
354 | CJR066 | CIBULAKAN | CJR008 | CUGENANG | CJR066-CJR008 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-27 | 2013-02-24 | 2013-02-26 | DONE
355 | CJR066 | CIBULAKAN | CJR008 | CUGENANG | CJR066-CJR008 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-25
356 | BDG302 | GUNUNGHALU | BDG109 | TOLPDLARANG | BDG302-BDG109 | MW NEW | MW0205_New: MW 1.8m 2 |  |  | 2013-02-12 | 2013-02-13 | 2013-02-16 | DONE
357 | BDG302 | GUNUNGHALU | BDG109 | TOLPDLARANG | BDG302-BDG109 | LAST MILE DELIVERY | MW 1.8m 2; CD6 |  |  | 2013-02-12
358 | SUB397 | Sarengseng-Paponcol | SUB016 | SARENGSENG | SUB397-SUB016 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-4 | 2013-02-13 | 2013-02-14 | 2013-02-14 | DONE |  |  |  | 2013-03-13 | 2013-02-21
359 | SUB397 | Sarengseng-Paponcol | SUB016 | SARENGSENG | SUB397-SUB016 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-13
360 | CMS238 | AXIS(JELAT) | TSK042 | NANGGEWER | CMS238-TSK042 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-14 | 2013-02-15 | 2013-02-15 | DONE
361 | CMS238 | AXIS(JELAT) | TSK042 | NANGGEWER | CMS238-TSK042 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-14
362 | CMS242 | AXIS(Golat) | TSK097 | MANGGUNG | CMS242-TSK097 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-14 | 2013-02-15 | 2013-03-06 | DONE
363 | CMS242 | AXIS(Golat) | TSK097 | MANGGUNG | CMS242-TSK097 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-14
364 | GRT264 | Axis-Limbangan | GRT182 | BUNISARI | GRT264-GRT182 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-14 | 2013-02-15 | 2013-03-08 | DONE
365 | GRT264 | Axis-Limbangan | GRT182 | BUNISARI | GRT264-GRT182 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-14
366 | BDG713 | SAGULING | BDG305 | CIPONGKOR | BDG713-BDG305 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-16 | 2013-02-17 | 2013-02-19 | DONE |  |  |  |  | 2013-03-20 |  | 2013-03-18
367 | BDG713 | SAGULING | BDG305 | CIPONGKOR | BDG713-BDG305 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-16
368 | BDG601 | DSCELAKM | BDG302 | GUNUNGHALU | BDG601-BDG302 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-16 | 2013-02-19 | 2013-02-20 | DONE |  |  |  | 2013-03-13 | 2013-02-26
369 | BDG601 | DSCELAKM | BDG302 | GUNUNGHALU | BDG601-BDG302 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-16
370 | KNG131_W_N | TBG-Kelapagunung | NA | NA | KNG131 | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-03-15 | 2013-03-17 | 2013-03-18 | DONE
371 | KNG131_W_N | TBG-Kelapagunung | NA | NA | KNG131 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6; 2 system |  |  | 2013-03-15 | [16 empty] | 1st LMD : comm case; return back to WH
372 | KNG131_W_N | TBG-Kelapagunung | NA | NA | KNG131 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-12 | 2013-03-18 | [16 empty] | 1st LMD : comm case; return back to WH
373 | CMS214 | CIKEMBULAN-KEDONGREJO | CMS021 | CIKEMBULAN | CMS214-CMS021 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-4 | 2013-02-17 | 2013-02-18
374 | CMS214 | CIKEMBULAN-KEDONGREJO | CMS021 | CIKEMBULAN | CMS214-CMS021 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-17
375 | CMS222 | KERTAMUKTI-CIKONDANG | CMS053 | KRNGTAWULAN | CMS222-CMS053 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-17 | 2013-02-18
376 | CMS222 | KERTAMUKTI-CIKONDANG | CMS053 | KRNGTAWULAN | CMS222-CMS053 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-17
377 | GRT246 | Protel-Krgpawitan | GRT011 | KRGPAWITAN | GRT246-GRT011 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-26 | 2013-02-27 | 2013-02-28 | DONE
378 | GRT246 | Protel-Krgpawitan | GRT011 | KRGPAWITAN | GRT246-GRT011 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-26
379 | BDG102 | STO Rancaekek | NA | NA | BDG102 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-48 | 2013-02-21
380 | TSK129_W_N_Dummy | DSKARYABAKTI | NA | NA | BDG223 | LAST MILE DELIVERY | Antenna Delivery (Destination: Tasikmalaya) |  | 1091113378-1 | 2012-09-22 | [11 empty] | 2013-02-15 | 2013-03-11 | 2013-02-15 | 2013-03-11
381 | TSK135_W_N_Dummy | COGREG | NA | NA | BDG419 | LAST MILE DELIVERY | Antenna Delivery (Destination: Tasikmalaya) |  | 1091113378-1 | 2012-09-29 | [11 empty] | 2013-02-15 | 2013-03-11 | 2013-02-15 | 2013-03-11
382 | CJR430_G_N | JATISARICJRM | NA | NA | CJR430 | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-02-21 | 2013-03-09 | 2013-03-22 | DONE
383 | TSK457_G_N | BARENGKOK-GNGOONG | NA | NA | TSK457 | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-02-26 | 2013-02-27 | 2013-02-28 | DONE
384 | GRT212_G_N | SUKAMANAHGRTM | NA | NA | GRT212 | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-02-24 | 2013-02-25 | 2013-02-26 | DONE
385 | CMS242_G_N | AXIS(Golat) | NA | NA | CMS242 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-22 | 2013-03-04 | 2013-03-05 | DONE
386 | GRT246_W_N | Protel-Krgpawitan | NA | NA | GRT246 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-27 | 2013-02-28 | 2013-02-27 | DONE
387 | GRT211_G_N | CIBURIALM | NA | NA | GRT211 | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-02-25 | 2013-02-26 | 2013-02-26 | DONE
388 | TSK499_G_N | CIGARUNGSANGM | NA | NA | TSK499 | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-02-26 | 2013-02-27 | 2013-02-27 | DONE
389 | BDG367_W_N | Protel-Pasirendah | NA | NA | BDG367 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-25 | 2013-02-26 | 2013-02-26 | DONE
390 | BDG179_W_N | Tmnsuryaidh-BCAKopo | NA | NA | BDG179 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-26 | 2013-02-27 | 2013-02-27 | DONE
391 | BDG625_W_N | BDGN-18-WBBMC-Site_7782-Protel | NA | NA | BDG625 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-02-25 | 2013-02-26 | 2013-02-26 | DONE
392 | KNG128_G_N | XL-Cipicung Kuningan | NA | NA | KNG128 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29 | 2013-03-21
393 | CJR430_G_N | JATISARICJRM | NA | NA | BDG052 | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-02-21
394 | TSK457_G_N | BARENGKOK-GNGOONG | NA | NA | BDG372 | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  | 1091118159-4 | 2013-02-26
395 | GRT212_G_N | SUKAMANAHGRTM | NA | NA | BDG320 | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-02-24
396 | CMS242_G_N | AXIS(Golat) | NA | NA | BDG349 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-22
397 | GRT246_W_N | Protel-Krgpawitan | NA | NA | BDG130 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-27
398 | GRT211_G_N | CIBURIALM | NA | NA | BDG237 | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  | 1091118159-4 | 2013-02-25
399 | TSK499_G_N | CIGARUNGSANGM | NA | NA | BDG182 | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-02-26
400 | BDG367_W_N | Protel-Pasirendah | NA | NA | BDG411 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-25
401 | BDG179_W_N | Tmnsuryaidh-BCAKopo | NA | NA | BDG110 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  | 1091118158-3 | 2013-02-26
402 | BDG625_W_N | BDGN-18-WBBMC-Site_7782-Protel | NA | NA | BDG231 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-25
403 | KNG128_G_N | XL-Cipicung Kuningan | NA | NA | BDG735 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-21
404 | CJR430_W_N_024-026 | JATISARICJRM | NA | NA | BDG420 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-13 | 2013-03-20 |  | 2013-03-20 | DONE
405 | TSK457_G_N | BARENGKOK-GNGOONG | NA | NA | BDG518 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-10 | 2013-02-27 |  | 2013-02-27 | DONE
406 | GRT212_G_N | SUKAMANAHGRTM | NA | NA | BDG250 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-02-25 |  | 2013-02-25 | DONE
407 | CMS242_G_N | AXIS(Golat) | NA | NA | CRB127 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-03-05 |  | 2013-03-05 | DONE
408 | GRT246_W_N_820-822 | Protel-Krgpawitan | NA | NA | CRB057 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-12 | 2013-02-27 |  | 2013-02-27 | DONE
409 | GRT211 ex MJL124_G_N_738-740 | CIBURIALM | NA | NA | CRB084 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-10 | 2013-02-26 |  | 2013-02-26 | DONE
410 | TSK499_G_N | CIGARUNGSANGM | NA | NA | CRB053 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-02-27 |  | 2013-02-27 | DONE
411 | BDG367_Dummy | Protel-Pasirendah | NA | NA | CRB489 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1 | 2013-02-26 |  | 2013-02-26 | DONE
412 | BDG179_W_N_583-585 | Tmnsuryaidh-BCAKopo | NA | NA | CRB010 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-11 | 2013-02-27 |  | 2013-02-27 | DONE
413 | BDG625_Dummy | BDGN-18-WBBMC-Site_7782-Protel | NA | NA | CRB049 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1 | 2013-02-27 |  | 2013-02-27 | DONE
414 | KNG128_G_N | XL-Cipicung Kuningan | NA | NA | CRB071 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13 | [12 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
415 | BDG179 | Tmnsuryaidh-BCAKopo | BDG814 | PSRCARINGIN | BDG179-BDG814 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-23 | 2013-02-24 | 2013-02-25 | DONE
416 | BDG625 | BDGN-18-WBBMC-Site_7782-Protel | BDG370 | CIRANGRANG | BDG625-BDG370 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-23 | 2013-02-24 | 2013-02-25 | DONE |  |  |  |  | 2013-03-20 |  | 2013-03-18
417 | BDG367 | Protel-Pasirendah | BDG073 | ARCAMANIKM | BDG367-BDG370 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-23 | 2013-02-24 | 2013-02-26 | DONE |  |  |  |  | 2013-03-20 |  | 2013-03-18
418 | CJR406 | Cibulakan-HARIMARTCNJR | CJR066 | CIBULAKAN | CJR406-CJR066 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-23 | 2013-02-24 | 2013-02-26 | DONE
419 | GRT249 | ISAT-MEKARMULYA | GRT030 | TALEGONG | GRT249-GRT030 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-25 | 2013-02-27 | 2013-02-28 | DONE |  |  |  | 2013-03-22 | 2013-03-13 |  | 2013-03-18
420 | GRT258 | Protel-Warungcagak | TSK039 | SIRNAGALIH | GRT258-TSK039 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-26 | 2013-02-27 | 2013-02-28 | DONE
421 | BDG179 | Tmnsuryaidh-BCAKopo | BDG814 | PSRCARINGIN | BDG179-BDG814 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-23
422 | BDG625 | BDGN-18-WBBMC-Site_7782-Protel | BDG370 | CIRANGRANG | BDG625-BDG370 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-23
423 | BDG367 | Protel-Pasirendah | BDG073 | ARCAMANIKM | BDG367-BDG370 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-23
424 | CJR406 | Cibulakan-HARIMARTCNJR | CJR066 | CIBULAKAN | CJR406-CJR066 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-23
425 | GRT249 | ISAT-MEKARMULYA | GRT030 | TALEGONG | GRT249-GRT030 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-25
426 | GRT258 | Protel-Warungcagak | TSK039 | SIRNAGALIH | GRT258-TSK039 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-26
427 | BDG223 | BANJARANMW | NA | NA | BDG223 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-07
428 | BDG419 | BOJONGKUNCIMW | NA | NA | BDG419 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-07
429 | BDG853 | CAMPAKAPDLMW | NA | NA | BDG853 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-26
430 | CMI008 | CIBEBERMW | NA | NA | CMI008 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-07
431 | BDG117 | CIGONDEWAHMW | NA | NA | BDG117 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-05
432 | BDG679 | CIGONDEWHKLRMW | NA | NA | BDG679 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-07
433 | BDG325 | DARAULINMW | NA | NA | BDG325 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-06
434 | BDG941 | DSRAHAYUMW | NA | NA | BDG941 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-08
435 | BDG080 | GRIYABDGINDHMW | NA | NA | BDG080 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-07
436 | BDG335 | JLSINDANGSRMW | NA | NA | BDG335 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-51 | 2013-02-11
437 | BDG111 | MARIBAYAMW | NA | NA | BDG111 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-08
438 | BDG221 | MENGGERMW | NA | NA | BDG221 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-06
439 | BDG824 | PASARLBGMW | NA | NA | BDG824 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-08
440 | BDG052 | RANCABOLANGMW | NA | NA | BDG052 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-08
441 | BDG372 | SADIPLAKMW | NA | NA | BDG372 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-06
442 | BDG320 | SANGKANHURIPMW | NA | NA | BDG320 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-05
443 | BDG349 | SUNTENJAYAMW | NA | NA | BDG349 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-11
444 | BDG130 | TOLBUAHBATUMW | NA | NA | BDG130 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-07
445 | BDG237 | UNJANIMW | NA | NA | BDG237 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-27
446 | BDG182 | WARUNGLOBAKMW | NA | NA | BDG182 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-52 | 2013-02-06
447 | BDG411 | CIGENTURMW | NA | NA | BDG411 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-18
448 | BDG110 | CILOAMW | NA | NA | BDG110 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-18
449 | BDG231 | CITATAHMW | NA | NA | BDG231 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-19
450 | BDG735 | KRGTANJUNGMW | NA | NA | BDG735 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-13
451 | BDG420 | MARGALUYUMW | NA | NA | BDG420 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-02-11
452 | BDG518 | SITUWANGIMW | NA | NA | BDG518 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-12
453 | BDG250 | STCILAMEMW | NA | NA | BDG250 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-19
454 | CRB127 | BLKKBNTAJUGMW | NA | NA | CRB127 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-05
455 | CRB057 | GEMPOLMW | NA | NA | CRB057 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-07
456 | CRB084 | JAMARASKIDULMW | NA | NA | CRB084 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-07
457 | CRB053 | PANGURAGANMW | NA | NA | CRB053 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-53 | 2013-02-06
458 | CRB489 | GETRAKMOYANMW | NA | NA | CRB489 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-55 | 2013-02-12
459 | CRB010 | KALIPASUNGMW | NA | NA | CRB010 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-55 | 2013-02-08
460 | CRB049 | PAKUSAMBENMW | NA | NA | CRB049 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-55 | 2013-02-08
461 | CRB071 | KALIMUKTIMW | NA | NA | CRB071 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-55 | 2013-02-13
462 | CRB451 | PABEDILANMW | NA | NA | CRB451 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-55 | 2013-02-13
463 | BDG374 | RAYAARGASARIMW | NA | NA | BDG374 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-55 | 2013-02-08
464 | GRT263_W_N | Protel-Wanakerta | NA | NA | GRT263 | LAST MILE DELIVERY | Combined BTS/NodeB with antenna&feeder & MW 0.3/0.6m 2; CD6 |  |  | 2013-03-20 | [16 empty] | 2nd Time Delivery; Success
465 | KNG131_W_N | TBG-Kelapagunung | NA | NA | KNG131 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6; 2 system |  |  | 2013-03-15 | [16 empty] | 2nd LMD : success
466 | GRT212_G_N | SUKAMANAHGRTM | NA | NA | GRT212 | OPTIONAL | Antenna Dismantlement&Packing |  |  | 2013-02-25 |  |  | DONE
467 | GRT211_G_N | CIBURIALM | NA | NA | GRT211 | OPTIONAL | Antenna Replacement&Packing |  | 1091117097-8 | 2013-02-26 |  |  | DONE
468 | TSK499_G_N | CILAWU-BOJONGLOA | NA | NA | TSK499 | OPTIONAL | Antenna Replacement&Packing |  | 1091117097-21 | 2013-02-27 |  |  | DONE
469 | GRT212_G_N | SUKAMANAHGRTM | NA | NA | GRT212 | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to Site; 1 SITE 1 TRIP |  |  | 2013-02-25
470 | GRT211_G_N | CIBURIALM | NA | NA | GRT211 | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to Site; 1 SITE 1 TRIP |  |  | 2013-02-25
471 | TSK499_G_N | CIGARUNGSANGM | NA | NA | TSK499 | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to Site; 1 SITE 1 TRIP |  |  | 2013-02-27
472 | GRT212_G_N | SUKAMANAHGRTM | NA | NA | GRT212 | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to WH; 1 SITE 1 TRIP |  |  | 2013-02-24
473 | GRT211_G_N | CIBURIALM | NA | NA | GRT211 | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to WH; 1 SITE 1 TRIP |  |  | 2013-02-25
474 | TSK499_G_N | CIGARUNGSANGM | NA | NA | TSK499 | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to WH; 1 SITE 1 TRIP |  |  | 2013-02-26
475 | KNG132 | SINDANGSARI | NA | NA | KNG132 | SURVEY | Engineering Site Survey & Design (BTS/NodeB or BTS/NodeB+MW) |  | 1091098759-4 | 2012-11-09 | [11 empty] | 2013-01-28 |  | 2013-01-31
476 | KNG128 | XL-Cipicung Kuningan | KNG006 | CIPORANG | KNG128-KNG006 | MW NEW | MW PDH (0.3m/0.6m) 2: Installation and Commissioning |  | 1091098837-28 | 2013-03-20
477 | TSK531_G_N | ISAT(PASIRWARU)-Cibeber | NA | NA | TSK531 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-02-15 | [16 empty] | 2nd LMD : success
478 | SMD021 | PADANAANPSHM | NA | NA | SMD021 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-03-02
479 | KNG038 | SIDAMULYAM | NA | NA | KNG038 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-03-05
480 | KNG048 | KAMPUNGLURAHM | NA | NA | KNG048 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-03-05
481 | KNG069 | KUWUKERTAM | NA | NA | KNG069 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-03-05
482 | IND017 | JTBARANGKOTAM | NA | NA | IND017 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-03-06
483 | IND020 | LELEAM | NA | NA | IND020 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-03-06
484 | GRT003 | LIMBANGANM | NA | NA | GRT003 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-02-28
485 | SMD056 | CILANGKAPM | NA | NA | SMD056 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-03-01
486 | SMD003 | TOMOM | NA | NA | SMD003 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-42 | 2013-03-01
487 | SMD088 | CIKONDANGSMDM | NA | NA | SMD088 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-03-01
488 | CMS074 | SINDANGMANGUM | NA | NA | CMS074 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-03-01
489 | CMS087 | DSKRNGMULYAM | NA | NA | CMS087 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-03-01
490 | TSK097 | MANGGUNGM | NA | NA | TSK097 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-03-06
491 | IND054 | WARUINDM | NA | NA | IND054 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-03-07
492 | GRT182 | BUNISARIM | NA | NA | GRT182 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-02-07
493 | KNG010 | SINDANGAGUNGM | NA | NA | KNG010 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-03-08
494 | IND052 | PABEANUDIKM | NA | NA | IND052 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-03-08
495 | IND133 | KPLANGUTM | NA | NA | IND133 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-03-08
496 | TSK023 | CIAWIM | NA | NA | TSK023 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-43 | 2013-03-08
497 | GRT074 | SUKARESIKM | NA | NA | GRT074 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-47 | 2013-03-08
498 | BDG983 | CANGKUANGWTNM | NA | NA | BDG983 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-55 | 2013-03-11
499 | TSK181 | SIMPANGTSKM | NA | NA | TSK181 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-47 | 2013-03-13
500 | TSK179 | TEGALLEGATSKM | NA | NA | TSK179 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-47 | 2013-03-14
501 | CRB050 | GEGESIKM | NA | NA | CRB050 | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-55 | 2013-03-14
502 | BDG910 | AMOSEAS | GRT148 | SARIMUKTI | BDG910-GRT148 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-14 | 2013-03-16 | 2013-03-18 | DONE
503 | CRB043 | CHIHIKEU | GRT027 | BUNGBULANG | CRB043-GRT027 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-14 | 2013-03-16 | 2013-03-18 | DONE
504 | TSK119 | RANCASALAH | GRT045 | LEUWIGOONG | TSK119-GRT045 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-14 | 2013-03-16 | 2013-03-18 | DONE
505 | KNG018 | GARAWANGI | KNG006 | CIPORANGM | KNG018-KNG006 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-14 | 2013-03-16 | 2013-03-17 | DONE
506 | CRB124 | SEDONGCIRBON | CRB010 | KALIPASUNGMW | CRB124-CRB010 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  |  | 2013-03-14
507 | IND044 | JAGAPURA | CRB001 | KEDATON | IND044-CRB001 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-14 | 2013-03-15 | 2013-03-16 | DONE
508 | IND001 | SUKAGUMIWANG | IND012 | KERTASMAYA | IND001-IND012 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-14
509 | MJL020 | JATITUJUH | MJL016 | LIGUNGM | MJL020-MJL016 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-14 | 2013-03-15 | 2013-03-16 | DONE | [6 empty] | 2012-12-21
510 | IND096 | PRAPATAN | CRB439 | TERISI | IND096-CRB439 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-14
511 | IND075 | RAJAWALI | SUB009 | PUSAKANEGARA | IND075-SUB009 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-14 | 2013-03-16 | 2013-03-16 | DONE
512 | BDG910 | AMOSEAS | GRT148 | SARIMUKTI | BDG910-GRT148 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-14
513 | CRB043 | CHIHIKEU | GRT027 | BUNGBULANG | CRB043-GRT027 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-14
514 | TSK119 | RANCASALAH | GRT045 | LEUWIGOONG | TSK119-GRT045 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-14
515 | KNG018 | GARAWANGI | KNG006 | CIPORANGM | KNG018-KNG006 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-14
516 | CRB124 | SEDONGCIRBON | CRB010 | KALIPASUNGMW | CRB124-CRB010 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-03-14
517 | IND044 | JAGAPURA | CRB001 | KEDATON | IND044-CRB001 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-14
518 | IND001 | SUKAGUMIWANG | IND012 | KERTASMAYA | IND001-IND012 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-14
519 | MJL020 | JATITUJUH | MJL016 | LIGUNGM | MJL020-MJL016 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-14
520 | IND096 | PRAPATAN | CRB439 | TERISI | IND096-CRB439 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-14
521 | IND075 | RAJAWALI | SUB009 | PUSAKANEGARA | IND075-SUB009 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-14
522 | GRT258_W_N | Protel-Warungcagak | NA | NA | GRT258 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-16 | 2013-03-18 | 2013-03-21 | DONE
523 | GRT258_G_N | Protel-Warungcagak | NA | NA | GRT258 | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-03-16 | 2013-03-18 | 2013-03-20 | DONE
524 | IND075_W_N | RAJAWALI | NA | NA | IND075 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-19 | 2013-03-19 | 2013-03-22 | DONE | [13 empty] | + swap existing antenna & return back to TSEL WH
525 | IND023_W_N | BUNGASINDMY | NA | NA | IND023 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-19 | 2013-03-21 | 2013-03-22 | DONE | [13 empty] | + swap existing antenna & return back to TSEL WH
526 | IND021_W_N | BANGODUA | NA | NA | IND021 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-14 | 2013-03-15 | 2013-03-16 | DONE
527 | MJL020_W_N | JATITUJUH | NA | NA | MJL020 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-15 | 2013-03-17 | 2013-03-23 | DONE
528 | GRT089_W_N | CIGANGSA | NA | NA | GRT089 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-14 | 2013-03-15 | 2013-03-16 | DONE
529 | GRT026_W_N | CISEWU | NA | NA | GRT026 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-14 | 2013-03-16 | 2013-03-19 | DONE
530 | GRT027_W_N | BUNGBULANG | NA | NA | GRT027 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-14 | 2013-03-16 | 2013-03-22 | DONE
531 | GRT062_W_N | RNCAGONGGONG | NA | NA | GRT062 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-16 | 2013-03-17 | 2013-03-20 | DONE
532 | COD044_W_N | CMBTKNGKOTA | NA | NA | COD044 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-19 | 2013-03-20 | 2013-03-21 | DONE
533 | KNG018_W_N | GARAWANGI | NA | NA | KNG018 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-15 | 2013-03-16 | 2013-03-17 | DONE | [13 empty] | + swap existing antenna & return back to TSEL WH
534 | IND044_W_N | JAGAPURA | NA | NA | IND044 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-15 | 2013-03-17 | 2013-03-19 | DONE
535 | KNG021_W_N | LURAGUNGKOTA | NA | NA | KNG021 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-14 | 2013-03-15 | 2013-03-17 | DONE
536 | GRT258_G_N | Protel-Warungcagak | NA | NA | GRT258 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6; 2 system |  |  | 2013-03-16
537 | IND075_W_N | RAJAWALI | NA | NA | IND075 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-19
538 | IND023_W_N | BUNGASINDMY | NA | NA | IND023 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-19
539 | IND021_W_N | BANGODUA | NA | NA | IND021 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-14
540 | MJL020_W_N | JATITUJUH | NA | NA | MJL020 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-15
541 | GRT089_W_N | CIGANGSA | NA | NA | GRT089 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-14
542 | GRT026_W_N | CISEWU | NA | NA | GRT026 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-14
543 | GRT027_W_N | BUNGBULANG | NA | NA | GRT027 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-14
544 | GRT062_W_N | RNCAGONGGONG | NA | NA | GRT062 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-16
545 | COD044_W_N | CMBTKNGKOTA | NA | NA | COD044 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-19
546 | KNG018_W_N | GARAWANGI | NA | NA | KNG018 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-15
547 | IND044_W_N | JAGAPURA | NA | NA | IND044 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-15
548 | KNG021_W_N | LURAGUNGKOTA | NA | NA | KNG021 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-14
549 | GRT258_W_N | Protel-Warungcagak | NA | NA | GRT258 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-03-21 |  | 2013-03-21 | DONE
550 | GRT258_G_N | Protel-Warungcagak | NA | NA | GRT258 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-03-21 |  | 2013-03-21 | DONE
551 | IND075 ex BDG192_W_N_108-110 | RAJAWALI | NA | NA | IND075 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-15 | 2013-03-22 |  | 2013-03-22 | DONE
552 | IND023_W_N | BUNGASINDMY | NA | NA | IND023 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-15 | 2013-03-22 |  | 2013-03-22 | DONE
553 | IND021_W_N | BANGODUA | NA | NA | IND021 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-16 | 2013-03-16 |  | 2013-03-16 | DONE
554 | MJL020_W_N | JATITUJUH | NA | NA | MJL020 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-15 | 2013-03-23 |  | 2013-03-23 | DONE
555 | GRT089_W_N | CIGANGSA | NA | NA | GRT089 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-15 | 2013-03-16 |  | 2013-03-16 | DONE
556 | GRT026_W_N | CISEWU | NA | NA | GRT026 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-15 | 2013-03-19 |  | 2013-03-19 | DONE
557 | GRT027 ex BDG511_W_N_024-026 | BUNGBULANG | NA | NA | GRT027 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-14 | 2013-03-22 |  | 2013-03-22 | DONE
558 | GRT062 ex BDG544_W_N_024-026 | RNCAGONGGONG | NA | NA | GRT062 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-14 | 2013-03-20 |  | 2013-03-20 | DONE
559 | COD044 ex BDG072_W_N_108-110 | CMBTKNGKOTA | NA | NA | COD044 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-15 | 2013-03-21 |  | 2013-03-21 | DONE
560 | KNG018_W_N | GARAWANGI | NA | NA | KNG018 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-16 | 2013-03-17 |  | 2013-03-17 | DONE
561 | IND044 ex BDG184_W_N_108-110 | JAGAPURA | NA | NA | IND044 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-15 | 2013-03-19 |  | 2013-03-19 | DONE
562 | KNG021_W_N | LURAGUNGKOTA | NA | NA | KNG021 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-16 | 2013-03-17 |  | 2013-03-17 | DONE
563 | CRB124_W_N | SEDONGCIRBON | NA | NA | CRB124 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-19 | 2013-03-20 | [15 empty] | + swap existing antenna & return back to TSEL WH
564 | TSK119_W_N | RANCASALAH | NA | NA | TSK119 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-16
565 | GRT051_W_N | SAMPIREUN | NA | NA | GRT051 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-18 | 2013-03-19 | 2013-03-21 | DONE | [13 empty] | + swap existing antenna & return back to TSEL WH
566 | BDG102_W_N | STORANCAEKEK | NA | NA | BDG102 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-20 | 2013-03-21
567 | BDG981_W_N | PUNGKUR-SAWAHKURUNG | NA | NA | BDG981 | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-26 | 2013-03-17 | 2013-03-18
568 | CRB124 ex CRB461_W_N_108-110 | SEDONGCIRBON | NA | NA | CRB124 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-15
569 | TSK119 ex TSK399_W_N_024-026 | RANCASALAH | NA | NA | TSK119 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-14
570 | GRT051 ex BDG549_W_N_108-110 | SAMPIREUN | NA | NA | GRT051 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-15 | 2013-03-21 |  | 2013-03-21 | DONE
571 | BDG102_W_N | STORANCAEKEK | NA | NA | BDG102 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-16
572 | BDG981_W_N | PUNGKUR-SAWAHKURUNG | NA | NA | BDG981 | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-12 | [12 empty] | 2013-01-21 | 2013-02-26 | 2013-01-21 | 2013-02-26
573 | CRB124_W_N | SEDONGCIRBON | NA | NA | CRB124 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-19
574 | TSK119_W_N | RANCASALAH | NA | NA | TSK119 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-16
575 | GRT051_W_N | SAMPIREUN | NA | NA | GRT051 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-18
576 | BDG102_W_N | STORANCAEKEK | NA | NA | BDG102 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-20
577 | BDG981_W_N | PUNGKUR-SAWAHKURUNG | NA | NA | BDG981 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-17
578 | IND159_G_N | BLOKPILANGM | NA | NA | IND159 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-17
579 | TSK497_G_N | PASIRHUNIM | NA | NA | TSK497 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-18
580 | GRT219_G_N | CIMAPAGM | NA | NA | GRT219 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-18
581 | IND159_G_N_738-740 | BLOKPILANGM | NA | NA | IND159 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-10
582 | TSK497_G_N | PASIRHUNIM | NA | NA | TSK497 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
583 | GRT219_G_N | CIMAPAGM | NA | NA | GRT219 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-18
584 | IND159_G_N | BLOKPILANGM | NA | NA | IND159 | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  | 1091118159-4 | 2013-03-17
585 | TSK497_G_N | PASIRHUNIM | NA | NA | TSK497 | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-03-18
586 | GRT219_G_N | CIMAPAGM | NA | NA | GRT219 | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-03-18
587 | TSK531 | ISAT(PASIRWARU)-Cibeber | TSK017 | KRNGNUNGGAL | TSK531-TSK017 | MW DISMANTLE | MW0601_Dismantlement&Packing: MW 0.3/0.6m 2 |  |  | 2013-02-20 | 2013-02-20
588 | CMS242 | AXIS(Golat) | TSK390 | PANUMBANGAN | CMS242-TSK390 | MW DISMANTLE | MW0601_Dismantlement&Packing: MW 0.3/0.6m 2 |  |  | 2013-02-28 | 2013-02-28
589 | CMS242 | AXIS(Golat) | TSK097 | MANGGUNG | CMS242-TSK097 | MW DISMANTLE | MW0601_Dismantlement&Packing: MW 0.3/0.6m 2 |  |  | 2013-03-01 | 2013-03-01
590 | BDG910_W_N | AMOSEAS | NA | NA | BDG910 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-19 | 2013-03-21
591 | CRB043_W_N | CHIHIKEU | NA | NA | CRB043 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-19
592 | IND096_W_N | PRAPATAN | NA | NA | IND096 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-20 | 2013-03-21
593 | IND001_W_N | SUKAGUMIWANG | NA | NA | IND001 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-20 | 2013-03-22
594 | CRB097_W_N | WALED | NA | NA | CRB097 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna
595 | BDG713_W_N | SAGULING | NA | NA | BDG713 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-20 | 2013-03-22
596 | CMI057_G_N | INFANTRI CIMAHI/Brigif | NA | NA | CMI057 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-20 | 2013-03-21 | 2013-03-22 | DONE | [13 empty] | + swap existing antenna & return back to TSEL WH
597 | CMI042_G_N | Unjani-STOCimahi | NA | NA | CMI042 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-20 | 2013-03-21 | 2013-03-22 | DONE | [13 empty] | + swap existing antenna & return back to TSEL WH
598 | GRT263_G_N | Protel-Wanakerta | NA | NA | GRT263 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-21 | 2013-03-22 | 2013-03-22 | DONE
599 | BDG910_W_N | AMOSEAS | NA | NA | BDG910 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
600 | CRB043_W_N | CHIHIKEU | NA | NA | CRB043 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-03-18 |  | 2013-03-18 | DONE
601 | IND096_W_N | PRAPATAN | NA | NA | IND096 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
602 | IND001_W_N | SUKAGUMIWANG | NA | NA | IND001 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
603 | CRB097_W_N | WALED | NA | NA | CRB097 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
604 | BDG713_Dummy | SAGULING | NA | NA | BDG713 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1
605 | CMI057_G_N | INFANTRI CIMAHI/Brigif | NA | NA | CMI057 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-03-18 |  | 2013-03-18 | DONE
606 | CMI042_G_N | Unjani-STOCimahi | NA | NA | CMI042 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-03-18 |  | 2013-03-18 | DONE
607 | GRT263_G_N | Protel-Wanakerta | NA | NA | GRT263 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-03-18 |  | 2013-03-18 | DONE
608 | BDG910_W_N | AMOSEAS | NA | NA | BDG910 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-19 |  | 2013-03-18
609 | CRB043_W_N | CHIHIKEU | NA | NA | CRB043 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-19
610 | IND096_W_N | PRAPATAN | NA | NA | IND096 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-20
611 | IND001_W_N | SUKAGUMIWANG | NA | NA | IND001 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-20
612 | CRB097_W_N | WALED | NA | NA | CRB097 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6
613 | BDG713_W_N | SAGULING | NA | NA | BDG713 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-20
614 | CMI057_G_N | INFANTRI CIMAHI/Brigif | NA | NA | CMI057 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-20
615 | CMI042_G_N | Unjani-STOCimahi | NA | NA | CMI042 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-20
616 | GRT263_G_N | Protel-Wanakerta | NA | NA | GRT263 | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  | 1091118159-2 | 2013-03-21
617 | BDG180 | BCAKopo-Mekarpuspita | BDG721 | MEKARPUSPITA | BDG180-BDG721 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-20
618 | BDG006 | STORAJAWALI | BDG105 | TAMANSAKURA | BDG006-BDG105 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-03-20
619 | BDG180 | BCAKopo-Mekarpuspita | BDG721 | MEKARPUSPITA | BDG180-BDG721 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-20
620 | BDG006 | STORAJAWALI | BDG105 | TAMANSAKURA | BDG006-BDG105 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-20
621 | BDG694 | RNCKASUMBA | BDG141 | CIBISORO | BDG694-BDG141 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-02-26 | 2013-02-27
622 | BDG694 | RNCKASUMBA | BDG141 | CIBISORO | BDG694-BDG141 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-02-26
623 | KNG128 | XL-Cipicung Kuningan | KNG006 | CIPORANG | KNG128-KNG006 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-03-20
624 | GRT263_W_N | Protel-Wanakerta | NA | NA | GRT263 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  | 2013-03-18 |  |  | DONE
625 | GRT249_G_N | ISAT-MEKARMULYA | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-28 | 2013-03-30 | 2013-03-31 | DONE
626 | GRT249_G_N | ISAT-MEKARMULYA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-20 |  |  | 2013-03-31 | DONE
627 | GRT249_G_N | ISAT-MEKARMULYA |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-28
628 | SUB417_G_N | PROTEL-Pabuaran | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-28 | 2013-03-30 | 2013-03-31 | DONE
629 | SUB417_G_N | PROTEL-Pabuaran |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-28 |  |  | 2013-03-31 | DONE
630 | SUB417_G_N | PROTEL-Pabuaran |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-28
631 | CJR406_G_N | Cibulakan-HARIMARTCNJR | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-28 | 2013-03-30 | 2013-03-31 | DONE
632 | CJR406_G_N | Cibulakan-HARIMARTCNJR |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-28 |  |  | 2013-03-31 | DONE
633 | CJR406_G_N | Cibulakan-HARIMARTCNJR |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-28
634 | CMS238_G_N | AXIS-JELAT | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-28 | 2013-03-30 | 2013-03-31 | DONE
635 | CMS238_G_N | AXIS-JELAT |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-20 |  |  | 2013-03-31 | DONE
636 | CMS238_G_N | AXIS-JELAT |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-28
637 | BDG799_G_N | KEBONTUNGGULM | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-03-28 | 2013-03-30 | 2013-03-31 | DONE
638 | BDG799_G_N | KEBONTUNGGULM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-18 |  |  | 2013-03-31 | DONE
639 | BDG799_G_N | KEBONTUNGGULM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-03-28
640 | CMS020_W_N | CIMERAK | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-04-06 | 2013-04-07 | 2013-04-09 | DONE
641 | CMS020_W_N | CIMERAK |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24 |  |  | 2013-04-09 | DONE
642 | CMS020_W_N | CIMERAK |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4 |  |  | 2013-04-06
643 | TSK128_W_N | TOBONGJAYA | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-04-06 | 2013-04-07 | 2013-04-09 | DONE
644 | TSK128_W_N | TOBONGJAYA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-26 |  |  | 2013-04-09 | DONE
645 | TSK128_W_N | TOBONGJAYA |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-09 |  |  | DONE
646 | CMS055_W_N | BATUKARAS | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-06 | 2013-04-07 | 2013-04-09 | DONE
647 | CMS055_W_N | BATUKARAS |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24 |  |  | 2013-04-09 | DONE
648 | CMS055_W_N | BATUKARAS |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-06
649 | CMS055_W_N | BATUKARAS |  |  |  | OPTIONAL | Antenna Dismantlement&Packing |  |  |  |  | 2013-04-09 | DONE | [13 empty] | RNP : Replace Antenna GSM to DBXLH-9090C-VTM
650 | CMS055_W_N | BATUKARAS |  |  |  | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to WH; 1 SITE 1 TRIP |  |  | 2013-04-09 |  |  | DONE
651 | TSK100_W_N | CIBEBERTSK | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-04-09 | 2013-04-07 | 2013-04-09 | DONE
652 | TSK100_W_N | CIBEBERTSK |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-26 |  |  | 2013-04-09 | DONE
653 | TSK100_W_N | CIBEBERTSK |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4 |  |  | 2013-04-06 |  |  | DONE
654 | CMS022_W_N | CIGUGUR | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-06 | 2013-04-07 | 2013-04-09 | DONE
655 | CMS022_W_N | CIGUGUR |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24 |  |  | 2013-04-09 | DONE
656 | CMS022_W_N | CIGUGUR |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-06 |  |  | DONE
657 | TSK408_W_N | CIHERAS | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-04-06 | 2013-04-07 | 2013-04-09 | DONE
658 | TSK408_W_N | CIHERAS |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-26 |  |  | 2013-04-09 | DONE
659 | TSK408_W_N | CIHERAS |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4 |  |  | 2013-04-06 |  |  | DONE
660 | CMS072_W_N | CINTAKARYA | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-06 | 2013-04-07 | 2013-04-09 | DONE
661 | CMS072_W_N | CINTAKARYA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24 |  |  | 2013-04-09 | DONE
662 | CMS072_W_N | CINTAKARYA |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-06 |  |  | DONE
663 | GRT033_W_N | CULAMEGA | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-04-06 | 2013-04-07 | 2013-04-09 | DONE
664 | GRT033_W_N | CULAMEGA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-26 |  |  | 2013-04-09 | DONE
665 | GRT033_W_N | CULAMEGA |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4 |  |  | 2013-04-06 |  |  | DONE
666 | TSK098_W_N | DSNASOL | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-04-06 | 2013-04-07 | 2013-04-09 | DONE
667 | TSK098_W_N | DSNASOL |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24 |  |  | 2013-04-09 | DONE
668 | TSK098_W_N | DSNASOL |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4 |  |  | 2013-04-06 |  |  | DONE
669 | TSK404_W_N | DSSDKERTATSK | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-06 | 2013-04-07 | 2013-04-09 | DONE
670 | TSK404_W_N | DSSDKERTATSK |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24 |  |  | 2013-04-09 | DONE
671 | TSK404_W_N | DSSDKERTATSK |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-06 |  |  | DONE
672 | TSK404_W_N | DSSDKERTATSK |  |  |  | OPTIONAL | Antenna Dismantlement&Packing |  |  |  |  | 2013-04-09 | DONE | [13 empty] | RNP : Replace Antenna GSM to DBXLH-9090C-VTM
673 | TSK404_W_N | DSSDKERTATSK |  |  |  | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to WH; 1 SITE 1 TRIP |  |  | 2013-04-09 |  |  | DONE
674 | TSK120_W_N | KARYAWANGI | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-06 | 2013-04-10
675 | TSK120_W_N | KARYAWANGI |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-23
676 | TSK120_W_N | KARYAWANGI |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-06
677 | CMS187_W_N | KPSIGUNG | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-04-06 | 2013-04-08 | 2013-04-12 | DONE
678 | CMS187_W_N | KPSIGUNG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-23 |  |  | 2013-04-12 | DONE
679 | CMS187_W_N | KPSIGUNG |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4 |  |  | 2013-04-06 |  |  | DONE
680 | CMS190_W_N | Sukamajucms | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-06 | 2013-04-08 | 2013-04-12 | DONE
681 | CMS190_W_N | Sukamajucms |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-12 | DONE
682 | CMS190_W_N | Sukamajucms |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-06 |  |  | DONE
683 | CMS190_W_N | Sukamajucms |  |  |  | OPTIONAL | Antenna Dismantlement&Packing |  |  | 2013-04-06 |  |  | DONE
684 | CMS190_W_N | Sukamajucms |  |  |  | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to WH; 1 SITE 1 TRIP |  |  | 2013-04-06 |  |  | DONE | [13 empty] | RNP : Replace Antenna GSM to DBXLH-9090C-VTM
685 | CMS014_W_N | BANYUSARI | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-08 | 2013-04-11 | 2013-04-11 | DONE
686 | CMS014_W_N | BANYUSARI |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24 |  |  | 2013-04-11 | DONE
687 | CMS014_W_N | BANYUSARI |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-08 |  |  | DONE
688 | TSK080_W_N | NANGELASARI | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-08 | 2013-04-11 | 2013-04-11 | DONE
689 | TSK080_W_N | NANGELASARI |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-23 |  |  | 2013-04-11 | DONE
690 | TSK080_W_N | NANGELASARI |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-08 |  |  | DONE
691 | TSK080_W_N | NANGELASARI |  |  |  | OPTIONAL | Antenna Dismantlement&Packing |  |  | 2013-04-08 |  |  | DONE
692 | TSK080_W_N | NANGELASARI |  |  |  | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to WH; 1 SITE 1 TRIP |  |  | 2013-04-08 |  |  | DONE
693 | TSK080_W_N | NANGELASARI | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-08 | 2013-04-09 | 2013-04-12 | DONE
694 | TSK149_W_N | BAGOLO |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-26
695 | TSK149_W_N | BAGOLO |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-08 |  |  | DONE
696 | GRT012_W_N | CIPEUNDEUY | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-08 | 2013-04-09 | 2013-04-24 | DONE
697 | GRT012_W_N | CIPEUNDEUY |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-24 | DONE
698 | GRT012_W_N | CIPEUNDEUY |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-08 |  |  | DONE
699 | GRT012_W_N | CIPEUNDEUY |  |  |  | OPTIONAL | Antenna Dismantlement&Packing |  |  | 2013-04-08 |  |  | DONE
700 | GRT012_W_N | CIPEUNDEUY |  |  |  | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to WH; 1 SITE 1 TRIP |  |  | 2013-04-08 |  |  | DONE
701 | TSK064_W_N | GNGTANJUNG | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-08 | 2013-04-11 | 2013-04-11 | DONE
702 | TSK064_W_N | GNGTANJUNG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24 |  |  | 2013-04-11 | DONE
703 | TSK064_W_N | GNGTANJUNG |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-08 |  |  | DONE
704 | CMS076_W_N | HEGARMANAH | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-08 | 2013-04-11 | 2013-04-11 | DONE
705 | CMS076_W_N | HEGARMANAH |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-26 |  |  | 2013-04-11 | DONE
706 | CMS076_W_N | HEGARMANAH |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-08 |  |  | DONE
707 | CMS099_W_N | JLKAWASEN | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-08 | 2013-04-11 | 2013-04-11 | DONE
708 | CMS099_W_N | JLKAWASEN |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24 |  |  | 2013-04-11 | DONE
709 | CMS099_W_N | JLKAWASEN |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-08 |  |  | DONE
710 | GRT016_W_N | RANCABUAYA | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-08 | 2013-04-11 | 2013-04-17 | DONE
711 | GRT016_W_N | RANCABUAYA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
712 | GRT016_W_N | RANCABUAYA |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-08 |  |  | DONE
713 | SUB397_G_N | Sarengseng-Paponcol | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-08 | 2013-04-11 | 2013-04-15 | DONE
714 | SUB397_G_N | Sarengseng-Paponcol |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-20 |  |  | 2013-04-15 | DONE
715 | SUB397_G_N | Sarengseng-Paponcol |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-08 |  |  | DONE
716 | CMS222_G_N | KERTAMUKTI-CIKONDANG | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-02 | 2013-04-15 | 2013-04-17 | DONE
717 | CMS222_G_N | KERTAMUKTI-CIKONDANG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-18 |  |  | 2013-04-17 | DONE
718 | CMS222_G_N | KERTAMUKTI-CIKONDANG |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-02 |  |  | DONE
719 | CMS214_G_N | CIKEMBULAN-KEDONGREJO | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-02
720 | CMS214_G_N | CIKEMBULAN-KEDONGREJO |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
721 | CMS214_G_N | CIKEMBULAN-KEDONGREJO |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-02
722 | GRT298_W_N | Samarang-Cintarakyat | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-11 | 2013-04-13 | 2013-04-18 | DONE
723 | GRT298_W_N | Samarang-Cintarakyat |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-18 | DONE
724 | GRT298_W_N | Samarang-Cintarakyat |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-11 |  |  | DONE
725 | BDSXX4_W_N | TBG-Cijambe | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-17 | 2013-04-18 | 2013-04-22 | DONE
726 | BDSXX4_W_N | TBG-Cijambe |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-22 | DONE
727 | BDSXX4_W_N | TBG-Cijambe |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-17 |  |  | DONE
728 | BDG895_W_N | BDGN-54-dmtaxis | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-18 | 2013-04-20 | 2013-04-24 | DONE
729 | BDG895_W_N | BDGN-54-dmtaxis |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-24 | DONE
730 | BDG895_W_N | BDGN-54-dmtaxis |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-18 |  |  | DONE
731 | BDG375_G_N | CIPEUTANG | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-19 | 2013-04-20 | 2013-04-21 | DONE
732 | BDG375_G_N | CIPEUTANG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-25 |  |  | 2013-04-21 | DONE
733 | BDG375_G_N | CIPEUTANG |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-19 |  |  | DONE
734 | GRT201_G_N | KPPASIRENTIK | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-19 | 2013-04-20 | 2013-04-21 | DONE
735 | GRT201_G_N | KPPASIRENTIK |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-28 |  |  | 2013-04-21 | DONE
736 | GRT201_G_N | KPPASIRENTIK |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-19 |  |  | DONE
737 | SUB445_G_N | Ciasemhilir-Mandalawangi | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-19 | 2013-04-21 | 2013-04-25 | DONE
738 | SUB445_G_N | Ciasemhilir-Mandalawangi |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-25 | DONE
739 | CRB532_G_N | CIKALOM | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-19 | 2013-04-22 | 2013-04-22 | DONE
740 | CRB532_G_N | CIKALOM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-22 | DONE
741 | CRB532_G_N | CIKALOM |  |  |  | OPTIONAL | Antenna Dismantlement&Packing |  |  | 2013-04-19 |  |  | DONE
742 | CRB532_G_N | CIKALOM |  |  |  | LAST MILE DELIVERY | Antenna Replacement&Packing; Site to WH; 1 SITE 1 TRIP |  |  | 2013-04-19 |  |  | DONE
743 | COD002_W_N | Combat KM 120 | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-05 | 2013-04-07 | 2013-04-09 | DONE
744 | COD002_W_N | Combat KM 120 |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-12 | DONE
745 | COD002_W_N | Combat KM 120 |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-05 |  |  | DONE
746 | BDS079_W_N | STT Telkom | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-20 | 2013-04-21 | 2013-04-22 | DONE
747 | BDS079_W_N | STT Telkom |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-22 | DONE
748 | BDS079_W_N | STT Telkom |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6 |  |  | 2013-04-20 |  |  | DONE
749 | BDS134_W_N | IBC STT Telkom | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-04-21 | 2013-04-22 | 2013-04-23 | DONE
750 | BDS134_W_N | IBC STT Telkom |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-23 | DONE
751 | BDS134_W_N | IBC STT Telkom |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4 |  |  | 2013-04-21 |  |  | DONE
752 | BDS079_G_N | STT Telkom | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-04-21 | 2013-04-22 | 2013-04-23 | DONE
753 | BDS079_G_N | STT Telkom |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-04-23 | DONE
754 | BDS079_G_N | STT Telkom |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4 |  |  | 2013-04-21 |  |  | DONE
755 | TSK408 | CIHERAS | TSK362 | CIPATUJAH | TSK408-TSK362 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-38 | 2013-04-05 | 2013-04-06 | 2013-04-07 | DONE
756 | TSK408 | CIHERAS | TSK362 | CIPATUJAH |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
757 | TSK404 | DSSDKERTATSK | TSK362 | CIPATUJAH | TSK404-TSK362 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-42 | 2013-04-05 | 2013-04-06 | 2013-04-07 | DONE
758 | TSK404 | DSSDKERTATSK | TSK362 | CIPATUJAH |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
759 | GRT033 | CULAMEGA | TSK080 | NANGELASARI | GRT033-TSK080 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-38 | 2013-04-05 | 2013-04-06 | 2013-04-07 | DONE
760 | GRT033 | CULAMEGA | TSK080 | NANGELASARI |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
761 | TSK128 | TOBONGJAYA | GRT033 | CULAMEGA | TSK128-GRT033 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-38 | 2013-04-05 | 2013-04-06 | 2013-04-07 | DONE
762 | TSK128 | TOBONGJAYA | GRT033 | CULAMEGA |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
763 | CRB139 | CIPAKEMGR | KNG036 | CIBIRUANG |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-04-05 | [16 empty] | GCI do LMD; NEWRTN do by KMS
764 | CMS072 | CINTAKARYA | CMS020 | CIMERAK | CMS072-CMS020 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  | 1091117396-38 | 2013-04-05 | 2013-04-07 | 2013-04-09 | DONE
765 | CMS072 | CINTAKARYA | CMS020 | CIMERAK |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
766 | CMS055 | BATUKARAS | CMS010 | CIJULANG | CMS055-CMS010 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-42 | 2013-04-05 | 2013-04-07 | 2013-04-09 | DONE
767 | CMS055 | BATUKARAS | CMS010 | CIJULANG |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
768 | CMS010 | CIJULANG | CMS020 | CIMERAK | CMS010-CMS020 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-41 | 2013-04-05 | 2013-04-07 | 2013-04-09 | DONE
769 | CMS010 | CIJULANG | CMS020 | CIMERAK |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
770 | TSK149 | BAGOLO | TSK394 | KALIPUCANG | TSK149-TSK394 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-42 | 2013-04-05 | 2013-04-07 | 2013-04-09 | DONE
771 | TSK149 | BAGOLO | TSK394 | KALIPUCANG |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
772 | TSK394 | KALIPUCANG | CMS005 | CIGANJENG | TSK394-CMS005 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  | 1091117396-40 | 2013-04-05 | 2013-04-07 | 2013-04-09 | DONE
773 | TSK394 | KALIPUCANG | CMS005 | CIGANJENG |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
774 | TSK120 | KARYAWANGI | TSK065 | CITUNDUNG | TSK120-TSK065 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-41 | 2013-04-05 | 2013-04-15 |  | DONE
775 | TSK120 | KARYAWANGI | TSK065 | CITUNDUNG |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
776 | TSK065 | CITUNDUNG | TSK011 | KAWALU | TSK065-TSK011 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  | 1091117396-39 | 2013-04-05 | 2013-04-15 | 2013-04-17 | DONE
777 | TSK065 | CITUNDUNG | TSK011 | KAWALU |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
778 | TSK098 | DSNASOL | CMS008 | CIKONENG | TSK098-CMS008 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  | 1091117396-40 | 2013-04-05 | 2013-04-15 | 2013-04-17 | DONE
779 | TSK098 | DSNASOL | CMS008 | CIKONENG |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
780 | TSK064 | GNGTANJUNG | TSK006 | MANONJAYA | TSK064-TSK006 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  | 1091117396-38 | 2013-04-05 | 2013-04-15 | 2013-04-17 | DONE
781 | TSK064 | GNGTANJUNG | TSK006 | MANONJAYA |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
782 | TSK100 | CIBEBERTSK | TSK006 | MANONJAYA | TSK100-TSK006 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-04-05 | 2013-04-15 | 2013-04-17 | DONE
783 | TSK100 | CIBEBERTSK | TSK006 | MANONJAYA |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
784 | CMS076 | HEGARMANAH | CMS021 | CIDOLOK | CMS076-CMS021 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-41 | 2013-04-05 | 2013-04-15 | 2013-04-17 | DONE
785 | CMS076 | HEGARMANAH | CMS021 | CIDOLOK |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-05 |  |  | DONE
786 | SUB081 | KEMBANGSARI | SUB037 | WANTILAN | SUB081-SUB037 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-04-06 | 2013-04-08 | 2013-04-09 | DONE
787 | SUB081 | KEMBANGSARI | SUB037 | WANTILAN |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-06 |  |  | DONE
788 | SUB085 | POPONCOL | SUB016 | SARENGSENG | SUB085-SUB016 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-04-06 | 2013-04-08 | 2013-04-09 | DONE
789 | SUB085 | POPONCOL | SUB016 | SARENGSENG |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-06 |  |  | DONE
790 | BDG919 | CMBPURWADADI | SUB006 | KALIJATI | BDG919-SUB006 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-04-06 | 2013-04-08 | 2013-04-09 | DONE
791 | BDG919 | CMBPURWADADI | SUB006 | KALIJATI |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-06 |  |  | DONE
792 | SUB062 | WANAJAYA | SUB007 | MANDALAWANGI | SUB062-SUB007 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-04-06 | 2013-04-08 | 2013-04-09 | DONE
793 | SUB062 | WANAJAYA | SUB011 | TAMBAKDAHAN |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-06 |  |  | DONE
794
795
796 | SUB050 | MEKARJAYA | SUB020 | HAURGLSKOTAM | SUB050-SUB020 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-04-06 | 2013-04-08 | 2013-04-09 | DONE
797 | SUB050 | MEKARJAYA | SUB020 | HAURGLSKOTAM |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-06 |  |  | DONE
798 | BDG230 | SIMPANGDAGO | BDG229 | DAGOBSC | BDG230-BDG229 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-04-06 | 2013-04-08 | 2013-04-09 | DONE
799 | BDG230 | SIMPANGDAGO | BDG229 | DAGOBSC |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-06 |  |  | DONE
800 | BDG313 | simplengkong | BDG185 | TSEL | BDG313-BDG185 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  | 1091117396-40 | 2013-04-06 | 2013-04-08 | 2013-04-09 | DONE
801 | BDG313 | simplengkong | BDG185 | TSEL |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-06 |  |  | DONE
802 | CMS024 | CISEELCMS | CMS021 | CIDOLOK | CMS024-CMS021 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  |  | 2013-04-18 | 2013-04-20 | 2013-04-22 | DONE
803 | CMS024 | CISEELCMS | CMS021 | CIDOLOK |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  |  |  | 2013-04-22 | DONE
804 | CMS050 | SIDAMULIH | CMS021 | CIDOLOK | CMS050-CMS021 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  |  | 2013-04-18 | 2013-04-20 | 2013-04-22 | DONE
805 | CMS050 | SIDAMULIH | CMS021 | CIDOLOK |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  |  |  | 2013-04-22 | DONE
806 | TSK479 | PSRKIDULTSK | TSK006 | MANONJAYA | TSK479-TSK006 | MW NEW | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-19
807 | TSK479 | PSRKIDULTSK | TSK006 | MANONJAYA |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-04-19
808 | BDS079 | STT Telkom | BDG040 | DAYEUHKOLOT | BDS079-BDG040 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-04-19
809 | BDS079 | STT Telkom | BDG040 | DAYEUHKOLOT |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-04-19
810 | SMD019 | UJUNGJAYA | MJL002 | KADIPATEN | SMD019-MJL002 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4
811 | TSK034 | PAGERAGUNGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-44
812 | IND003 | STOINDRAMAYUM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-44
813 | TSK182 | DSJANGGALAM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-44
814 | TSK016 | SUKARAJAM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-44
815 | GRT077 | SUCIKALERM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-44
816 | GRT102 | DSNGAMPLANGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-44
817 | GRT142 | KADUNGSARIM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-44
818 | GRT006 | TAROGONGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-44
819 | GRT154 | KATAPANGSUCIM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
820 | CMI042 | SUDIRMANCMHM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
821 | GRT153 | CIPICUNGGRTM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-44
822 | GRT081 | BABAKANM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
823 | GRT139 | PANEMBONGGRTM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
824 | BDG100 | BUKITIPISM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
825 | BDG096 | BUKITPUTERANM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
826 | BDG421 | LIMALEMBANGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
827 | BDG744 | GRANDLEMBANGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
828 | BDG172 | CIMAREMEM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
829 | BDG691 | CIBACANGKLRM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
830 | BDG425 | BALICOMM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
831 | BDG505 | PENGKOLANM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
832 | BDG225 | BCAPDLARANGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-54
833 | CMS067 | GDGOLKARCMSM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
834 | BDG920 | CMBCISAGAM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
835 | SMD040 | JATIROKEM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
836 | BDG835 | CIGAGAKM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-56
837 | GRT011 | KRGPAWITANM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
838 | SUB018 | SUKAASIHM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
839 | GRT190 | PERUMCMPKGRTM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
840 | SUB051 | PARUNGHILIRM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
841 | BDG288 | RANCAPNGGUNGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-56
842 | BDG603 | WARUNGAWIM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-56
843 | CMS191 | WAHIDHASYIMM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-45
844 | GRT202 | OTTISTAGRTM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-46
845 | GRT188 | TNJGPURAGRTM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-46
846 | SUB003 | STOCIASEMM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-46
847 | SUB061 | PSRKAREUMBIM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-46
848 | SUB004 | STOSUBANGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-46
849 | GRT192 | KPPAMENDONGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-46
850 | CRB454 | CIKIJINGKOTAM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-46
851 | MJL003 | STOMJLENGKAM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-46
852 | BDG098 | STOBATUJAJARM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-56
853 | BDG103 | STOLEMBANGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-56
854 | SMD009 | JATINANGORM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
855 | CRB446 | CIRANGGANISM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report |  | 1091117097-46
856 | GRT246_G_N | MSJDKRGPAWITANMW | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna
857 | GRT246_G_N | MSJDKRGPAWITANMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-25
858 | GRT246_G_N | MSJDKRGPAWITANMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
859 | BJR030_G_N | TOSINBANJARMW | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna
860 | BJR030_G_N | TOSINBANJARMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-28
861 | BJR030_G_N | TOSINBANJARMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
862 | CJR420_W_N | DCI-Sindangjaya | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna
863 | CJR420_W_N | DCI-Sindangjaya |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
864 | CJR420_W_N | DCI-Sindangjaya |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + Ant&Feeder; CD6
865 | BDG952_G_N | DSCILAME | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
866 | BDG952_G_N | DSCILAME |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
867 | BDG952_G_N | DSCILAME |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
868 | BDG986_G_N | KUJANGSARI | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
869 | BDG986_G_N | KUJANGSARI |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
870 | BDG986_G_N | KUJANGSARI |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
871 | BDG290_G_N | CIPAGALO | NA | NA |  | BTS NEW | Macro BTS/NodeB: Hardware Installation, Supervision & PAT |  | 1091098837-29
872 | BDG290_G_N | CIPAGALO |  |  |  | CROSSCONNECT | BTS/NodeB: Microwave Cross-connection from BTS/NodeB to BSC/RNC |  | 1091098855-13
873 | BDG290_G_N | CIPAGALO |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
874 | BDG544_G_N | CIPADUNGKDL | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
875 | BDG544_G_N | CIPADUNGKDL |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
876 | BDG544_G_N | CIPADUNGKDL |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
877 | BDG903_G_N | CILEUNYIWETAN | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
878 | BDG903_G_N | CILEUNYIWETAN |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
879 | BDG903_G_N | CILEUNYIWETAN |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
880 | BDG866_G_N | JLCIKENDI | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
881 | BDG866_G_N | JLCIKENDI |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
882 | BDG866_G_N | JLCIKENDI |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
883 | BDG367_G_N | PASIRENDAH | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
884 | BDG367_G_N | PASIRENDAH |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
885 | BDG367_G_N | PASIRENDAH |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
886 | BDG975_G_N | CIHIDEUNGBDG | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
887 | BDG975_G_N | CIHIDEUNGBDG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
888 | BDG975_G_N | CIHIDEUNGBDG |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
889 | BDG499_W_N | BDGN-7-PsrmalakaProtel | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
890 | BDG499_Dummy | BDGN-7-PsrmalakaProtel |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-1
891 | BDG499_W_N | BDGN-7-PsrmalakaProtel |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
892 | BDG619_G_N | WARENGBDG | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
893 | BDG619_G_N | WARENGBDG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
894 | BDG619_G_N | WARENGBDG |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
895 | BDG981_G_N | CIATEULTNGH | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
896 | BDG981_G_N | CIATEULTNGH |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
897 | BDG981_G_N | CIATEULTNGH |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
898 | BDG198_G_N | BJNGLOAKALER | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
899 | BDG198_G_N | BJNGLOAKALER |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
900 | BDG198_G_N | BJNGLOAKALER |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
901 | BDG973_G_N | SANGKURIANG | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
902 | BDG973_G_N | SANGKURIANG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
903 | BDG973_G_N | SANGKURIANG |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
904 | BDG955_G_N | HOTELBANANA | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
905 | BDG955_G_N | HOTELBANANA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
906 | BDG955_G_N | HOTELBANANA |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
907 | BDG535_G_N | KPCIKADO | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
908 | BDG535_G_N | KPCIKADO |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
909 | BDG535_G_N | KPCIKADO |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
910 | BDS113_G_N | KPCISARANTA | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna
911 | BDS113_G_N | KPCISARANTA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
912 | BDS113_G_N | KPCISARANTA |  |  |  | LAST MILE DELIVERY | BTS/NodeB + No Power Sys + No Ant&Feeder; CD4
913 | BDS134 | TBG-Cijambe | BDG364 | PERMATABIRU | BDS134-BDG364 | MW NEW | MW0201_New: MW 0.3/0.6m 2
914 | BDSXX4 | TBG-Cijambe |  |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4
915 | CJR420 | DCI-Sindangjaya | BOO046 | STOCIPANAS | CJR420-BOO046 | MW NEW | MW0201_New: MW 0.3/0.6m 2
916 | CJR420 | DCI-Sindangjaya |  |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4
917 | CRB127 | BLKKBNTAJUGM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-46
918 | CRB127 | BLKKBNTAJUGM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-33
919 | CRB127 | BLKKBNTAJUGM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
920 | CRB127 | BLKKBNTAJUGM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
921 | CRB127 | BLKKBNTAJUGM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
922 | CRB050 | GEGESIKM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-46
923 | CRB050 | GEGESIKM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-33
924 | CRB050 | GEGESIKM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
925 | CRB050 | GEGESIKM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
926 | CRB050 | GEGESIKM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
927 | CRB057 | GEMPOLM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-46
928 | CRB057 | GEMPOLM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-33
929 | CRB057 | GEMPOLM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
930 | CRB057 | GEMPOLM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
931 | CRB057 | GEMPOLM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
932 | CRB071 | KALIMUKTIM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-46
933 | CRB071 | KALIMUKTIM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-33
934 | CRB071 | KALIMUKTIM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
935 | CRB071 | KALIMUKTIM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
936 | CRB071 | KALIMUKTIM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
937 | CRB102 | KLIWONM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-46
938 | CRB102 | KLIWONM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-33
939 | CRB102 | KLIWONM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
940 | CRB102 | KLIWONM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
941 | CRB102 | KLIWONM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
942 | BDG225 | BCAPDLARANGM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-47
943 | BDG225 | BCAPDLARANGM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-34
944 | BDG225 | BCAPDLARANGM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
945 | BDG225 | BCAPDLARANGM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
946 | BDG225 | BCAPDLARANGM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
947 | BDG853 | CAMPAKAPDLM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-46
948 | BDG853 | CAMPAKAPDLM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-33
949 | BDG853 | CAMPAKAPDLM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
950 | BDG853 | CAMPAKAPDLM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
951 | BDG853 | CAMPAKAPDLM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
952 | BDG100 | BUKITIPISM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-46
953 | BDG100 | BUKITIPISM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-33
954 | BDG100 | BUKITIPISM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
955 | BDG100 | BUKITIPISM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
956 | BDG100 | BUKITIPISM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
957 | BDG735 | KRGTANJUNGM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-46
958 | BDG735 | KRGTANJUNGM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-33
959 | BDG735 | KRGTANJUNGM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
960 | BDG735 | KRGTANJUNGM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
961 | BDG735 | KRGTANJUNGM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
962 | BDG835 | CIGAGAKM | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-46
963 | BDG835 | CIGAGAKM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
964 | BDG835 | CIGAGAKM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
965 | BDG835 | CIGAGAKM |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
966 | BDG835 | CIGAGAKM |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
967 | SMD021 | PADANAANPSHMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
968 | SMD021 | PADANAANPSHMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
969 | SMD021 | PADANAANPSHMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  | 1091118157-1
970 | SMD021 | PADANAANPSHMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
971 | SMD021 | PADANAANPSHMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
972 | SMD056 | CILANGKAPMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
973 | SMD056 | CILANGKAPMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
974 | SMD056 | CILANGKAPMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  | 1091118157-1
975 | SMD056 | CILANGKAPMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
976 | SMD056 | CILANGKAPMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
977 | SMD088 | CIKONDANGSMDMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
978 | SMD088 | CIKONDANGSMDMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
979 | SMD088 | CIKONDANGSMDMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  | 1091118157-1
980 | SMD088 | CIKONDANGSMDMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
981 | SMD088 | CIKONDANGSMDMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
982 | SUB018 | SUKAASIHMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
983 | SUB018 | SUKAASIHMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
984 | SUB018 | SUKAASIHMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  | 1091118157-1
985 | SUB018 | SUKAASIHMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
986 | SUB018 | SUKAASIHMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
987 | IND017 | JTBARANGKOTAMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
988 | IND017 | JTBARANGKOTAMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
989 | IND017 | JTBARANGKOTAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
990 | IND017 | JTBARANGKOTAMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
991 | IND017 | JTBARANGKOTAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
992 | IND020 | LELEAMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
993 | IND020 | LELEAMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
994 | IND020 | LELEAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
995 | IND020 | LELEAMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
996 | IND020 | LELEAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
997 | IND133 | KPLANGUTMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
998 | IND133 | KPLANGUTMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
999 | IND133 | KPLANGUTMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1000 | IND133 | KPLANGUTMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1001 | IND133 | KPLANGUTMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1002 | IND052 | PABEANUDIKMG | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
1003 | IND052 | PABEANUDIKMG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
1004 | IND052 | PABEANUDIKMG |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1005 | IND052 | PABEANUDIKMG |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1006 | IND052 | PABEANUDIKMG |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1007 | KNG048 | KAMPUNGLURAHMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
1008 | KNG048 | KAMPUNGLURAHMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
1009 | KNG048 | KAMPUNGLURAHMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1010 | KNG048 | KAMPUNGLURAHMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1011 | KNG048 | KAMPUNGLURAHMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1012 | KNG069 | KUWUKERTAMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
1013 | KNG069 | KUWUKERTAMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
1014 | KNG069 | KUWUKERTAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1015 | KNG069 | KUWUKERTAMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1016 | KNG069 | KUWUKERTAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1017 | BDG920 | CMBCISAGAMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
1018 | BDG920 | CMBCISAGAMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
1019 | BDG920 | CMBCISAGAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4 |  | 1091118157-1
1020 | BDG920 | CMBCISAGAMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1021 | BDG920 | CMBCISAGAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1022 | CMS066 | PULAUMAJUMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
1023 | CMS066 | PULAUMAJUMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
1024 | CMS066 | PULAUMAJUMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1025 | CMS066 | PULAUMAJUMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1026 | CMS066 | PULAUMAJUMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1027 | GRT074 | SUKARESIKMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
1028 | GRT074 | SUKARESIKMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
1029 | GRT074 | SUKARESIKMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1030 | GRT074 | SUKARESIKMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1031 | GRT074 | SUKARESIKMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1032 | TSK023 | CIAWIMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
1033 | TSK023 | CIAWIMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
1034 | TSK023 | CIAWIMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1035 | TSK023 | CIAWIMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1036 | TSK023 | CIAWIMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1037 | TSK034 | PAGERAGUNGMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-44
1038 | TSK034 | PAGERAGUNGMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-31
1039 | TSK034 | PAGERAGUNGMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1040 | TSK034 | PAGERAGUNGMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1041 | TSK034 | PAGERAGUNGMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1042 | TSK097 | MANGGUNGMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-45
1043 | TSK097 | MANGGUNGMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-32
1044 | TSK097 | MANGGUNGMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1045 | TSK097 | MANGGUNGMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1046 | TSK097 | MANGGUNGMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1047 | TSK179 | TEGALLEGATSKMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-45
1048 | TSK179 | TEGALLEGATSKMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-32
1049 | TSK179 | TEGALLEGATSKMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1050 | TSK179 | TEGALLEGATSKMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1051 | TSK179 | TEGALLEGATSKMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1052 | GRT077 | SUCIKALERMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-45
1053 | GRT077 | SUCIKALERMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-32
1054 | GRT077 | SUCIKALERMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1055 | GRT077 | SUCIKALERMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1056 | GRT077 | SUCIKALERMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1057 | GRT190 | PERUMCMPKGRTMD | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-45
1058 | GRT190 | PERUMCMPKGRTMD |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-32
1059 | GRT190 | PERUMCMPKGRTMD |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1060 | GRT190 | PERUMCMPKGRTMD |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1061 | GRT190 | PERUMCMPKGRTMD |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1062 | GRT202 | Pemdagrt-Tarogong | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-45
1063 | GRT202 | Pemdagrt-Tarogong |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-32
1064 | GRT202 | Pemdagrt-Tarogong |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1065 | GRT202 | Pemdagrt-Tarogong |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1066 | GRT202 | Pemdagrt-Tarogong |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1067 | CMS017 | PONPESDRLHDAMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
1068 | CMS017 | PONPESDRLHDAMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
1069 | CMS017 | PONPESDRLHDAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1070 | CMS017 | PONPESDRLHDAMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1071 | CMS017 | PONPESDRLHDAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1072 | CMS062 | KECBANJARMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
1073 | CMS062 | KECBANJARMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
1074 | CMS062 | KECBANJARMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1075 | CMS062 | KECBANJARMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1076 | CMS062 | KECBANJARMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1077 | CMS074 | SINDANGMANGUMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
1078 | CMS074 | SINDANGMANGUMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
1079 | CMS074 | SINDANGMANGUMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1080 | CMS074 | SINDANGMANGUMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1081 | CMS074 | SINDANGMANGUMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1082 | CMS087 | DSKRNGMULYAMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
1083 | CMS087 | DSKRNGMULYAMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
1084 | CMS087 | DSKRNGMULYAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1085 | CMS087 | DSKRNGMULYAMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1086 | CMS087 | DSKRNGMULYAMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1087 | CMS126 | CIPICUNGCMSMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-43
1088 | CMS126 | CIPICUNGCMSMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-30
1089 | CMS126 | CIPICUNGCMSMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1090 | CMS126 | CIPICUNGCMSMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1091 | CMS126 | CIPICUNGCMSMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1092 | GRT142 | KADUNGSARIMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-45
1093 | GRT142 | KADUNGSARIMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-32
1094 | GRT142 | KADUNGSARIMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1095 | GRT142 | KADUNGSARIMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1096 | GRT142 | KADUNGSARIMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1097 | GRT081 | BABAKANMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-45
1098 | GRT081 | BABAKANMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-32
1099 | GRT081 | BABAKANMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1100 | GRT081 | BABAKANMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1101 | GRT081 | BABAKANMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1102 | GRT102 | DSNGAMPLANGMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-45
1103 | GRT102 | DSNGAMPLANGMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-32
1104 | GRT102 | DSNGAMPLANGMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1105 | GRT102 | DSNGAMPLANGMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1106 | GRT102 | DSNGAMPLANGMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1107 | GRT139 | PANEMBONGGRTMW | NA | NA |  | BTS NEW | BTS0504_Swap: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  | 1091117396-45
1108 | GRT139 | PANEMBONGGRTMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-32
1109 | GRT139 | PANEMBONGGRTMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1110 | GRT139 | PANEMBONGGRTMW |  |  |  | BTS DISMANTLEMENT | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder
1111 | GRT139 | PANEMBONGGRTMW |  |  |  | LAST MILE DELIVERY | BTS/NodeB + NO POWER SYS + NO ANT&FEEDER; CD4
1112 | BJR002_W_N | BBKPERTAMINA | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna
1113 | BJR002_W_N | BBKPERTAMINA |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4
1114 | BJR002_W_N | BBKPERTAMINA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-24
1115 | BJR002 | BBKPERTAMINA | BJR001 | BANJARKOTA | BJR002-BJR001 | MW NEW | MW0201_New: MW 0.3/0.6m 2
1116 | BJR002-BJR001 |  |  |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4
1117 | CMS024 | CISEELCMS | TSK370 | LAKBOK | CMS024-TSK370 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  |  | 2013-05-07 | 2013-05-13 | 2013-05-31 | DONE
1118 | CMS024 | CISEELCMS | TSK370 | LAKBOK | CMS024-TSK370 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-05-07
1119 | CMS005 | CIGANJENG | CMS009 | BANJARSARI | CMS005-CMS009 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  |  | 2013-05-07 | 2013-05-13 | 2013-05-15 | DONE
1120 | CMS005 | CIGANJENG | CMS009 | BANJARSARI | CMS005-CMS009 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-05-07
1121 | TSK370 | LAKBOK | CMS005 | CIGANJENG | TSK370-CMS005 | MW NEW | MW0205_New: MW 1.8m 2 |  |  | 2013-05-08 | 2013-05-15 | 2013-05-30 | DONE
1122 | TSK370 | LAKBOK | CMS005 | CIGANJENG | TSK370-CMS005 | LAST MILE DELIVERY | MW 1.8m 2; CD6 |  |  | 2013-05-08
1123 | CMS009 | BANJARSARI | CMS024 | CISEELCMS | CMS009-CMS024 | MW NEW | MW0205_New: MW 1.8m 2 |  |  | 2013-05-09 | 2013-05-13 | 2013-05-15 | DONE
1124 | CMS009 | BANJARSARI | CMS024 | CISEELCMS | CMS009-CMS024 | LAST MILE DELIVERY | MW 1.8m 2; CD6 |  |  | 2013-05-09
1125 | CJR027 | MERKARGALIH | CJR335 | RAJAMANDALA | CJR027-CJR335 | MW NEW | MW0205_New: MW 1.8m 2 |  |  | 2013-05-11 | 2013-05-14 | 2013-05-15 | DONE
1126 | CJR027 | MERKARGALIH | CJR335 | RAJAMANDALA | CJR027-CJR335 | LAST MILE DELIVERY | MW 1.8m 2; CD6 |  |  | 2013-05-11
1127 | CJR051 | SALAGEDANG | CJR010 | CIAJAG | CJR051-CJR010 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  |  | 2013-05-10 | 2013-05-12 | 2013-05-13 | DONE
1128 | CJR051 | SALAGEDANG | CJR010 | CIAJAG | CJR051-CJR010 | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-05-10
1129 | CJR337_W_N | BOJONGPICUNGM | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-10 | 2013-05-15 | 2013-05-16 | DONE
1130 | CJR337_W_N | BOJONGPICUNGM |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-10
1131 | CJR337_W_N | BOJONGPICUNGM |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-16 | DONE
1132 | CJR027_W_N | MERKARGALIH | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-11 | 2013-05-13 | 2013-05-15 | DONE
1133 | CJR027_W_N | MERKARGALIH |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-11
1134 | CJR027_W_N | MERKARGALIH |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-15 | DONE
1135 | CJR051_W_N | SALAGEDANG | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-10 | 2013-05-13 | 2013-05-15 | DONE
1136 | CJR051_W_N | SALAGEDANG |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-10
1137 | CJR051_W_N | SALAGEDANG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-15 | DONE
1138 | SUB466_W_N | CMBCISALAKMD | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-10 | 2013-05-12 | 2013-05-23 | DONE
1139 | SUB466_W_N | CMBCISALAKMD |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-10
1140 | SUB466_W_N | CMBCISALAKMD |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-23 | DONE
1141 | SUB466_W_N | CMBCISALAKMD |  |  |  | OPTIONAL | BTS1008_Optional: Antenna Dismantlement&Packing |  |  |  |  | 2013-05-23 | DONE
1142 | CJR331_W_N | PAGELARANMG | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-10 | 2013-05-13 | 2013-05-23 | DONE
1143 | CJR331_W_N | PAGELARANMG |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-10
1144 | CJR331_W_N | PAGELARANMG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-23 | DONE
1145 | CJR061_W_N | MUARACIKADU | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-10 | 2013-05-13 | 2013-05-23 | DONE
1146 | CJR061_W_N | MUARACIKADU |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-10
1147 | CJR061_W_N | MUARACIKADU |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-23 | DONE
1148 | CJR061 | MUARACIKADU | CJR016 | SINDGBARANG | CJR061-CJR016 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-10 | 2013-05-15 | 2013-05-16 | DONE
1149 | CJR061 | MUARACIKADU | CJR016 | SINDGBARANG | CJR061-CJR016 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-10
1150 | CJR064_W_N | JAYAGIRI | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-10 | 2013-05-13 | 2013-05-23 | DONE
1151 | CJR064_W_N | JAYAGIRI |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-10
1152 | CJR064_W_N | JAYAGIRI |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-23 | DONE
1153 | BDG541 | PERUMADIPURA | BDG300 | NUANSAINDAH | BDG541-BDG300 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-11 | 2013-05-13 | 2013-05-14 | DONE
1154 | BDG541 | PERUMADIPURA | BDG300 | NUANSAINDAH | BDG541-BDG300 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-11
1155 | BDG837 | KOPORAYAPRM | BDG128 | KOPOSARI | BDG837-BDG128 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-12 | 2013-05-28 | 2013-05-29 | DONE
1156 | BDG837 | KOPORAYAPRM | BDG128 | KOPOSARI | BDG837-BDG128 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-12
1157 | BDG250 | STCILAME | BDG094 | GNGBENGKUNG | BDG250-BDG094 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-12 | 2013-05-15 | 2013-05-16 | DONE
1158 | BDG250 | STCILAME | BDG094 | GNGBENGKUNG | BDG250-BDG094 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-12
1159 | BDG237 | UNJANI | CMI008 | CIBEBERCMH | BDG237-CMI008 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-12 | 2013-05-15 | 2013-05-16 | DONE
1160 | BDG237 | UNJANI | CMI008 | CIBEBERCMH | BDG237-CMI008 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-12
1161 | BDG738 | BUKITINDAH | BDG106 | SARIJADI | BDG738-BDG106 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-12
1162 | BDG738 | BUKITINDAH | BDG106 | SARIJADI | BDG738-BDG106 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-12
1163 | CJR076 | CIWARUCJR | CJR016 | SINDGBARANG | CJR076-CJR016 | MW NEW | MW0205_New: MW 1.8m 2 |  |  | 2013-05-13 | 2013-06-15 | 2013-06-21 | DONE
1164 | CJR076 | CIWARUCJR | CJR016 | SINDGBARANG | CJR076-CJR016 | LAST MILE DELIVERY | MW 1.8m 2; CD6 |  |  | 2013-05-13
1165 | BDG309 | PACETCPRY | BDG112 | PSRCIPARAY | BDG309-BDG112 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-13 | 2013-05-14 | 2013-05-15
1166 | BDG309 | PACETCPRY | BDG112 | PSRCIPARAY | BDG309-BDG112 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-13
1167 | BDG942_W_N | DARAWATI | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-05-17 | 2013-05-29
1168 | BDG942_W_N | DARAWATI |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-17
1169 | BDG942_W_N | DARAWATI |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
1170 | BDG889_W_N | CISAID | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-05-15 | 2013-05-16 | 2013-05-17 | DONE
1171 | BDG889_W_N | CISAID |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-15
1172 | BDG889_W_N | CISAID |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-17 | DONE
1173 | BDG770_W_N | KPCIKALAGE | NA | NA |  | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-05-18 | 2013-05-21 | 2013-05-21 | DONE
1174 | BDG770_W_N | KPCIKALAGE |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-18
1175 | BDG770_W_N | KPCIKALAGE |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-21 | DONE
1176 | COD108_W_N | Combat Sumberkulon | NA | NA |  | BTS NEW | BTS0215_New: DBS RRU on tower (2 system) + No Power System + Antenna |  |  | 2013-05-15 | 2013-05-16 | 2013-05-17 | DONE
1177 | COD108_W_N | Combat Sumberkulon |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-15
1178 | COD108_G_N | Combat Sumberkulon |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-15 |  | 2013-05-17 | DONE
1179 | COD108_W_N | Combat Sumberkulon |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-17
1180 | COD108_W_N | Combat Sumberkulon |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-17 | DONE
1181 | COD108 | Combat Sumberkulon | MJL016 | LIGUNG | COD108-MJL016 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-15 | 2013-05-16 | 2013-05-16 | DONE | [13 empty] | LMD by NEC
1182 | CJR028_W_N | SIRNASARI | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-15 | 2013-05-17 | 2013-05-24 | DONE
1183 | CJR028_W_N | SIRNASARI |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-15
1184 | CJR028_W_N | SIRNASARI |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-24 | DONE
1185 | BDG892_W_N | KAWAHPUTIH | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-15 | 2013-05-17 | 2013-05-21 | DONE
1186 | BDG892_W_N | KAWAHPUTIH |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-15
1187 | BDG892_W_N | KAWAHPUTIH |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-21 | DONE
1188 | BDG896_W_N | BDGN-58-DMT3 | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-15 | 2013-05-17 | 2013-05-18 | DONE
1189 | BDG896_W_N | BDGN-58-DMT3 |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-15
1190 | BDG896_W_N | BDGN-58-DMT3 |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-27 |  |  | 2013-05-18 | DONE
1191 | BDG896 | BDGN-58-DMT3 | BDG769 | Hotel Horison | BDG896-BDG769 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-14 | 2013-05-15 | 2013-05-16 | DONE
1192 | BDG896 | BDGN-58-DMT3 | BDG769 | Hotel Horison | BDG896-BDG769 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-14
1193 | CJR019 | SINDGBARANG | CJR016 | TANGEUNG | CJR019-CJR016 | MW NEW | MW0205_New: MW 1.8m 2 |  |  | 2013-05-15 | 2013-05-23 | 2013-05-23 | DONE
1194 | CJR019 | SINDGBARANG | CJR016 | TANGEUNG | CJR019-CJR016 | LAST MILE DELIVERY | MW 1.8m 2; CD6 |  |  | 2013-05-15
1195 | TSK498_G_N | CIBAHAYU | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-20 | 2013-05-23 | 2013-05-24 | DONE
1196 | TSK498_G_N | CIBAHAYU |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-20
1197 | TSK498_G_N | CIBAHAYU |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-24 | DONE
1198 | CMS244_G_N | CIMURANGSANA | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-20 |  | 2013-05-24 | DONE
1199 | CMS244_G_N | CIMURANGSANA |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-20
1200 | CMS244_G_N | CIMURANGSANA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-28 |  |  | 2013-05-24 | DONE
1201 | BDG925_G_N | KPMARGALUYU | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-20 | 2013-05-21 | 2013-05-21 | DONE
1202 | BDG925_G_N | KPMARGALUYU |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-20
1203 | BDG925_G_N | KPMARGALUYU |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-21 | DONE
1204 | BDG896_G_N | BDGN-58-DMT3 | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-20
1205 | BDG896_G_N | BDGN-58-DMT3 |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-20
1206 | BDG896_G_N | BDGN-58-DMT3 |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
1207 | CJR076_W_N | CIWARUCJR | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-21 | 2013-05-23 | 2013-05-23 | DONE
1208 | CJR076_W_N | CIWARUCJR |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-21
1209 | CJR076_W_N | CIWARUCJR |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-23 | DONE
1210 | BDG943_W_N | Sadiplak-Tmnholis | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-23 | 2013-05-25 | 2013-05-25 | DONE
1211 | BDG943_W_N | Sadiplak-Tmnholis |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-23
1212 | BDG943_W_N | Sadiplak-Tmnholis |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  | 1091117097-40 |  |  | 2013-05-26 | DONE
1213 | BDG943 | Sadiplak-Tmnholis | BDG838 | TMNHOLISIDH | BDG943-BDG838 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-23 | 2013-05-24 | 2013-05-24 | DONE
1214 | BDG943 |  | BDG838 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-23
1215 | GRT309_W_N | Kec. Bungbulang | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-22 | 2013-05-23 | 2013-05-24 | DONE
1216 | GRT309_W_N | Kec. Bungbulang |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-22
1217 | GRT309_W_N | Kec. Bungbulang |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-24 | DONE
1218 | GRT309 | Kec. Bungbulang | GRT027 | BUNGBULANG | GRT309-GRT027 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-21 | 2013-05-22 | 2013-05-23 | DONE
1219 | GRT309 |  | GRT027 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-21
1220 | BDS135_G_N | BAROSTBG | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-23 | 2013-05-24 | 2013-06-26 | DONE
1221 | BDS135_G_N | BAROSTBG |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-23
1222 | BDS135_G_N | BAROSTBG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-26 | DONE
1223 | BDB025_G_N | SASAKSAATTBG | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-23 | 2013-05-24 | 2013-05-25 | DONE
1224 | BDB025_G_N | SASAKSAATTBG |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-23
1225 | BDB025_G_N | SASAKSAATTBG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-25 | DONE
1226 | BDB026_G_N | RAJAMANDALAKULONTBG | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-23 | 2013-05-24 | 2013-05-29 | DONE
1227 | BDB026_G_N | RAJAMANDALAKULONTBG |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-23
1228 | BDB026_G_N | RAJAMANDALAKULONTBG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-29 | DONE
1229 | SUB360 | BOJONEGARA | SUB026 | COMPRENGSBG | SUB360-SUB026 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-20 | 2013-05-31 | 2013-05-31 | DONE
1230 | SUB360 |  | SUB026 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-20
1231 | SUB357 | JATIBARU | SUB007 | MANDALAWANGI | SUB357-SUB007 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-20 | 2013-05-31 | 2013-05-31 | DONE
1232 | SUB357 | JATIBARU | SUB007 | MANDALAWANGI | SUB357-SUB007 | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-20
1233 | BDG079 | BABAKANSARI | BDG086 | ANTAPANI | BDG079-BDG086 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-20 | 2013-05-21 | 2013-05-21 | DONE
1234 | BDG079 |  | BDG086 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-20
1235 | SUB466 | CMBCISALAKMD | SUB041 | KASOMALANG | SUB466-SUB041 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-20 | 2013-05-21 | 2013-05-22 | DONE
1236 | SUB466 |  | SUB041 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-20
1237 | CJR028 | SIRNASARI | CJR027 | MERKARGALIH | CJR028-CJR027 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-20 | 2013-03-22 | 2013-03-23 | DONE
1238 | CJR028 |  | CJR027 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-20
1239 | CJR331 | PAGELARANMG | CJR019 | TANGEUNG | CJR331-CJR019 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-21 | 2013-05-22 | 2013-05-22 | DONE
1240 | CJR331 |  | CJR019 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-21
1241 | CJR064 | JAYAGIRI | CJR016 | SINDGBARANG | CJR064-CJR016 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-10 | 2013-05-12 | 2013-05-13 | DONE
1242 | CJR064 |  | CJR016 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-10
1243 | GRT307 | BDGN-187 (shift)-Netwave mapp sindang sari | GRT024 | CISURUPAN | GRT307-GRT024 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-23 | 2013-05-24 | 2013-05-26 | DONE
1244 | GRT307 |  | GRT024 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-23
1245 | GRT307_W_N | BDGN-187 (shift)-Netwave mapp sindang sari | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-24 | 2013-05-26 | 2013-05-29 | DONE
1246 | GRT307_W_N |  |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-24
1247 | GRT307_W_N |  |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-29 | DONE
1248 | GRT308 | BDGN-223-PsrMelatiNetwave mapp to sukamukti | TSK039 | SIRNAGALIH | GRT308-TSK039 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-23 | 2013-05-24 | 2013-05-26 | DONE
1249 | GRT308 |  | TSK039 |  |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-23
1250 | GRT308_W_N | BDGN-223-PsrMelatiNetwave mapp to sukamukti | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-24 | 2013-05-26 | 2013-05-29 | DONE
1251 | GRT308_W_N |  |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-24
1252 | GRT308_W_N |  |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-28 | DONE
1253 | BDG940_W_N | KPMULYANA | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-27 | 2013-05-28 | 2013-05-29 | DONE
1254 | BDG940_W_N |  |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-27
1255 | BDG940_W_N |  |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-29 | DONE
1256 | BDG868_G_N | SUKAASIHKOPO | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-25 | 2013-05-26 | 2013-05-27 | DONE
1257 | BDG868_G_N |  |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-25
1258 | BDG868_G_N |  |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-27 | DONE
1259 | BDG469_G_N | KRGSETRA | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-24 | 2013-05-25
1260 | BDG469_G_N |  |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-24
1261 | BDG469_G_N |  |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
1262 | CJR407_W_N | PASIRSEMBUNGMD | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-29 | 2013-05-30
1263 | CJR407_W_N | PASIRSEMBUNGMD |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-29
1264 | CJR407_W_N | PASIRSEMBUNGMD |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
1265 | CJR422_W_N | KPRWBANGOMD | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-29 | 2013-05-30 | 2013-05-31 | DONE
1266 | CJR422_W_N | KPRWBANGOMD |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-29
1267 | CJR422_W_N | KPRWBANGOMD |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-31 | DONE
1268 | CJR386_W_N | KBNPALACJRMG | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-21 | 2013-05-25 | 2013-05-25 | DONE
1269 | CJR386_W_N | KBNPALACJRMG |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-21
1270 | CJR386_W_N | KBNPALACJRMG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-25 | DONE
1271 | CJR330_W_N | PALASARICJRMG | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-29 | 2013-05-30 | 2013-05-31 | DONE
1272 | CJR330_W_N | PALASARICJRMG |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-29
1273 | CJR330_W_N | PALASARICJRMG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-31 | DONE
1274 | MJL124_G_N | MALAUSMA/KELAPADUA-CIKADUMJL | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-23 | 2013-05-24 | 2013-05-25 | DONE
1275 | MJL124_G_N | MALAUSMA/KELAPADUA-CIKADUMJL |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-25 | DONE
1276 | KNG116_G_N | MEKARJAYAKNG | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-24 | 2013-05-25 | 2013-05-25 | DONE
1277 | KNG116_G_N | MEKARJAYAKNG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-25 | DONE
1278 | BDS055_G_N | KELCIBIRUHILIR | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-28 | 2013-05-29 | 2013-06-01 | DONE
1279 | BDS055_G_N | KELCIBIRUHILIR |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-28
1280 | BDS055_G_N | KELCIBIRUHILIR |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-01 | DONE
1281 | BDG989_G_N | CIMENYAN | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-28 | 2013-05-29 | 2013-05-30 | DONE
1282 | BDG989_G_N | CIMENYAN |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-28
1283 | BDG989_G_N | CIMENYAN |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-30 | DONE
1284 | BDK141_G_N | KPCIPAHEUTKDL | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-28 | 2013-05-29 | 2013-05-30 | DONE
1285 | BDK141_G_N | KPCIPAHEUTKDL |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-28
1286 | BDK141_G_N | KPCIPAHEUTKDL |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-30 | DONE
1287 | BDB023_G_N | KPKUTALKSANA | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-28 | 2013-05-29 | 2013-05-30 | DONE
1288 | BDB023_G_N | KPKUTALKSANA |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-28
1289 | BDB023_G_N | KPKUTALKSANA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-30 | DONE
1290 | BDK138_G_N | JLNARADIREJA | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-28 | 2013-05-29 | 2013-05-30 | DONE
1291 | BDK138_G_N | JLNARADIREJA |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-28
1292 | BDK138_G_N | JLNARADIREJA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-30 | DONE
1293 | BDG971_G_N | LENGKONGBDGMW | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-29 | 2013-05-29 | 2013-05-30 | DONE
1294 | BDG971_G_N | LENGKONGBDGMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-29
1295 | BDG971_G_N | LENGKONGBDGMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-30 | DONE
1296 | BDG958_G_N | UNISBAMW | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-29 | 2013-05-29 | 2013-05-30 | DONE
1297 | BDG958_G_N | UNISBAMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-29
1298 | BDG958_G_N | UNISBAMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-30 | DONE
1299 | BDG800_G_N | DIPATIUKURMW | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-29 | 2013-05-29 | 2013-05-30 | DONE
1300 | BDG800_G_N | DIPATIUKURMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-29
1301 | BDG800_G_N | DIPATIUKURMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-30 | DONE
1302 | BDG798_G_N | HOTELGEULISMW | NA | NA |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-29 | 2013-05-29 | 2013-05-30 | DONE
1303 | BDG798_G_N | HOTELGEULISMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-29
1304 | BDG798_G_N | HOTELGEULISMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-05-30 | DONE
1305 | BDG230 | SIMPANGDAGO |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1306 | BDG165 | TGAGROBISNIS |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1307 | BDG866 | JLCIKENDIMD |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1308 | BDG094 | GNGBENGKUNGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1309 | BDG109 | TOLPDLARANGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1310 | BDG640 | CKALONGWETANM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1311 | BDG115 | KAYUAMBONM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1312 | BDG861 | GRAHABTNUNGLM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1313 | SMD137 | SUKAWNINGBDGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1314 | SUB071 | MARSINUM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1315 | IND107 | KALIMEANGM |  |  |  | SURVEY | BTS0101_Survey: BTS or BTS&MW Engineering Survey + Report
1316 | CMI087_W_N | BDGN-239-PABxl | NA | NA |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-22 | 2013-05-24
1317 | CMI087_W_N | BDGN-239-PABxl |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-22
1318 | CMI087_W_N | BDGN-239-PABxl |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC
1319 | CJR386 | KBNPALACJR | CJR025 | SUKALUYUCJR | CJR386-CJR025 | MW NEW | MW0201_New: MW 0.3/0.6m 2 |  |  | 2013-05-21 | 2013-05-22 | 2013-05-23 | DONE
1320 | CJR386 | KBNPALACJR | CJR025 | SUKALUYUCJR |  | LAST MILE DELIVERY | MW 0.3m/0.6m 2; CD4 |  |  | 2013-05-21
1321 | CMS011 | STDNGALUHCMS | TSK006 | MANONJAYA | CMS011-TSK006 | MW NEW | MW0203_New: MW 0.9/1.2m 2 |  |  | 2013-05-30 | 2013-05-31 | 2013-05-31 | DONE
1322 | CMS011 | STDNGALUHCMS | TSK006 | MANONJAYA |  | LAST MILE DELIVERY | MW 0.9m/1.2m 2; CD4 |  |  | 2013-05-31
1323 | CMS006 | RANCAHCIAMIS | CMS011 | STDNGALUHCMS | CMS006-CMS011 | MW NEW | MW0205_New: MW 1.8m 2 |  |  | 2013-05-31
1324 | CMS006 | RANCAHCIAMIS | CMS011 | STDNGALUHCMS |  | LAST MILE DELIVERY | MW 1.8m 2; CD6
1325 | GRT062_W_N | RNCAGONGGONG | NA | NA | GRT062 | OPTIONAL | Antenna Dismantlement&Packing
1326 | BDG910_W_N | AMOSEAS | NA | NA | BDG910 | OPTIONAL | Antenna Dismantlement&Packing
1327 | CRB043_W_N | CHIHIKEU | NA | NA | CRB043 | OPTIONAL | Antenna Dismantlement&Packing
1328 | CMI057_G_N | INFANTRI CIMAHI/Brigif | NA | NA | CMI057 | OPTIONAL | Antenna Dismantlement&Packing
1329 | CMI042_G_N | Unjani-STOCimahi | NA | NA | CMI042 | OPTIONAL | Antenna Dismantlement&Packing
1330 | TSK497_G_N | PASIRHUNIM | NA | NA | TSK497 | OPTIONAL | Antenna Dismantlement&Packing
1331 | TSK457_G_N | BARENGKOK-GNGOONG | NA | NA | TSK457 | OPTIONAL | Antenna Dismantlement&Packing
1332 | IND159_G_N | BLOKPILANGM | NA | NA | IND159 | OPTIONAL | Antenna Dismantlement&Packing
1333 | GRT219_G_N | CIMAPAGM | NA | NA | GRT219 | OPTIONAL | Antenna Dismantlement&Packing
1334 | SUB398_G_N | GARDUMUKTI | NA | NA | SUB398 | BTS NEW | BTS0208_New: DBS RRU on tower (1 system) + No Power System + No Antenna |  |  | 2013-06-04 | 2013-06-06 | 2013-06-08 | DONE
1335 | SUB398_G_N | GARDUMUKTI | NA | NA | SUB398 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-08 | DONE
1336 | SUB398_G_N | GARDUMUKTI | NA | NA | SUB398 | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-04
1337
1338
1339
1340 | GRT255 | XL(PASIRWANGI) | NA | NA | GRT255 | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-28 | 2013-05-31 | 2013-06-01 | DONE
1341 | GRT255 | XL(PASIRWANGI) | NA | NA | GRT255 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-01 | DONE
1342 | GRT255 | XL(PASIRWANGI) | NA | NA | GRT255 | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-28
1343 | BDG277 | Axis-Bukit Cilame | NA | NA | BDG277 | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-04 | 2013-06-06 | 2013-06-14 | DONE
1344 | BDG277 | Axis-Bukit Cilame | NA | NA | BDG277 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-14 | DONE
1345 | BDG277 | Axis-Bukit Cilame | NA | NA | BDG277 | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-04
1346 | BDG524 | SUKABUNGAHMW | NA | NA | BDG524 | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-29 | 2013-05-31 | 2013-06-07 | DONE
1347 | BDG524 | SUKABUNGAHMW | NA | NA | BDG524 | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-07 | DONE
1348 | BDG524 | SUKABUNGAHMW | NA | NA | BDG524 | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-29
| BDG960 | BUKITJARIANMW |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-29 | 2013-05-31 | 2013-06-08 | DONE
| BDG960 | BUKITJARIANMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-08 | DONE
| BDG960 | BUKITJARIANMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-29
| BDG952 | DSCILAME |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-05-01 | 2013-05-03 | 2013-06-10 | DONE
| BDG952 | DSCILAME |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-10 | DONE
| BDG952 | DSCILAME |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-05-01
| BDG972 | SUKAGALIH |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-11 | 2013-06-12 | 2013-06-14 | DONE
| BDG972 | SUKAGALIH |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-14 | DONE
| BDG972 | SUKAGALIH |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-11
| BDG767 | MARTADINATAMW |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-11 | 2013-06-12 | 2013-06-14 | DONE
| BDG767 | MARTADINATAMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-14 | DONE
| BDG767 | MARTADINATAMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-11
| IND160 | CILANDAKIND |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-13 | 2013-06-15 | 2013-06-24 | DONE
| IND160 | CILANDAKIND |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-24 | DONE
| IND160 | CILANDAKIND |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-13
| CMI086 | KELBAROSMW |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-13 | 2013-06-15 | 2013-06-15 | DONE
| CMI086 | KELBAROSMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-15 | DONE
| CMI086 | KELBAROSMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-13
| SUB464_G_N | Dangdeur-Cibogo |  |  |  | BTS NEW | BTS0215_New: DBS RRU on tower (2 system) + No Power System + Antenna |  |  | 2013-06-13 | 2013-06-15 | 2013-06-23 | DONE
| SUB464_G_N | Dangdeur-Cibogo |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-23 | DONE
| SUB464_G_N | Dangdeur-Cibogo |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-13
| BDB027 | Pakemitan-Rajamandala |  |  |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-13 | 2013-06-15 | 2013-06-19 | DONE
| BDB027 | Pakemitan-Rajamandala |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-19 | DONE
| BDB027 | Pakemitan-Rajamandala |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-13
| BDG616 | CIKUTRACCADASMW |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-18 | 2013-06-19 | 2013-06-20 | DONE
| BDG616 | CIKUTRACCADASMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-20 | DONE
| BDG616 | CIKUTRACCADASMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-18
| CMI083 | SADARMANAHMW |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-13 | 2013-06-14 | 2013-06-15 | DONE
| CMI083 | SADARMANAHMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-15 | DONE
| CMI083 | SADARMANAHMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-13
| BDG771 | BONGKORMW |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-13 | 2013-06-14 | 2013-06-18 | DONE
| BDG771 | BONGKORMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-18 | DONE
| BDG771 | BONGKORMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-13
| BDG734 | CANGKUANGKLNMW |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-15 | 2013-06-16 | 2013-06-19 | DONE
| BDG734 | CANGKUANGKLNMW |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-19 | DONE
| BDG734 | CANGKUANGKLNMW |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-15
| BDG778_W_N | CIAPUSMG |  |  |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-07 | 2013-06-08 | 2013-06-09 | DONE
| BDG778_W_N | CIAPUSMG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-09 | DONE
| BDG778_W_N | CIAPUSMG |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-07
| GRT296_W_N | Mekarsari-Panembong |  |  |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-07 | 2013-06-08 | 2013-06-10 | DONE
| GRT296_W_N | Mekarsari-Panembong |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-10 | DONE
| GRT296_W_N | Mekarsari-Panembong |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-07
| CJR406_W_N | LIMBANGANSARIMG |  |  |  | BTS NEW | BTS0303_Colo SRAN: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-12 | 2013-06-13 | 2013-06-15 | DONE
| CJR406_W_N | LIMBANGANSARIMG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-15 | DONE
| CJR406_W_N | LIMBANGANSARIMG |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-12
| CJR394_W_N | KPPASKOMD |  |  |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-12 | 2013-06-13 | 2013-06-15 | DONE
| CJR394_W_N | KPPASKOMD |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-15 | DONE
| CJR394_W_N | KPPASKOMD |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-12
| TSK406_W_N | SIRNAPUTRA |  |  |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-10 | 2013-06-12 | 2013-06-25 | DONE
| TSK406_W_N | SIRNAPUTRA |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-25 | DONE
| TSK406_W_N | SIRNAPUTRA |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-10
| IND148_W_N | GENDEREHMG |  |  |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-18 | 2013-06-19 | 2013-06-20 | DONE
| IND148_W_N | GENDEREHMG |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-20 | DONE
| CMS213_W_N | RYPGANDARANMD |  |  |  | BTS NEW | BTS0207_New: DBS RRU on tower (1 system) + No Power System + Antenna |  |  | 2013-06-21 | 2013-06-22 | 2013-06-23 | DONE
| CMS213_W_N | RYPGANDARANMD |  |  |  | CROSSCONNECT | BTS0901_E1 cross-connection from BTS/NodeB to BSC/RNC |  |  |  |  | 2013-06-23 | DONE
| CMS213_W_N | RYPGANDARANMD |  |  |  | LAST MILE DELIVERY | DBS RRU On Tower + NO POWER SYS + NO ANT&FEEDER; CD4 |  |  | 2013-06-21

## INDOSAT
Project Name : INDOSAT
63 | 68 | 68 | 49 | 49 | 49 | 49 | 68 | 1 | 68 | 43 | 38 | 17 | 17 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 3 | 0 | 0
[10 empty] | Job Description | [6 empty] | Document |  |  |  |  | ESAR
[10 empty] | Installation |  | Site Integration |  | ATP
No | Site ID NE | Site Name | Site ID FE | Site Name | NE-FE | SOW | PO Detail SOW | Project | PO Number Released | MOS Status | Installation Status | SI Date | SI Status | ATP Date | Punch list close date | ATP Status | SIR ID List that already approve by DC Region | email/transmittal submit SIR documents to QC | TSSR Documemt Submit Date | ATP Documemt Submit Date | BAST Approved Date | ESAR 1 SUBMITTED | ESAR 1 APPROVED | ESAR 2 SUBMITTED | ESAR 2 APPROVED | Document Complete Submit to Jakarta | Remark
1 | 03CMI008 | CIHANJUANG | NA | NA | NA | ANTENNA SYSTEM INSTALLATION | BBU INSTALLATION & COMMISSIONING | ；West Java_TE; 38218350000000 Engineering Name: Indosat 3 years of frame Swap and New Expantion Modernization project_no:5517626 | 1091112863-6 | 2012-12-20 | 2012-12-21 | 2012-12-21 | DONE | [13 empty] | temporary solution : install new Cabinet; use existing antenna & feeder
2 | 03BDG692 | SETRA_SARI | NA | NA | NA | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  | 1091112863-6 | 2012-12-28 | 2013-01-04 | 2013-01-04 | DONE | 2013-02-08 |  | DONE
3 | 03SRN261 | SARINTEN | NA | NA | NA | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  | 1091112863-6 | 2013-01-06 | 2013-03-22 | 2013-03-22 | DONE | 2013-05-27 |  | PENDING
4 | 03BDG024 | CIUMBULEUIT | NA | NA | NA | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  | 1091112863-6 | 2013-02-10 | 2013-02-13 | 2013-02-13 | DONE | 2013-02-27 |  | DONE
5 | 03BDG045 | NICOLE | NA | NA | NA | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  | 1091112863-6 | 2013-02-14 | 2013-02-18 | 2013-02-18 | DONE | 2013-05-15 |  | PENDING
6 | 03BDG015 | AL_KAUTSAR | NA | NA | NA | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  | 1091112863-6 | 2013-03-01 | 2013-03-04 | 2013-03-04 | DONE | 2013-05-10 |  | PENDING
7 | 03BDG023 | Jl.RIAU | NA | NA | NA | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  | 1091112863-6 | 2013-02-21 | 2013-03-04 | 2013-03-04 | DONE | 2013-05-12 |  | PENDING
8 | 03BDG088 | GUDANG SLT | NA | NA | NA | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  | 1091112863-6 | 2013-02-21 | 2013-02-26 | 2013-02-26 | DONE | 2013-05-14 |  | PENDING
9 | 03BDG086 | GARDUJATI | NA | NA | NA | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  | 1091112863-6 | 2013-02-24 | 2013-03-05 | 2013-03-05 | DONE
10 | 03CMI008 | CIHANJUANG | NA | NA | NA | DELIVERY | DELIVERY |  | 1091113036-15 | 2012-12-20 | [11 empty] | 2013-03-08
11 | 03BDG692 | SETRA_SARI | NA | NA | NA | DELIVERY | DELIVERY |  | 1091113036-15 | 2012-12-28
12 | 03SRN261 | SARINTEN | NA | NA | NA | DELIVERY | DELIVERY |  | 1091113036-15 | 2013-01-06
13 | 03BDG024 | CIUMBULEUIT | NA | NA | NA | DELIVERY | DELIVERY |  | 1091113036-15 | 2013-02-10
14 | 03BDG045 | NICOLE | NA | NA | NA | DELIVERY | DELIVERY |  | 1091113036-15 | 2013-02-14
15 | 03BDG015 | AL_KAUTSAR | NA | NA | NA | DELIVERY | DELIVERY |  | 1091113036-15 | 2013-02-16
16 | 03BDG015 | AL_KAUTSAR | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-02-16
17 | 03BDG023 | Jl.RIAU | NA | NA | NA | DELIVERY | DELIVERY |  | 1091113036-15 | 2013-02-21 | [11 empty] | 2013-03-08
18 | 03BDG088 | GUDANG SLT | NA | NA | NA | DELIVERY | DELIVERY |  | 1091113036-15 | 2013-02-21
19 | 03BDG086 | GARDUJATI | NA | NA | NA | DELIVERY | DELIVERY |  | 1091113036-15 | 2013-02-24 | [11 empty] | 2013-03-08
20 | 03BDG208 | MARANATHA | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-07 | 2013-03-10 | [10 empty] | 2013-03-08
21 | 03SRN120 | RRI_CIUMBULEUIT | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-08 | 2013-03-13
22 | 03BDG692 | SETRA_SARI | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  |  | 2013-01-04 | 2013-01-04 | DONE | 2013-02-08 |  | DONE
23 | 03SRN261 | SARINTEN | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  | 1091112863-6 | 2013-01-06 | 2013-03-22 | 2013-03-22 | DONE | 2013-05-27 |  | PENDING
24 | 03BDG024 | CIUMBULEUIT | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  | 1091112863-6 | 2013-02-10 | 2013-02-13 | 2013-02-13 | DONE | 2013-02-27 |  | DONE
25 | 03BDG045 | NICOLE | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  | 1091112863-6 | 2013-02-14 | 2013-02-18 | 2013-02-18 | DONE | 2013-05-15 |  | PENDING
26 | 03BDG015 | AL_KAUTSAR | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  | 1091112863-6 | 2013-03-01 | 2013-03-04 | 2013-03-04 | DONE | 2013-05-10 |  | PENDING
27 | 03BDG023 | Jl.RIAU | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  | 1091112863-6 | 2013-02-21 | 2013-03-04 | 2013-03-04 | DONE | 2013-05-12 |  | PENDING
28 | 03BDG088 | GUDANG SLT | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  | 1091112863-6 | 2013-02-21 | 2013-02-26 | 2013-02-26 | DONE | 2013-05-14 |  | PENDING
29 | 03BDG086 | GARDUJATI | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  | 1091112863-6 | 2013-02-24 | 2013-03-05 | 2013-03-05 | DONE
30 | 03BDG024 | CIUMBULEUIT | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  | 1091112863-6 | 2013-02-19 | 2013-02-19 | [15 empty] | + Dismantle : 2 BTS Cabinet & 1 Recti Cabinet
31 | 03BDG045 | NICOLE | NA | NA | NA | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER |  | 1091112863-6 |  | 2013-03-01 | [15 empty] | + Dismantle : 3 BTS Cabinet + 1 Recti Cabinet
32 | 03BDG015 | AL_KAUTSAR | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  | 1091112863-6 |  | 2013-03-05
33 | 03BDG023 | Jl.RIAU | NA | NA | NA | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  | 1091112863-6 |  | 2013-03-06
34 | 03BDG086 | GARDUJATI | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  | 1091112863-6 |  | 2013-03-04
35 | 03BDG024 | CIUMBULEUIT | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  | 2013-02-19 | 2013-02-19
36 | 03BDG045 | NICOLE | NA | NA | NA | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-03-01
37 | 03BDG045 | NICOLE | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-03-01
38 | 03BDG024 | CIUMBULEUIT | NA | NA | NA |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-02-25
39 | 03BDG045 | NICOLE | NA | NA | NA | BTS0810_Dismantlement&Packing: BTS/NodeB (3 system) + Power System + No Antenna&Feeder | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-03-03
40 | 03BDG015 | AL_KAUTSAR | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-03-05
41 | 03BDG015 | AL_KAUTSAR | NA | NA | NA | BTS0806_Dismantlement&Packing: BTS/NodeB (2 system) + Power System + No Antenna&Feeder | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-03-06
42 | 03BDG023 | Jl.RIAU | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-03-06
43 | 03BDG023 | Jl.RIAU | NA | NA | NA | BTS0810_Dismantlement&Packing: BTS/NodeB (3 system) + Power System + No Antenna&Feeder | BTS0801_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + Antenna& Feeder |  |  |  | 2013-03-07
44 | 03BDG088 | GUDANG SLT | NA | NA | NA | BTS0810_Dismantlement&Packing: BTS/NodeB (3 system) + Power System + No Antenna&Feeder | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-02-28
45 | 03BDG088 | GUDANG SLT | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-02-26
46 | 03BDG088 | GUDANG SLT | NA | NA | NA | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-02-27
47 | 03BDG088 | GUDANG SLT | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-02-26
48 | 03BDG208 | MARANATHA | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  |  | 2013-03-10
49 | 03SRN120 | RRI_CIUMBULEUIT | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  |  | 2013-03-13
50 | 03BDG091 | HOLIS | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-13 | 2013-03-16 | 2013-03-16 | DONE | 2013-05-17 |  | PENDING
51 | 03BDG091 | HOLIS | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-13 | 2013-03-16 | 2013-03-16 | DONE | 2013-05-17 |  | PENDING
52 | 03BDG091 | HOLIS | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-13
53 | 03BDG091 | HOLIS | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-13
54 | 03BDG015 | AL_KAUTSAR | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  | 1091112863-6 | 2013-03-01 | 2013-03-04 | 2013-03-04 | DONE | 2013-05-10 |  | PENDING
55 | 03BDG024 | CIUMBULEUIT | NA | NA | NA |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-02-25
56 | 03BDG086 | GARDUJATI | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-02-24 | 2013-03-05 | 2013-03-05 | DONE
57 | 03BDG088 | GUDANG SLT | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-02-21 | 2013-02-26 | 2013-02-26 | DONE | 2013-05-14 |  | PENDING
58 | 03BDG023 | Jl.RIAU | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-02-21 | 2013-03-04 | 2013-03-04 | DONE | 2013-05-12 |  | PENDING
59 | 03BDG045 | NICOLE | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-02-14 | 2013-02-18 | 2013-02-18 | DONE | 2013-05-15 |  | PENDING
60 | 03BDG692 | SETRA_SARI | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-01-04 | 2013-01-04 | 2013-01-04 | DONE | 2013-02-08 |  | DONE
61 | 03BDG017 | CISOKAN | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-13 | 2013-03-15 | 2013-03-15 | DONE | 2013-05-18 |  | PENDING
62 | 03BDG017 | CISOKAN | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-13 | 2013-03-15 | 2013-03-15 | DONE | 2013-05-18 |  | PENDING
63 | 03BDG017 | CISOKAN | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-13 | 2013-03-15 | 2013-03-15 | DONE
64 | 03BDG017 | CISOKAN | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-13 | 2013-03-15 | 2013-03-15 | DONE
65 | 03BDG017 | CISOKAN | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-03-16
66 | 03BDG017 | CISOKAN | NA | NA | NA | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-03-16
67 | 03SRN120 | BSM | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-16 | 2013-03-26 | 2013-03-26 | DONE
68 | 03SRN120 | BSM | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-16 | 2013-03-26 | 2013-03-26 | DONE
69 | 03CRN081 | SAMADIKUN | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-16 | 2013-03-22 | 2013-03-22 | DONE | 2013-05-30 |  | PENDING
70 | 03CRN081 | SAMADIKUN | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-16 | 2013-03-22 | 2013-03-22 | DONE | 2013-05-30
71 | 03CRN081 | SAMADIKUN | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-16 | 2013-03-22 | 2013-03-22 | DONE | 2013-05-30
72 | BDG193_3_S_0 | CIWARUGA | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-3 | 2012-12-19 | 2012-12-19 | [10 empty] | 2013-03-08 | 2013-03-11
73 | BDG190_G_S_0 | KOL_MASTURI_PL | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-3 | 2012-12-06 | 2012-12-11 | [10 empty] | 2013-03-08 | 2013-03-11
74 | BDG106_3_S_0 | SINDANGLAYA | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-3 | 2012-12-28 | 2013-01-04 | [10 empty] | 2013-03-08 | 2013-03-11
75 | CMI006_3_S_0 | GADOBANGKONG | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-4 | 2012-12-06 | 2012-12-11 | [10 empty] | 2013-03-08 | 2013-03-11
76 | SRN057_3_S_0 | PNRAMA_LEMBANG | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-5 | 2012-12-28 | 2013-01-04 | [10 empty] | 2013-03-08 | 2013-03-11
77 | SRN030_3_S_0 | LEMBANG | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-5 | 2013-02-04 | 2013-02-04 | [10 empty] | 2013-03-08 | 2013-03-11
78 | SRN180_G_S_0 | PASIRLANGU | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-5 | 2012-11-28 | 2012-12-07 | [10 empty] | 2013-03-08 | 2013-03-11
79 | SRN229_3_S_0 | CIPAGERAN_KMT | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-6 | 2012-12-11 | 2012-12-14 | [10 empty] | 2013-03-08 | 2013-03-11
80 | BDG248_G_S_0 | NDL_SENTRASARI | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-8 | 2012-12-20 | 2012-12-20 | [10 empty] | 2013-03-08 | 2013-03-11
81 | 03CRN017 | KARTINI_CRB | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-20 | 2013-03-30 | 2013-03-30 | DONE
82 | 03CRN017 | KARTINI_CRB | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-20 | 2013-03-30 | 2013-03-30 | DONE
83 | 03CRN017 | KARTINI_CRB | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-20 | 2013-03-30 | 2013-03-30 | DONE | 2013-05-30 |  | PENDING
84 | 03CRN017 | KARTINI_CRB | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-20 | 2013-03-30 | 2013-03-30 | DONE | 2013-05-30 |  | PENDING
85 | 03SRN025 | DAGO_PAKAR | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-20 | 2013-03-30 | 2013-03-30 | DONE
86 | 03SRN025 | DAGO_PAKAR | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-20 | 2013-03-30 | 2013-03-30 | DONE
87 | 03SRN025 | DAGO_PAKAR | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-20 | 2013-03-30 | 2013-03-30 | DONE
88 | 03CMI021 | Sariwangi | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-04-01 | 2013-04-18 | 2013-04-19 | DONE
89 | 03CMI021 | Sariwangi | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-01 | 2013-04-18 | 2013-04-19 | DONE | 2013-05-07 |  | PENDING
90 | 03CMI021 | Sariwangi | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-01 | 2013-04-18 | 2013-04-19 | DONE | 2013-05-07 |  | PENDING
91 | 03SRN054 | MARIBAYA | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-26
92 | 03SRN054 | MARIBAYA | NA | NA | NA | DELIVERY | DELIVERY |  |  | 2013-03-26
93 | 03SRN054 | MARIBAYA | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-26 | 2013-03-29 | 2013-03-29 | DONE
94 | 03SRN054 | MARIBAYA | NA | NA | NA | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-03-26 | 2013-03-29 | 2013-03-29 | DONE
97 | BDG091_3_S_0 | HOLIS | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-2
98 | 03SRN032 | CIHANJUANG 3 | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-5 | 2013-01-10 | 2013-01-16
99 | BDG003_3_S_0 | SUKASARI | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-1 | 2013-01-09 | 2013-01-16
100 | BDG015_3_S_0 | AL_KAUTSAR | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-1 | 2013-01-12 | 2013-01-12
101 | BDG017_3_S_0 | CISOKAN | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-1
102 | 03SRN183 | DCS_CIMAHIM | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-5 | 2013-03-09 | 2013-03-11
103 | 03CRN011 | BERLIAN_TIMUR | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-6 | 2013-03-13 | 2013-03-14
104 | 03CRN016 | SILIWANGI | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-7 | 2013-03-13 | 2013-03-15
106 | 03CRN035 | KECOMBERAN | NA | NA | NA | PRE-ASSEMBLE | PRE-ASSEMBLE |  | 1091113036-7 | 2013-03-20 | 2013-03-20
| BDG209_D_S_0 | _RSI_SANTOSA |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-4
| SRN119_3_S_0 | BJONGKONENG |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-5
| SRN039_3_S_0 | 3GIP_PASIR_LAYUNG |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-5
| SRN031_3_S_0 | LEMBANG_CITY |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-5
| SRN054_G_S_0 | MARIBAYA |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-5
109 | 03CRN110 | Trusmi_Kulon |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-04
110 | 03CRN110 | Trusmi_Kulon |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-04
111 | 03CRN110 | Trusmi_Kulon |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-04 | 2013-04-09 | 2013-04-09 | DONE | 2013-05-31 |  | PENDING
112 | 03CRN110 | Trusmi_Kulon |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-04 | 2013-04-09 | 2013-04-09 | DONE | 2013-05-31 |  | PENDING
113 | 03CRN110 | Trusmi_Kulon |  |  |  | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  |  | 2013-04-04 | 2013-04-09 | 2013-04-09 | DONE | 2013-05-31 |  | PENDING
114 | 03BDG081 | LBAK_Sariwangi |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-03 | 2013-04-10 | 2013-04-10 | DONE
115 | 03BDG081 | LBAK_Sariwangi |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-03 | 2013-04-10 | 2013-04-10 | DONE | 2013-05-21 |  | PENDING
116 | 03BDG081 | LBAK_Sariwangi |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-03 | 2013-04-10 | 2013-04-10 | DONE | 2013-05-21 |  | PENDING
117 | 03BDG081 | LBAK_Sariwangi |  |  |  | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  |  | 2013-04-03 | 2013-04-10 | 2013-04-10 | DONE | 2013-05-21 |  | PENDING
118 | 03BDG075 | WIRAYUDA |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-06 | 2013-04-10 | 2013-04-10 | DONE
119 | 03BDG075 | WIRAYUDA |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-06 | 2013-04-10 | 2013-04-10 | DONE | 2013-05-22 |  | PENDING
120 | 03BDG075 | WIRAYUDA |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-06 | 2013-04-10 | 2013-04-10 | DONE | 2013-05-22 |  | PENDING
121 | 03BDG075 | WIRAYUDA |  |  |  | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  |  | 2013-04-06 | 2013-04-10 | 2013-04-10 | DONE | 2013-05-22 |  | PENDING
122 | 03BDG111 | ARS |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-10 | 2013-04-11 | 2013-04-11 | DONE
123 | 03BDG111 | ARS |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-10 | 2013-04-11 | 2013-04-11 | DONE
124 | 03BDG111 | ARS |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-10 | 2013-04-11 | 2013-04-11 | DONE
125 | 03BDG069 | Parakansaat |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-05 | 2013-04-16 | 2013-04-16 | DONE
126 | 03BDG069 | Parakansaat |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-05 | 2013-04-16 | 2013-04-16 | DONE
127 | 03BDG069 | Parakansaat |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-05 | 2013-04-16 | 2013-04-16 | DONE
128 | 03BDG093 | Pungkur |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-10
129 | 03BDG093 | Pungkur |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-10 | 2013-04-17 | 2013-04-17 | DONE | 2013-05-24 |  | PENDING
130 | 03BDG093 | Pungkur |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-10 | 2013-04-17 | 2013-04-17 | DONE | 2013-05-24 |  | PENDING
131 | 03BDG093 | Pungkur |  |  |  | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  |  | 2013-04-10 | 2013-04-17 | 2013-04-17 | DONE | 2013-05-24 |  | PENDING
132 | 03CRB004 | Kangraksan |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-10
133 | 03CRB004 | Kangraksan |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-10 | 2013-04-12 | 2013-04-12 | DONE | 2013-05-31 |  | PENDING
134 | 03CRB004 | Kangraksan |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-10 | 2013-04-12 | 2013-04-12 | DONE | 2013-05-31 |  | PENDING
135 | 03CRB004 | Kangraksan |  |  |  | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  |  | 2013-04-10 | 2013-04-12 | 2013-04-12 | DONE | 2013-05-31 |  | PENDING
136 | 03BDG344 | Banda |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-18
137 | 03BDG344 | Banda |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-18 | 2013-04-25 | 2013-04-25 | DONE | 2013-05-16 |  | PENDING
138 | 03BDG344 | Banda |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-18 | 2013-04-25 | 2013-04-25 | DONE | 2013-05-16 |  | PENDING
139 | 03BDG344 | Banda |  |  |  | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  |  | 2013-04-18 | 2013-04-25 | 2013-04-25 | DONE | 2013-05-16 |  | PENDING
140 | 03CRN040 | Klanggenan |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-20 | 2013-04-22
141 | 03CRN040 | Klanggenan |  |  |  | DELIVERY | DELIVERY |  |  | 2013-04-20 | 2013-04-22
142 | 03CRN040 | Klanggenan |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-20 | 2013-04-22 | 2013-04-22 | DONE
143 | 03CRN040 | Klanggenan |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING |  |  | 2013-04-20 | 2013-04-22 | 2013-04-22 | DONE
144 | 03CRN040 | Klanggenan |  |  |  | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION |  |  | 2013-04-20 | 2013-04-22 | 2013-04-22 | DONE
145 | 03SRN062 | Cikantung |  |  |  | DELIVERY | DELIVERY
146 | 03SRN062 | Cikantung |  |  |  | DELIVERY | DELIVERY
147 | 03SRN062 | Cikantung |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING
148 | 03SRN062 | Cikantung |  |  |  | BBU INSTALLATION & COMMISSIONING | BBU INSTALLATION & COMMISSIONING
149 | 03SRN062 | Cikantung |  |  |  | ANTENNA SYSTEM INSTALLATION | ANTENNA SYSTEM INSTALLATION
150 | 03SRN261 | SARINTEN | NA | NA | NA | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-03-23
151 | 03SRN261 | SARINTEN | NA | NA | NA |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-05-25
152 | 03BDG045 | NICOLE |  |  |  |  | BTS0808_Dismantlement&Packing: BTS/NodeB (2 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-03-05
153 | 03BDG045 | NICOLE | DELIVERY (Site to WH); CD6 |  |  | 2013-04-05 | DELIVERY (Site to WH); CD6 |  |  | 2013-04-05
154 | 03BDG015 | AL_KAUTSAR |  |  |  |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-03-06
155 | 03SRN261 | SARINTEN |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-21
156 | 03BDG024 | CIUMBULEUIT |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-04-27
157 | 03BDG015 | AL_KAUTSAR |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-04-05
158 | 03BDG023 | Jl.RIAU |  |  |  |  | BTS0808_Dismantlement&Packing: BTS/NodeB (2 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-03-07
159 | 03BDG023 | Jl.RIAU |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-04-27
160 | 03BDG088 | GUDANG SLT |  |  |  |  | BTS0808_Dismantlement&Packing: BTS/NodeB (2 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-02-28
161 | 03BDG088 | GUDANG SLT |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-11
162 | 03BDG086 | GARDUJATI | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-03-04
163 | 03BDG086 | GARDUJATI | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-03-04
164 | 03BDG086 | GARDUJATI |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-03-08
165 | 03BDG086 | GARDUJATI |  |  |  |  | BTS0808_Dismantlement&Packing: BTS/NodeB (2 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-03-08
166 | 03BDG086 | GARDUJATI |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-15
167 | 03BDG091 | HOLIS |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-15
168 | 03BDG091 | HOLIS |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-15
169 | 03CRN081 | SAMADIKUN |  |  |  |  | ANTENNA SYSTEM INSTALLATION |  |  | 2013-03-16 | 2013-03-22 | 2013-03-22 | DONE | 2013-05-30
170 | 03CRN081 | SAMADIKUN |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  | 2013-03-22
171 | 03CRN081 | SAMADIKUN |  |  |  |  | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  | 2013-03-23
172 | 03CRN081 | SAMADIKUN |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-05-10
173 | 03CRN081 | SAMADIKUN |  |  |  |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-05-10
174 | 03CRN017 | KARTINI_CRB |  |  |  |  | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-04-02
175 | 03CRN017 | KARTINI_CRB |  |  |  |  | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-04-02
176 | 03CRN017 | KARTINI_CRB |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-04-02
177 | 03CRN017 | KARTINI_CRB |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-04-02
178 | 03CRN017 | KARTINI_CRB |  |  |  |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-04-02
179 | 03CRN017 | KARTINI_CRB |  |  |  |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-04-02
180 | 03BDG091 | HOLIS |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-16
181 | 03BDG017 | CISOKAN |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-11
182 | 03CRN081 | SAMADIKUN |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-22
183 | 03CRN017 | KARTINI_CRB |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-22
184 | 03SRN025 | DAGO_PAKAR |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER
185 | 03SRN025 | DAGO_PAKAR |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER
186 | 03CRN110 | Trusmi_Kulon |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-05-04
187 | 03CRN110 | Trusmi_Kulon |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-04
188 | 03CRN110 | Trusmi_Kulon |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-28
189 | 03BDG081 | LBAK_Sariwangi |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-04-11
190 | 03BDG081 | LBAK_Sariwangi |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-04-11
191 | 03BDG081 | LBAK_Sariwangi |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-04-25
192 | 03BDG081 | LBAK_Sariwangi |  |  |  |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-04-25
193 | 03BDG081 | LBAK_Sariwangi |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-15
194 | 03BDG075 | WIRAYUDA |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-04-23
195 | 03BDG075 | WIRAYUDA |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-04-23
196 | 03BDG075 | WIRAYUDA |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-04-23
197 | 03BDG075 | WIRAYUDA |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-04-23
198 | 03BDG075 | WIRAYUDA |  |  |  |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-04-23
199 | 03BDG075 | WIRAYUDA |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-18
200 | 03BDG093 | Pungkur |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-02
201 | 03BDG093 | Pungkur |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-02
202 | 03BDG093 | Pungkur |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-05-02
203 | 03BDG093 | Pungkur |  |  |  |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-05-02
204 | 03BDG093 | Pungkur |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-18
205 | 03CRB004 | Kangraksan |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-06
206 | 03CRB004 | Kangraksan |  |  |  |  | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-06
207 | 03CRB004 | Kangraksan |  |  |  |  | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-06
208 | 03CRB004 | Kangraksan |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-05-06
209 | 03CRB004 | Kangraksan |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-05-06
210 | 03CRB004 | Kangraksan |  |  |  |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-05-06
211 | 03CRB004 | Kangraksan |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-28
212 | 03CRN040 | Klanggenan |  |  |  |  | DISMANTLE UNIVERSAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-22
213 | 03CRN040 | Klanggenan |  |  |  |  | DISMANTLE SPECIAL ANTENNA MOUNTING & ANTENNA & FEEDER |  |  |  | 2013-05-22
214 | 03CRN040 | Klanggenan |  |  |  |  | BTS0802_Dismantlement&Packing: BTS/NodeB (1 system) + Power System + No Antenna&Feeder |  |  |  | 2013-05-22
215 | 03CRN040 | Klanggenan |  |  |  |  | BTS0804_Dismantlement&Packing: BTS/NodeB (1 system) + No Power System + No Antenna&Feeder |  |  |  | 2013-05-22
216 | 03CRN040 | Klanggenan |  |  |  |  | DELIVERY (Site to WH); CD6 |  |  | 2013-05-28
217 | 03CMI008 | CIHANJUANG | BBU INSTALLATION & COMMISSIONING |  |  |  | BBU INSTALLATION & COMMISSIONING
218 | CRN008_3_S_0 | 3GIP_PALIMANAN |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-6
219 | CRB022_3_S_0 | JL_ANYELIR |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-6
220 | CRB021_3_S_0 | 3G_JL_SUDARSONO |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-6
221 | CRN103_3_S_0 | 3G_SETUPATOK |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-7
222 | CRN110_3_S_0 | 3GIP_TRUSMI_KULON |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-7
223 | CRN086_G_S_0 | CANGKOAK |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-7
224 | CRN077_3_S_0 | 3G_MEGA_INDAH |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-7
225 | CRN065_3_S_0 | 3G_CIDENG |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-7
226 | CRN061_3_S_0 | 3GIP_TENGAH_TANI |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-7
227 | CRN055_G_S_0 | BAKUNG_LOR |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-7
228 | CRN034_G_S_0 | KARANGMULYA |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-7
229 | CRN023_G_S_0 | BOBOS |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-7
230 | CRN116_G_S_0 | SETUPATOK_CRN |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-8
231 | BDG341_G_S_0 | ISTANABUNGA |  |  |  |  | PRE-ASSEMBLE |  | 1091113036-8
|  |  | NA | NA | NA | PRE-ASSEMBLE
|  |  | NA | NA | NA | PRE-ASSEMBLE
|  |  | NA | NA | NA | PRE-ASSEMBLE
|  |  | NA | NA | NA | PRE-ASSEMBLE
|  |  | NA | NA | NA | PRE-ASSEMBLE

## AXIS
Project Name : AXIS
33 | 33 | 0 | 0 | 0 | 33 | 33 | 0 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Job Description | [6 empty] | Document |  |  |  |  | ESAR
[10 empty] | Installation |  | Site Integration |  | ATP
No | Site ID NE | Site Name | Site ID FE | Site Name | NE-FE | SOW | PO Detail SOW | Project | PO Number Released | MOS Status | Installation Status | SI Date | SI Status | ATP Date | Punch list close date | ATP Status | SIR ID List that already approve by DC Region | email/transmittal submit SIR documents to QC | TSSR Documemt Submit Date | ATP Documemt Submit Date | BAST Approved Date | ESAR 1 SUBMITTED | ESAR 1 APPROVED | ESAR 2 SUBMITTED | ESAR 2 APPROVED | Document Complete Submit to Jakarta | Remark
1 | JBSA002-JBSA005_MW_Mod | Sukamelang-Subang Kota |  |  | JBSA002-JBSA005 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511952 | 1091098837-2 | 2012-06-16 | 2012-06-26 | 2012-06-26 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
2 | JBSA005-JBSA006_MW_Mod | Subang Kota-Dangdeur-Subang |  |  | JBSA005-JBSA006 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511953 | 1091098837-2 | 2012-06-13 | 2012-06-26 | 2012-06-26 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
3 | JBSA006-JBSA026_MW_Mod | Dangdeur-Subang-Binong |  |  | JBSA006-JBSA026 | MW SWAP | MW PDH 1.8m 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511954 | 1091098837-2 | 2012-06-22 | 2012-06-27 | 2012-06-27 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
4 | JBSA008-JBSA001_MW_Mod | Cijengkol-Ciater |  |  | JBSA008-JBSA001 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511955 | 1091098837-2 | 2012-06-20 | 2012-06-26 | 2012-06-26 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
5 | JBKB056-JBBD011_MW_Mod | Cirangrang-Cibolerang |  |  | JBKB056-JBBD011 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511956 | 1091098837-2 | 2012-06-18 | 2012-06-22 | 2012-06-22 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
6 | JBKB062-JBKB056_MW_Mod | Istana Mekar Wangi-Cirangrang |  |  | JBKB062-JBKB056 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511957 | 1091098837-2 | 2012-06-21 | 2012-06-22 | 2012-06-22 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
7 | JBSA010-JBSA001_MW_Mod | Bunihayu-Ciater |  |  | JBSA010-JBSA001 | MW SWAP | MW PDH (0.9m/1.2m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511958 | 1091098837-2 | 2012-06-19 | 2012-06-22 | 2012-06-22 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
8 | JBSA012-JBSA001_MW_Mod | Curugrendeng-Ciater |  |  | JBSA012-JBSA001 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511959 | 1091098837-2 | 2012-06-19 | 2012-06-22 | 2012-06-22 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
9 | JBSA011-JBSA012_MW_NewHWIns | Sagala Herang-Curugrendeng |  |  | JBSA011-JBSA012 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511960 | 1091098837-2 | 2012-06-19 | 2012-06-22 | 2012-06-22 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
10 | JBBD050-JBBD052_MW_NewHWIns | Padalarang-2-Gunung Pamucatan |  |  | JBBD050-JBBD052 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511961 | 1091098837-2 | 2012-06-25 | 2012-06-25 | 2012-06-25 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
11 | JBBD053-JBBD050_MW_NewHWIns | Nyalindung / Cijengkol-Padalarang-2 |  |  | JBBD053-JBBD050 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511962 | 1091098837-2 | 2012-06-25 | 2012-06-28 | 2012-06-28 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
12 | JBBD055-JBBD052_MW_Mod | Cikalong Wetan-Gunung Pamucatan |  |  | JBBD055-JBBD052 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511963 | 1091098837-2 | 2012-06-25 | 2012-06-25 | 2012-06-25 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
13 | JBBD056-JBBD052_MW_Mod | PTPN VIII / Maswati-Gunung Pamucatan |  |  | JBBD056-JBBD052 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511964 | 1091098837-2 | 2012-06-25 | 2012-06-25 | 2012-06-25 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
14 | JBSA009-JBSA010_MW_Mod | Kasomalang Subang-Bunihayu |  |  | JBSA009-JBSA010 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511965 | 1091098837-2 | 2012-07-06 | 2012-07-23 | 2012-07-23 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
15 | JBSA060-JBSA001_MW_Mod | Cisaat Subang-Ciater |  |  | JBSA060-JBSA001 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511966 | 1091098837-2 | 2012-07-05 | 2012-07-05 | 2012-07-05 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
16 | JBCM043-JBCM042_MW_Mod | Batu Lawang-Banjar Kota |  |  | JBCM043-JBCM042 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511967 | 1091098837-2 | 2012-07-05 | 2012-07-06 | 2012-07-06 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
17 | JBCM032-JBCM043_MW_Mod | Bangun Sari-Batu Lawang |  |  | JBCM032-JBCM043 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511968 | 1091098837-2 | 2012-07-06 | 2012-07-25 | 2012-07-25 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
18 | JBCM015-JBCM003_MW_Mod | Cisaga-Purwaharja |  |  | JBCM015-JBCM003 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511969 | 1091098837-2 | 2012-07-30 | 2012-07-30 | 2012-07-30 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
19 | JBCM035-JBCM007_MW_Mod | Hegar Sari-Sinar jaya komunika |  |  | JBCM035-JBCM007 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511970 | 1091098837-2 | 2012-07-11 | 2012-07-13 | 2012-07-13 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
20 | JBSA015-JBSA004_MW_Mod | Rawalele-Pasir Rembi |  |  | JBSA015-JBSA004 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511971 | 1091098837-2 | 2012-07-11 | 2012-08-13 | 2012-08-13 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-06 | 2012-12-28
21 | JBSA004-JBSA006_MW_Mod | Pasir Rembi-Dangdeur-Subang |  |  | JBSA004-JBSA006 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511972 | 1091098837-2 | 2012-07-11 | 2012-07-12 | 2012-07-12 | DONE | [8 empty] | 2013-01-14 | 2013-02-06 | 2012-12-28
22 | JBSA007-JBSA004_MW_Mod | Cileuleuy-Pasir Rembi |  |  | JBSA007-JBSA004 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511973 | 1091098837-2 | 2012-07-11 | 2012-07-12 | 2012-07-12 | DONE | [8 empty] | 2013-01-14 | 2013-02-06 | 2012-12-28
23 | JBCM004-JBCM007_MW_Mod | Pataruman-Sinar jaya komunika |  |  | JBCM004-JBCM007 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511974 | 1091098837-2 | 2012-07-11 | 2012-07-18 | 2012-07-18 | DONE | [8 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
24 | JBCM007-JBCM042_MW_Mod | Sinar jaya komunika-Banjar Kota |  |  | JBCM007-JBCM042 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511975 | 1091098837-2 | 2012-07-11 | 2012-07-13 | 2012-07-13 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
25 | JBCM042-JBCM031_MW_Mod | Banjar Kota-Karang Kamulyan |  |  | JBCM042-JBCM031 | MW SWAP | MW PDH (0.9m/1.2m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511976 | 1091098837-2 | 2012-07-11 | 2012-07-20 | 2012-07-20 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
26 | JBCM031-JBCM011_MW_Mod | Karang Kamulyan -Ciamis Kota |  |  | JBCM031-JBCM011 | MW SWAP | MW PDH 1.8m 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511977 | 1091098837-2 | 2012-07-11 | 2012-07-19 | 2012-07-19 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
27 | JBCM003-JBCM042_MW_Mod | Purwaharja-Banjar Kota |  |  | JBCM003-JBCM042 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511978 | 1091098837-2 | 2012-07-26 | 2012-07-31 | 2012-07-31 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
28 | JBSA003-JBSA005_MW_Mod | R.A Kartini-Subang Kota |  |  | JBSA003-JBSA005 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511979 | 1091098837-2 | 2012-07-24 | 2012-07-25 | 2012-07-25 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
29 | JBSA001-JBBD051_MW_Mod | Ciater-PTPN (Ciater) |  |  | JBSA001-JBSA051 | MW SWAP | MW PDH (0.3m/0.6m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511980 | 1091098837-2 | 2012-07-24 | 2012-07-25 | 2012-07-25 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
30 | JBBD051-JBBD018_MW_Mod | PTPN (Ciater)-Lembang 2/Ridwan Nopandi |  |  | JBBD051-JBBD018 | MW SWAP | MW PDH (0.9m/1.2m) 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511981 | 1091098837-2 | 2012-07-31 | 2012-10-11 | 2012-10-11 | DONE |  |  | DONE | [5 empty] | 2013-01-14 | 2013-02-04 | 2012-12-28
31 | JBCM060-JBCM011_MW_Mod | Maleber Ciamis-Ciamis Kota |  |  | JBCM060-JBCM011 | MW MOD | Change IDU | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511982 | 1091111999-1 | 2012-09-08 | 2012-09-21 | 2012-09-21 | DONE |  |  | DONE | [5 empty] | 2013-01-14
32 | JBCM047-JBCM031_MW_Mod | Jajawar-Karang Kamulyan |  |  | JBCM047-JBCM031 | MW MOD | Change IDU | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511982 | 1091111999-1 | 2012-09-08 | 2012-09-19 | 2012-09-19 | DONE |  |  | DONE | [5 empty] | 2013-01-14
33 | JBCM011-JBTS023_MW_Mod | Ciamis Kota-Bunderan Suaka |  |  | JBTS023-JBCM011 | MW SWAP | MW PDH 2.4/2.5m 2: Installation and Commissioning | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511984 | 1091098837-2 | 2012-12-19 | [5 empty] | DONE | [5 empty] | 2013-02-04 | 2013-02-20
34 | JBGT004_2G/3G_ModS5 | Sukamantri | NA | NA | JBGT004 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511985 | 1091098837-3 | 2012-06-14 | 2012-06-22 | 2012-06-22 | DONE | [8 empty] | 2012-11-22 | 2012-12-26 | 2012-12-26
35 | JBGT006_2G/3G_ModS5 | Tarogong | NA | NA | JBGT006 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511986 | 1091098837-13 | 2012-06-15 | 2012-06-16 | 2012-06-16 | DONE | [8 empty] | 2012-11-22 | 2012-12-26 | 2012-12-26
36 | JBGT008_2G/3G_ModS5 | Flamboyan | NA | NA | JBGT008 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511987 | 1091098837-3 | 2012-07-11 | 2012-07-26 | 2012-07-26 | DONE | [8 empty] | 2012-11-22 | 2012-12-26 | 2012-12-26
37 | JBGT012_2G/3G_ModS5 | Karang Pawitan-Wanaraja | NA | NA | JBGT012 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511988 | 1091098837-10 | 2012-07-12 | 2012-07-26 | 2012-07-26 | DONE | [8 empty] | 2012-11-22 | 2012-12-26 | 2012-12-26
38 | JBKR032_2G/3G_ModS1 | Teluk Jambe | NA | NA | JBKR032 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511989 | 1091098837-8 | 2012-07-18 | 2012-07-24 | 2012-07-24 | DONE | 2012-11-09 | 2012-11-09 | DONE | [5 empty] | 2012-11-22 | 2012-12-20 | 2012-12-26
39 | JBCM003_2G/3G_ModS5 | Purwaharja | NA | NA | JBCM003 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511990 | 1091098837-1 | 2012-07-22 | 2012-07-24 | 2012-07-24 | DONE | 2012-11-09 | 2012-11-09 | DONE | [5 empty] | 2012-11-22 | 2012-12-20 | 2012-12-26
40 | JBCM015_2G/3G_ModS5 | Cisaga | NA | NA | JBCM015 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511991 | 1091098837-1 | 2012-07-22 | 2012-07-28 | 2012-07-28 | DONE | 2012-11-07 | 2012-11-07 | DONE | [5 empty] | 2012-11-22 | 2012-12-20 | 2012-12-26
41 | JBGT007_2G/3G_ModS5 | Cangkuang | NA | NA | JBGT007 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511992 | 1091098837-11 | 2012-07-24 | 2012-07-25 | 2012-07-25 | DONE | [8 empty] | 2012-11-22 | 2012-12-26 | 2012-12-26
42 | JBCM004_2G/3G_ModS5 | Pataruman | NA | NA | JBCM004 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511993 | 1091098837-1 | 2012-07-01 | 2012-07-02 | 2012-07-02 | DONE | 2012-11-10 | 2012-11-10 | DONE | [5 empty] | 2012-11-22 | 2012-12-20 | 2012-12-26
43 | JBGT003_2G/3G_ModS5 | Babakan Munawar | NA | NA | JBGT003 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511994 | 1091098837-12 | 2012-07-01 | 2012-07-02 | 2012-07-02 | DONE | [8 empty] | 2012-11-22 | 2012-12-26 | 2012-12-26
44 | JBBD076_2G/3G_ModS5 | Giri Asih | NA | NA | JBBD076 | BTS SWAP | Macro BTS/NodeB without Antenna & Feeder: Hardware Installation, Supervision & PAT | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091098837-3 | 2012-11-13 | 2012-11-13 | 2012-11-14 | DONE | [8 empty] | 2013-01-14 | 2013-02-06
45 | JBSA002-JBSA005 |  |  |  | JBSA002-JBSA005 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
46 | JBSA003-JBSA005 |  |  |  | JBSA003-JBSA005 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
47 | JBCM015-JBCM003 |  |  |  | JBCM015-JBCM003 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
48 | JBKB056-JBBD011 |  |  |  | JBKB056-JBBD011 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
49 | JBBD050-JBBD052 |  |  |  | JBBD050-JBBD052 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
50 | JBSA004-JBSA006 |  |  |  | JBSA004-JBSA006 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
51 | JBSA011-JBSA012 |  |  |  | JBSA011-JBSA012 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
52 | JBCM032-JBCM043 |  |  |  | JBCM032-JBCM043 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
53 | JBCM043-JBCM042 |  |  |  | JBCM043-JBCM042 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
54 | JBSA012-JBSA001 |  |  |  | JBSA012-JBSA001 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
55 | JBSA009-JBSA010 |  |  |  | JBSA009-JBSA010 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
56 | JBSA007-JBSA004 |  |  |  | JBSA007-JBSA004 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
57 | JBSA001-JBBD051 |  |  |  | JBSA001-JBBD051 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
58 | JBSA015-JBSA004 |  |  |  | JBSA015-JBSA004 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
59 | JBSA010-JBSA001 |  |  |  | JBSA010-JBSA001 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
60 | JBSA008-JBSA001 |  |  |  | JBSA008-JBSA001 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
61 | JBBD051-JBBD018 |  |  |  | JBBD051-JBBD018 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
62 | JBCM011-JBTS023 |  |  |  | JBCM011-JBTS023 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
63 | JBSA006-JBSA026 |  |  |  | JBSA006-JBSA026 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
64 | JBCM007-JBCM042 |  |  |  | JBCM007-JBCM042 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
65 | JBBD056-JBBD052 |  |  |  | JBBD056-JBBD052 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
66 | JBBD055-JBBD052 |  |  |  | JBBD055-JBBD052 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
67 | JBCM031-JBCM011 |  |  |  | JBCM031-JBCM011 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
68 | JBCM042-JBCM031 |  |  |  | JBCM042-JBCM031 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
69 | JBSA005-JBSA006 |  |  |  | JBSA005-JBSA006 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
70 | JBKB062-JBKB056 |  |  |  | JBKB062-JBKB056 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
71 | JBCM004-JBCM007 |  |  |  | JBCM004-JBCM007 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
72 | JBCM035-JBCM007 |  |  |  | JBCM035-JBCM007 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
73 | JBCM003-JBCM042 |  |  |  | JBCM003-JBCM042 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
74 | JBBD053-JBBD050 |  |  |  | JBBD053-JBBD050 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
75 | JBSA060-JBSA001 |  |  |  | JBSA060-JBSA001 | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-1 | [12 empty] | 2013-01-21 | 2013-02-06
76 | JBCM060-JBCM011_MW_Mod |  |  |  | JBCM060-JBCM011_MW_Mod | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-2 | [12 empty] | 2013-01-21 | 2013-02-20
77 | JBCM047-JBCM031_MW_Mod |  |  |  | JBCM047-JBCM031_MW_Mod | MW Cut Over at night |  | ；Banten (excluding Tangerang), Jawa Barat (excluding Bogor, Depok and Bekasi); 00036011139128 Engineering Name: Indonesia AXIS AMBER Project project_no:5511995 | 1091115745-2 | [12 empty] | 2013-01-21 | 2013-02-20